**IASC Protection Task Team Work Plan, 2016 – 2017 *(DRAFT 26 September 2016)***

| Objectives | Activities | Key Indicators | Focal Point/Contributing Organizations | Timeframe |
| --- | --- | --- | --- | --- |
| 1. Thorough and successful roll out of the IASC Protection Policy across the humanitarian system, including within humanitarian organisations, the humanitarian leadership, and inter-agency fora. | * 1. Further develop the roll out and implementation strategy for the IASC Protection Policy | * Overall approach to roll out and implementation agreed and supported by the IASC WG | Task Team | October 2016 |
| 1.2. Provide key stakeholders with tools and materials to support wide dissemination of the Protection Policy | * Wide dissemination to all key stakeholders with ERC cover letter * Materials posted on IASC website and used in briefings * Key stakeholders report positively on usefulness of materials | Task Team, in collaboration with key actors (e.g. IASC Secretariat, EDG, STAIT, GPC, OCHA  *[see more comprehensive list of key stakeholders below]* | October 2016 – February 2017 |
| 1. The institutionalization of the Centrality of Protection within humanitarian organisations, the humanitarian leadership, inter-agency fora, mechanisms, and decision-making processes, and in relation to other relevant stakeholders (see section B of the IASC Protection Policy roll out and implementation plan). | 2.1 Promote the implementation of the IASC Protection Policy, in liaison with other key stakeholders, including through integration into policies, guidance and management of humanitarian response activities | * Full coverage of all stakeholders identified in the strategy * #s of briefings, webinars, etc * Critical inter-agency policies and guidance material incorporate the Protection Policy | Task Team | October 2016 – December 2017 |
| 2.2 Promote practical support for country level implementation in close collaboration with relevant stakeholders | * Meeting records * Reports from country missions and reviews | Task Team | October 2016 – December 2017 |
| 1. Strategic and collective response to achieve protection outcomes in humanitarian crises. | 3.1 Undertake specific tasks identified by the IASC WG to advance the protection agenda. | * EDG, IASC WG, Principals agendas include critical protection issues and recommended actions relevant to the roles of these fora | Task Team  IASC Secretariat | Continuous, as per the dates of relevant meetings |
| 3.2 Keep the IASC WG informed of progress on the implementation of these tasks with a view to soliciting their advice and support. | * Key stakeholders report to the IASC WG on steps taken encourage implementation (periodic) * One report on experiences and lessons learned | Task Team | January 2017  July 2017  December 2017 |

***Notes:***

**Focal points**: currently the potential Task Team as a whole is identified as the Focal Point for facilitation of these activities. If and when this Task Team is created, specific focal points to lead the collaborative work of the Task Team will be fleshed out further. All activities will be carried out in close consultation with the key stakeholders of each activity.

**Key stakeholders** include:

* All IASC Principals, including the Emergency Relief Coordinator, the High Commissioner for Refugees, the High Commissioner for Human Rights
* All IASC members
* Humanitarian Coordinators
* Humanitarian Country Teams
* Emergency Directors Group
* STAIT
* OCHA Humanitarian Leadership Strengthening Unit (HLSU)
* Global Protection Cluster and field level protection clusters
* All Global Cluster Coordinators and field level cluster coordinators
* Inter-Cluster Coordination Group
* International NGOs
* National NGO Consortia
* National and local NGOs
* Donor governments
* National governments (as/if appropriate)