## Slide 1
26 March
OPAG meeting
March – May 2024
Consultation period**
6 June
OPAG in-person meeting
July
Desk review & Consolidating Outcomes of Consultations
30 September
Deputies in-person meeting
October/November
Announcement on IASC Subsidiary bodies for 2025
DRAFT* Timeline
Consultations to inform the Work of the IASC Subsidiary Bodies
Mid-May
Background document to inform OPAG discussion
August
Draft Note on Options for the 2025 IASC Subsidiary Bodies
October
Issuance of final Note on the IASC structures
15 May
Progress report of Task Forces and Associated Entities
* Subject to consultation with the ERC.
** Consultations will target IASC Chairs, members, and bodies. They will also include field leadership, NGO consortia members, local NGO representatives, donors, among others.
*** Timing is to be confirmed.
October
Consultation with the ERC & the IASC Principals***
December 2023
IASC Subsidiary bodies extended to the end of June 2024