2010 Calendar for the IASC WG Humanitarian Financing Group

(3 May 2010)

| Date | Operational Meeting | Policy Meeting |
| --- | --- | --- |
| 10 February | Finalize the proposed meeting topics and schedule for the IASC Group on Humanitarian Financing CERF Narrative Reporting Template |  |
| 10 March | Country-based pooled funds: Presentation of ToR for 3rd CHF Evaluation Discussion of agenda for CHF Working Group meeting Thematic Issues: Early recovery financing - preparatory discussions to identify the scope of our work Transaction costs - preparatory discussions on transaction costs to prioritize recommendations Funding for preparedness - preparatory discussions to identify the scope of our work November half-day meeting – initial identification of issues GHD: Decision on HFG approach to GHD |  |

| 24 March | CERF: Performance and Accountability Framework (PAF) Discussion of results of single country evaluation and consequences for PAF Discussion of Planning for CERF Five-Year Evaluation, including ToR |  |
| --- | --- | --- |
| 30 March | Country-based pooled funds: Report on outcome of CHF Working Group meeting Thematic Issues: Early recovery financing - further discussions to identify the scope of our work Transaction costs - further discussions on transaction costs to prioritize recommendations Funding for preparedness - further discussions to identify the scope of our work November half-day meeting – identification of issues |  |
| 28 April |  | Thematic Issues: Early recovery financing – decisions on scope of our work and workplan (inclusive of Montreux feedback) Transaction costs – decision on priority recommendations and workplan Funding for preparedness - decision on priority recommendations and workplan Agree on issues for November half-day meeting |
| 26 May | CERF: Discussion of CERF Annual Report Preparations for second UFE round |  |
| 23 June | CERF: CERF SG Report Country-based pooled funds: Update on 3rd CHF Evaluation, including presentation of inception report Discussion of agenda for CHF Working Group meeting Semi-annual review of CHF guidelines |  |
| 28 July |  | Thematic Issues Discussion of progress on early recovery, transition costs and funding for preparedness |
| August | No meeting Outcome of July CHF Working Group meeting circulated by email Planning for CERF Five-Year Evaluation circulated by email |  |

| 29 September | Thematic Issues: Planning discussion of HFG annual report Country-based pooled funds Semi-annual review of ERF guidelines |  |
| --- | --- | --- |
| 27 October |  | Thematic Issues: Discussion of progress on early recovery, transition costs and funding for preparedness |
| 10-12 November |  | Half-day discussion on humanitarian financing in IASC WG |
| 15 December | CERF: Results of the CERF Advisory Group meeting First UFE Round of 2011 Country-based pooled funds: Update on 3rd CHF Evaluation, including presentation of final report and findings Discussion of CHF Working Group December meeting Thematic issues: Endorsement of HFG annual report Endorsement of workplan for 2011 |  |