Inter-Agency Standing Committee

IASC Subsidiary Bodies

Report on Activities in 2007 by the Task Force on Mental Health and Psychosocial Support in Emergency Settings

# Report on Activities Undertaken in 2007

## Achievements of the Task Forces (TF) in line with the 2007 Work Plans endorsed by the IASC

In 2007, the TF completed the following activities in line with the endorsed Work Plans:

- Completion of the Guidelines (IASC WG endorsement in Feb 2007)

- Translation of the Guidelines in Arabic, French, and Spanish.  Because the quality of most good documents is often lost in translation, the Task Force conducted the following resource-intensive, multi-step process to ensure quality. (1) translation by a UN agency translation service, (2) subsequent technical editing of translated language by a contracted psychosocial specialist fluent in the relevant language (3) subsequent consultation (through teleconference) on technical edits through a reference group of psychosocial specialists fluent in the relevant language. Lessons learned: The time and resources required for technical proofreading of a translation are substantial and are at least equal to the time and resources needed for the original translation by a translation service.  The TF recommends this thorough process for the translation of all IASC technical documents.

- Design and printing of Guidelines in English (10,000 copies) has been completed. Design and printing of Guidelines in French (6,000 copies), Arabic (3000 copies) and Spanish (3000 copies) will be completed by the end of the 2007.

- Field testing was conducted in Sri Lanka. The field testing involved three, 2-day orientation workshops by two TF members observed by an independent evaluator, who returned 3 months after the workshops to evaluate potential impact. Please see Appendix A for the report on field testing in Sri Lanka. The TF has been invited to do field testing in Peru and Colombia, which will likely occur late 2007 or early 2008.  Please see section 1.3 for an explanation why field testing did not occur in 5 sites, the number that was specified in the 2007 TF Work Plan.

- According to the 2007 Work Plan, a toolkit was to be devised that supports effective implementation of the guidelines. A short, field version of the IASC Guidelines is in preparation and will be completed by the TF before the end of the year.  In addition, the TF has collected numerous Power Point presentations used in workshops on the Guidelines.

- Following the 2007 Work Plan, the Task Force engaged with Clusters, placing the Guidelines on the agenda in meetings of the Global Health, Protection (3x), and Nutrition Clusters. Although the IASC Guidelines are mainstreamed increasingly within Global Protection Cluster documents, the work on integrating the IASC Guidelines on Mental Health and Psychosocial Support in Emergency Settings in the work by the Clusters has just begun.

## Additional activities performed by the TF in 2007

- The IASC TF briefed the HLWG on 12 September 2007. Over 50 persons were present in the meeting, including ten donor countries. The TF asked HLWG donors to use the Guidelines to evaluate submitted proposals to ensure that funded projects are helpful rather than harmful. Since then, it has been reported that ECHO in Jordan is requiring funded agencies to comply with the Guidelines. ECHO also ordered 100 copies of the Guidelines for its staff in HQ.

- The TF organized the Global launch of the IASC Guidelines on 14 September 2007 with senior speakers from WHO, InterAction, UNICEF, UNHCR, IFRC ICVA and World Vision. A joint 26-agencypress release was widely disseminated on the day of the launch. The IASC Guidelines will be launched in India (Feb 2008), New York (Nov 20) and Washington, DC (Nov). OCHA has provisionally confirmed that Sir John Holmes will speak at the launch in NYC.

- A multi-agency, sub-regional Training of Trainers (ToT) on the Guidelines will be conducted in Nairobi this Fall for East Africa.

- Numerous other activities on the Guidelines are organized by TF agencies on all continents. Although these have not been organized collectively by the Task Force  and are thus not reflected in this report, the TF has learned this year that these “spontaneous” activities are highly valuable in promoting implementation.

## Opportunities and constraints faced by the TF

- The Task Force committed itself to field testing in five countries in 2007. To achieve this goal, the TF assertively suggested to colleagues in Sri Lanka that there would be field testing in February 2007, which indeed took place.  The lessons from this experience are described in Appendix A. It includes the key message that field testing, if it is to succeed, should probably not be initiated from the outside. To initiate from the outside is to risk overwhelming local capacities and undermining potential local ownership of the process, resulting in only limited implementation of the Guidelines. Rather, for a TF operating at the Global level, it makes much more sense to identify and support 'local champions' (i.e. IASC and non-IASC agency staff in countries who are interested in promoting implementation of the Guidelines locally). This process involves nurturing relationships with potential interested groups in countries, when opportunities arise. Although this process takes time, opportunities have arisen in Colombia (where the Government now has formally endorsed the Guidelines) and Peru. Field testing will likely begin in both these countries later this year.

- A key challenge that still needs to be addressed relates to the intersectoral nature of implementing the Guidelines. The Guidelines have provided an intersectoral framework because psychosocial work is cross-cutting.  There are currently great risks that implementation of the Guidelines will fall between the cracks of the Cluster system. As the TF will close by 31 December 2007, a proposal to the IASC will be submitted to consider setting-up an IASC Reference Group on Mental Health and Psychosocial Support in Emergency Settings to work with all Clusters - but especially with the Health Cluster and the cross-cutting Protection Cluster - to ensure that the Guidelines' recommendations will be integrated in the overall Cluster work. As explained in the companion proposal, the formation of a Reference Group would also enable the additional time needed to promote the implementation of the Guidelines.

# Status Update with Reference to Objectives Set in the 2007 Work Plan

| Objectives | Activities | Status / Update |
| --- | --- | --- |
| Collect data to guide decision about whether to revise the Guidance | Develop field testing questionnaires, refine methodology Identify key networks and agencies in focal sites Hire and prepare consultants Collect data from five focal sites and also from other sites | Field testing questionnaire was developed Data were formally collected in Sri Lanka. Similar data will be collected in Colombia and Peru likely this year or early 2008. |
| 2. Analyse data and decide whether to revise the guidance | Compile and analyse data Task Force meets to decide whether to revise immediately | A TF meeting was convened in Sep 2007, and it was decided that there is no need to revise the guidelines at this time. However, the TF believes that is important to collect more data, especially about how the Guidelines may be effectively introduced in emergencies. |
| 3. Revise guidance if indicated | Member agencies make revisions according to a plan agreed upon by the Task Force | Not applicable |
| 4. Support the early implementation of the guidance | Develop tools to support effective implementation Site visits by Task Force members to promote the guidance and build capacities for effective implementation Facilitate integration of Task Force recommendations into the work of different Clusters | A field version will be completed this year. Yet, additional ToT materials will be needed. Site visits have occurred in a range of countries through TF agencies, but a global roster of experts trained in the Guidelines is needed to help build both surge capacity and local capacities to scale up activities in countries Contacts with three Clusters have been established and briefings to these Clusters have been held. Representatives of the Health and Protection Clusters participated in the recent face-to-face TF meeting. The Protection Cluster has started to integrate the Guidelines' recommendations in its products. |

Appendix A: Report on field testing in Sri Lanka: Lessons from Sri Lanka

Lessons Learned and Recommendations on Orientation Workshops and Field Testing the IASC Guidelines on Mental Health and Psychosocial Support in Emergency Settings

Updated, final version: July 2007

Introduction

Initial ‘lessons learned’ from the field-testing process in Sri Lanka were synthesized by the IASC Task Force facilitators and external consultant at the end of the orientation workshops in March, 2007.  Additional feedback and comments from workshop participants and key agencies working in the mental health and psychosocial sectors were compiled in the Feedback Report written by the independent consultant at the end of July, 2007.

This compilation of key lessons learned and recommendations from field testing the IASC Guidelines on Mental Health and Psychosocial Support in Emergency Settings in Sri Lanka reflects both the objective information gained from feedback discussions and questionnaires, and the views of the IASC Task Force facilitators and the independent consultant.

1.  Objectives and Expectations of  Field Testing and Orientation Workshops

Prior to and during the ’field testing’ and workshops in Sri Lanka, there was some confusion as to the objectives of the workshops.  Some participants thought the purpose was to field test the Guidelines with a view to further revisions and adaptations of the Guidelines; others thought the objective was to learn how to implement the guidelines; and some participants expected to learn new technical skills to promote psychosocial approaches.  The lack of clarity regarding the objectives and expectations of the workshops resulted in very divergent expectations, and in the feedback discussions some participants expressed a sense of disappointment in both the process and outcome of the workshops.

Recommendations:

- The IASC Task Force needs to clarify and agree on the objectives of the ‘field-testing’:

- Is it really field-testing, with a view to revising the Guidelines according to the feedback at some future date?

- Is it an orientation, to introduce the Guidelines and seek endorsement and commitment from Government and agencies?

- Is it ‘early implementation’, which implies efforts to operationalize the Guidelines?

- Once the IASC Task Force agrees on the objectives of the ‘field testing’ process,  language and terminology should be revised to reflect the agreed objectives and expectations.  (We would recommend the use of ‘orientation’ or ‘case study’ rather than ‘field testing’.)

2.  Planning and Organisation of Workshops

In Sri Lanka, there were 5 weeks for organisers to plan the workshops. This was  insufficient time to brief agencies or participants on the purpose and objectives of the workshops, select appropriate participants, translate and distribute the guidelines (in local languages)  prior to the workshops, and arrange the logistics for the workshops.

Recommendations:

- At least 2 months preparation time is needed prior to orientation workshops to sensitize organisations, organise the logistics of the workshops, and prepare and distribute materials.

- The IASC Task Force should identify an agency or national consultant (perhaps through the IASC Country Team) who will accept responsibility and has the time to conceptualize and organize the orientation workshops. This work should be done through a consultative process that engages various local stakeholders and is sensitive to local issues of power and exclusion. It also involves the preparation and distribution of materials, provision of technical support, and post-orientation follow-up and evaluation.

- Funding must be provided for a period of six months, to cover the costs of the agency/personnel involved in organizing and implementing the workshops, workshop materials, technical support, and follow-up activities.

3.  Structure and Organisation of Workshops

The model of orientation workshops is useful in preparing  agencies and practitioners to use the IASC Guidelines, but workshops should be adjusted to respond to the country-specific context, and different levels, functions, and priorities of participating agencies.

In Sri Lanka, the workshops intermixed people whose primary work is psychosocial programming with people who work in sectors such as water/sanitation and shelter, and have limited exposure to psychosocial programming. Moreover, some of the workshops were very large with 40-50 participants, and participants varied greatly in terms of work experience and responsibilities within their agencies. With such large group size and great variability in the levels of expertise, experience, responsibility, and language ability, it was very difficult to engage all the participants in the most effective manner.

In feedback discussions, it was emphasized that the cultural norm and practice in Sri Lanka is top-down management and implementation strategies.   Many participants said that until the head of their agency commits to using the Guidelines, there was little they could do as individuals to promote the Guidelines.  They suggested that it would be preferable for the IASC Task Force members to first orient and introduce the guidelines with heads of agencies, to elicit willingness to support implementation of the guidelines within and through their own agencies.

Other participants felt the key role for IASC Task Force members was to advocate for the Government to accept the IASC Guidelines as an international standard.  In the current political context in Sri Lanka, they felt it was crucial to gain approval and commitment from the relevant Government ministries at national level, prior to introducing the Guidelines at district and local levels.  Indeed, this is the way UN agencies usually work when doing development, yet the question arises whether this should also be the case for IASC Guidelines. It takes years for Governments to adopt documents. Humanitarian actors should be able to take documents such as this forward without formal Government commitment, although that would be extremely helpful.

Recommendations for Orientation Workshops:

- It is very important to carefully select participants in workshops and not to issue open invitations to multiple-day workshops with invitations of all backgrounds and levels.

Based on ‘lessons learned‘ in Sri Lanka,  we would encourage consideration of a 3-tier model of orientation workshops., Yet, as no single model applies to all contexts, this model is not intended to lock local planners into a single approach. In fact, it is likely that local actors will create alternate models that may be much better adapted to their particular context.

First Tier (national-level, likely conducted in the capital): Orientation by IASC Task Force members with IASC country team (UN and NGO agency heads), government decision-makers in relevant government departments, and the relevant in-country IASC Cluster leaders. The objective of these orientation briefings and meetings would be to obtain government and agency commitment to endorse, integrate, implement and promote the guidelines.

Second Tier (national-level, likely conducted in the capital):  Five-day orientations for key MHPSS workers, both nationals and internationals, such as people who are psychosocial/mental health ‘focal points’, psychosocial/mental health coordinators, or otherwise technically responsible for psychosocial and mental health programmes in their agency/Department/Cluster in different regions of the country. Participants would thus come from multiple regions beyond the capital; include women, men, and members of different ethnic and religious groups; and would have expressed in advance a willingness to subsequently conduct an orientation workshop in their region, making this an ‘Orientation of Orienters’ (OoO) approach.

Facilitators for these ‘Orientation of Orienters’ should be a combination of IASC Task Force members and national focal points in MHPSS.

Third Tier: Orientation at regional and field level, facilitated by people who completed the five-day orientation workshop (second tier).  These diverse workshops would respond to the specific needs and context of each geographical region, be conducted in the local language(s), and could include:

- Orientation to regional-level UN / NGO agency field office heads, regional-level government decision-makers in relevant government departments, and the relevant regional-level IASC Cluster leaders

- Orientation to mental health/psychosocial staff on the guidelines (2-3 days). The participants would be mainly made up of staff that tend to attend MHPSS regional-level coordination meetings in emergencies. Participants would be informed in advance that the workshop will not teach them counseling or any other specific field skills (e.g. there will be no certificate!), that the orientation will focus on learning about the IASC framework for MHPSS, and that the workshops aim to lead to better MHPSS programming.  The number of participants in such orientation may need to be limited to a maximum of 20-25 people.

- Brief (e.g. ½ day - 1 day orientations) to people working in core humanitarian services (e.g. watsan, nutrition, food, general health services).  Participants would be informed in advance that the workshop will not teach them counseling or any other specific field skills, but that on the contrary the orientation will focus on learning about the IASC framework for MHPSS and that the workshops aim to lead to effective use of a MHPSS lens in normal humanitarian programming, to ensure that normal humanitarian programming does not undermine psychosocial well-being.

4.  Content and Format of the Guidelines

Based on the selected worksheets presented during the workshops and group exercises in the use and application of the Guidelines, workshop participants viewed the Guidelines as technically sound, and most participants saw them as relevant.  There was hardly any critique of the contents of the guidelines.

However, there was considerable feeling that the Guidelines are overwhelming, and should be formatted in a way that is more ‘user friendly’, and adapted to the local context.  In follow-up discussions by the independent consultant, it was found that very few participants or key actors in the MHPSS field had actually read or browsed the Guidelines, saying that they did not have the time to wade through such a dense document. The general message was: “the content is good and useful, but accessibility is difficult.”

Some workshop participants were unable to read the Guidelines due to delays in translating the document in full into Tamil and Sinhalese.  There were many divergent views as to the value of translating the document in full into local languages.  Many of the key actors felt that the quality of translations was poor, and distorted the content of the Guidelines.  Others thought that it would be preferable for each agency to select the relevant Action Sheets, and adapt and translate these for the field, instead of translating the document in full.

Recommendations:

- The IASC Task Force should develop and distribute a colorful, illustrated, user-friendly ‘Guide to the Guidelines’.

This introductory pamphlet should include:

WHAT: Describing the focus, function and global nature of the Guidelines

WHY:  	Emphasizing the need to maximize ‘lessons learned’ and minimize harm, and the 	importance of a multi-sectoral approach

HOW:	Describing the ways in which the Guidelines can be used as:

- A guide for policy-makers

- A check-list for program planning and emergency response

- A ‘reference book’ rather than a manual to be read in full

KEY CONCEPTS:  Outline the six Core Principles

- Add an index at the end of the guidelines, for easy reference.

- Colour-code the different Action Sheets

- Translations of the Guidelines into local languages should be discussed with key actors and the workshop organizers prior to the orientation workshops. The time and effort to produce quality translation of such large document should not be under-estimated (at least 2 months). It may be preferable to only translate the field version.

***