DRAFT:   Time Line: E-Learning on Gender Equality in Humanitarian Action  --  August 2007- October 2008

| Activities | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March | April | May | June | July | Aug. | Sept. | Oct. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SWG Reviews / provides feedback on InterAction Concept paper, TOR , Budget | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final TOR for hiring project manager circulated to SWG members and key consortia for broader circulation. | XX |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Advisory committee on E-Learning formed | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Staff person hired with SWG and Advisory Comte. input. |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review e-learning company data, identify three companies and solicit proposals/ Budgets. |  |  | XXXX | X |  |  |  |  |  |  |  |  |  |  |  |
| Outline key concepts for inclusion in E-Learning |  |  | XXXX |  |  |  |  |  |  |  |  |  |  |  |  |
| Review key concepts with Advisory Comte. |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |
| Categorize concepts into e-learning modules |  |  |  | XXXX |  |  |  |  |  |  |  |  |  |  |  |
| Review Chapter Content with Advisory Comte. |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |
| Develop E- lay out for each module* |  |  |  |  | XXX | XXX | XXX |  |  |  |  |  |  |  |  |
| Review Lay out with Advisory Comte. |  |  |  |  |  | X | X | X |  |  |  |  |  |  |  |
| Supply Lay out to E-learning technicians |  |  |  |  |  | XXX | XXX | XXXX | X |  |  |  |  |  |  |
| Review technical product and provide feedback |  |  |  |  |  |  | XXX | XXXX | XXX | XXX | XXX | XXX |  |  |  |
| Review technical product with Advisory Comte. |  |  |  |  |  |  | X | X | X | X | X | X |  |  |  |
| Field test technical product with humanitarian staff not working on Gender |  |  |  |  |  |  | XX | XX | XX | XX | XX | XX |  |  |  |
| Project Manager provides monthly progress reports to SWG |  | X | X | X | X | X | X | X | X | X | X | X |  |  |  |
| Interaction provides quarterly progress reviews/ updates to key stakeholders/ as needed. |  |  |  | X |  |  | X |  |  | X |  |  |  |  |  |
| Review each proposed final module with Advisory Comte. for final review and approval. |  |  |  |  |  |  |  | X | X | X | X | X | X |  |  |
| Final Layout and Production of CD-rom |  |  |  |  |  |  |  |  |  |  |  |  | XX |  |  |
| Dissemination Begins |  |  |  |  |  |  |  |  |  |  |  |  |  | XXX | XXX |
| To promote use of the E-learning tool through broad outreach with NGO and UN networks. |  |  | X | X | X | X | X | X | X | X | X | X | XXX | XXX | XXX |