Brief Note for the Record of the IASC TF Teleconference

June 2

Participants:

Marian (UNHCR)

Aslene  (IOM)

Katya (IOM)

Hilary (consultant)

By phone:

Alexander (UNDP)

Veronique (UNDP)

Hannah (OCHA)

Sarah (UNICEF)

Simona (MdM)

Ahmed (WHO)

Yuki (IASC Secretariat)

Annemarie (WFP)

Carol (FAO)

Thobias (UNAIDS Secretariat)

Nabina (UNAIDS Secretariat)

Agenda item 1): Update on the drafting of the Guidelines

Hilary gave a brief update on the status of the Guidelines. She informed that she now has working drafts of the glossary, introduction and coordination and planning chapters. OCHA is working on a section on emergency preparedness which will be included in the planning and coordination chapter. UNHCR informed that it is working on the M&E section which will be ready by this week. With regards to the action sheets, Hilary has received and is working on the ones on HIV awareness raising, health, protection, shelter, CCCM, and education, although the preamble for health is still missing. In addition, she still needs to receive action sheets for bullets points (three or four) under nutrition and livelihood support, and HIV in the workplace along with the overall preambles/introduction to the sectors (as had been agreed previously, sectors with two or more action sheets/bullet points will have a preamble).

Hilary also emphasized that the actual action sheets will only cover minimum response interventions (with a paragraph or so on preparedness and essential response).

The following action points agreed upon:

- All parties will send in their remaining inputs by June 6 (at the very latest).

- Hilary will send a complete first draft to all TF members by June 19.

- TF members will comment on this draft by June 26.

- Sub- working groups to send inputs to Hilary through the designated focal point.

Agenda item 2):  Field testing/peer review strategy

Simona and Sarah (as members of the working group on developing the field testing/peer review strategy) gave a brief update on what the group had been doing. Essentially, the group has been incorporating inputs received from TF members on the old field testing questionnaire. Following further discussions during the teleconference, it was agreed that the main objective of this exercise is to get inputs from the field to be able to finalize the Guidelines and that the questionnaire needed to be modified to reflect this (Hilary has suggested a draft). There were also discussions on using a two pronged approach to carrying out the field testing/peer review: 1) through country visits either by TF members and or regional focal points of agencies (especially if they are going to be traveling to the field during July and August) and 2) through the dissemination of the questionnaires to targeted people (i.e. specific clusters/sectors) for them to fill out. Furthermore, there was agreement that the questionnaire would be circulated/disseminated through cluster agencies (to the respective clusters) and within various agencies. In addition, there was general agreement that the questionnaire should be translated into French, Spanish and Portuguese and assistance to do so could be solicited from various agencies (like IOM who has taken on to translate it into Portuguese). Participants also agreed that a generic power point presentation which would be helpful in the field testing/peer review could/should be developed.  Hilary will be analyzing the parts of the questionnaire relevant to finalizing the Guidelines.

The following action points were agreed upon:

- The working group will update the concept note (based on the discussions above) and circulate it to the TF members by June 15

- All agencies to inform the working group on any travels that they or their regional focal points maybe undertaking during July and August and during which the guidelines could be field tested/reviewed (as soon as possible)

Agenda item 3): AOB

Kenya – members of the recent inter-agency team to Kenya shared their findings with the group. A mission report is forthcoming.

Myanmar – the UCC of Myanmar gave a brief update on the HIV response following the cyclone emphasizing that the three areas of focus at the moment are protection of children and women, reproductive health issues and looking at early warning systems to for changes in sex work patterns (due to migration, disruption of livelihoods etc. etc.)