Inter-Agency Standing Committee

Working Group Meeting

IASC Subsidiary Bodies

CAP SWG
Work Plan for 2008

# Narrative Summary

Consolidated and flash appeals are as much in demand as ever.  Improvements in response and coordination capacity on the ground, plus commitment by donors (still being fulfilled) to Good Humanitarian Donorship, provide an opportunity in the medium term to realize the CAP’s potential as a forum to assess needs and ensure that they are covered.  The CAP SWG in 2008 will focus on completing the adaptation of the CAP to new developments in humanitarian response, with the ultimate goal of credible planning and funding according to needs.

Sector leads under the cluster approach are in a position to solve many long-standing CAP problems: holistic joint needs assessment and analysis, influencing funding, mapping the response to the needs, selecting and prioritizing projects to be counted in the CAP, and monitoring at the level of strategic objectives.  The SWG will provide materials and other support as needed to capacitate sector leads to fulfill this role.

The SWG will support the dissemination, feedback and continual improvement of the IASC’s Needs Analysis Framework.  The related practice of strategic monitoring will be strengthened, to allow HCs, sector leads, and others responsible for humanitarian action to evaluate trends and meet emerging needs.  Adaptations such as these will be crystallized in an update of the 1994 IASC CAP guidelines.

The flash appeal system will be overhauled, with a view to taking best advantage of new financing methods such as CERF, and supporting country teams without humanitarian capacity to plan the response to sudden-onset disasters (which may remain frequent if climate change is the cause of 2007’s increased frequency of disasters).

The Montreux donor retreat on the CAP and related issues will review and endorse plans for CAP improvement, and (it is hoped) obtain donor commitments to play their part in realizing the potential of CAPs as they move towards Good Humanitarian Donorship.

In addition, the SWG will perform its core function re 2008 and 2009 CAPs, plus flash appeals as needed: support the field in each appeal’s development, review and finalise at HQ level, and publish and follow up on the appeals, including sharing information on appeal funding and continually updated funding requirements via FTS.

# Work Plan for 2008

| Activities | Expected Outcomes: | Focal Points | Timeframe | Results |
| --- | --- | --- | --- | --- |
| I: Develop and propose policy and guidelines for endorsement by the IASC WG on select priority issues to advance gains made in 2007 |
| Continue orienting cluster leads and HCs on responsibilities vis-à-vis CAP. NAF to be reviewed by cluster leads who failed to do so in 2007. Dissemination and trainings in the field to continue in collaboration with OCHA’s EPS section Strategic monitoring to be better incorporated in regular CAP guidelines, and easy tools to be made available, taking into account existing initiatives and building on available methods/tools. Provide inputs to other IASC and/or ECHA subsidiary bodies to ensure policy coherence on issues related to the CAP (e.g. TF on Gender, TF on HIV/AIDS in Emergencies, UNDG/ECHA WG on Transition). Revise the 1994 IASC Guidelines on the CAP to benefit from the recent developments in strategic thinking, approaches and strategies, e.g.: setting criteria for when to begin and when to end a CAP, clarifying the role of CAP in transition countries, place of early recovery, and outlining common law practice of government involvement in the CAP. Prioritisation and selection of projects process to be better defined; country teams to get easy-to-use tools. Flash appeals system overhaul to be agreed and implemented, including integration of early recovery elements. Humanitarian finance innovations to be integrated into CAPs and flash appeals | Better CAPs (better needs assessment, sectoral response plans, and project selection) through clear assignment of responsibility and accountability within country team. NAF to be used in 100% of CAP countries for 2009. Demonstrate the effectiveness of humanitarian action, and highlight gaps, by improving impact analysis of the CAP and trend analysis for crises. Participation in subsidiary body meetings as needed. Inputs provided to subsidiary body policies and guidelines as needed. Cross-cutting issues upheld in CAP guidelines and training tools 1994 IASC Guidelines on the CAP to be redrafted to provide criteria and mechanisms for initiating and ending a CAP, government and NGO involvement. Draft Guidelines to be prepared for preliminary endorsement of IASC WG meeting in June Full funding for greatest priorities Better response to sudden-onset disasters in anticipation of frequent climate-change-related emergencies Better balanced, more timely humanitarian response by taking advantage of interactions between appeals and new financing instruments. | IASC CAP SWG OCHA and Agencies OCHA SWG members IASC CAP SWG IASC-WG IASC CAP SWG IASC CAP SWG IASC CAP SWG | Year-round Year-round Year-round Year-round By December For 2009 CAP season By end 2008 By end 2008 | Most (7/12 CAP countries) formally implement the cluster approach. The other countries have all reviewed their coordination mechanisms, and the FTS can now accommodate any non-standard coordination scheme. Documents drafted and circulated detailing role of HCs and cluster leads in the CAP, as part of CAP 2009 Guidelines. By end of year, a refined version, taking the new cluster tools into account, will be finalised. By mid-year, most country teams were able to monitor outputs against their objectives. Evaluation of impact should be strengthened, but will require a sophisticated and cluster-level approach for methodological reasons. Detailed guidance on M&E for common humanitarian funds, applicable to CAPs in general, is now available. Done Under way By the 2008 CAP Mid-year reviews, most CAPs are prioritized. Donors’ response to such consensual priorities has been analysed (they follow the priorities more often than not, though there is room for improvement) and circulated to donors; this measurement should be included as a GHD performance indicator. Under way. FA overhaul paper drafted and endorsed, partially implemented; guidelines/tools being created. CERF interacts productively with the flash appeal and CAP processes. ERFs, and pilot new CHFs are similarly embedded in the consolidated appeal process. |
| II: Enhance the timeliness and reliability of the Financial Tracking System |
| Timely agency reporting to the FTS (at least monthly, or ad hoc whenever a new commitment is received). Agencies report allocations of unearmarked funds to CAP projects (in line with results of dialogue led by UNHCR re when to report unearmarked funds as firmly allocated). Encourage main NGOs to include their proposals in the CAPs or at least to report their requirements, so as to account for them in total humanitarian requirements. Also, to report their humanitarian contributions to FTS. Agencies and FTS to move towards more automated, real-time data transmission into FTS. Agencies can make data transmission to FTS easier by keeping their Appeal projects in line with projects as reflected in their internal financial systems, starting with CAP launch and continually updated throughout the year. Consolidate the processes of CERF reporting and CAP Mid-year reviews, to avoid repetition and ensure that CERF financial data is reflected in CAP documents/MYRs Develop and test an on-line project submission system for new CAPs in 2008 to improve the prioritization process, make it easier to update projects, and provide a searchable on-line project database | 1. Better humanitarian resourcing decisions through more complete and up-to-date info on funding to date 2. More visibility for unearmarked funds, leading to greater donor willingness to provide them. 3. More credible CAPs that reflect a greater part of humanitarian action and needs; more complete worldwide humanitarian funding data. 4. Better humanitarian resourcing decisions through more complete and up-to-date info on funding to date, achieved more labour- efficiently. 5. Better humanitarian resourcing decisions through more complete and up-to-date info on funding to date, achieved more labour- efficiently. 6. Better picture of the funding situation in a given country; less burdensome reporting. 7. Increased quality and improved prioritization of project proposals leading to more effective humanitarian action. | Agencies’ FTS focal points Agencies’ FTS focal points OCHA OCHA, Agencies’ FTS focal points IASC CAP SWG, Agencies’ FTS focal points IASC CAP SWG FTS, Agencies’ FTS focal points, Agencies’ field offices, IASC CAP SWG | year round year round Year round By 3rd quarter 2008 Year round Year round By end of 2nd quarter 2008 | Information is sent monthly more often than not; ad hoc reports of any new commitments would be better still. Information on agencies’ use of unearmarked funds is increasingly comprehensive. Information on receipt of unearmarked funds would be useful, to give full credit and visibility to flexible donors. Distinct improvement in NGO participation in CAPs: for example, in 2008 fully 40% of CAP and flash appeal projects are NGO projects. (See Humanitarian Appeal 2008 and 2009 documents for further detail and analysis.) Nearly all NGO projects that were reported as funded by MYR time were accounted towards their respective appeal. This objective was transmuted slightly into the development of the CAP Online Projects System, which will greatly change the CAP production and update process starting in late 2008. More progress needed on this: too often, the argument is still heard that agencies cannot report on funding per project because the delineation of projects in their own system differs from that which they expressed in the CAP. Still to be implemented. The online project database is functional for the CAP 2009 season. |
| III: Advocate support for the Agencies and NGOs participating in the CAP |
| Donors Organise January Programme Kick-Off, June Mid-Year Review, and November Launch events. Actively contribute to Montreux Donors’ Retreat agenda and meeting. Obtain two new donors to CAP. IASC Conduct field workshops for IASC Country Teams in countries that are producing a CAP or CHAP. Conduct training of trainers workshop for IASC members. Provide trainings and briefings to IASC member staff in headquarters. Inform other IASC-related humanitarian training programmes (e.g. UNDAF, EFCT, EWPM, etc.) Continued advocacy and policy improvement to increase NGOs participation in CAPs Related: Yearly update of CAP training tools to reflect new policy developments. | Three events with clear foci. Donors provide substantive feedback on CAP. Recommendations from the retreat disseminated to the field and used by IASC CTs in their discussions with donors. Two potential donors are identified and meetings held at the working level to discuss their potential role. All requests for CAP field workshops are met. At least 10 new CAP trainers trained and all are deployed at least once in 2008. Requests by IASC members for CAP briefings/training are met. CAP policies and guidelines are accurately reflected in IASC members’ humanitarian training programmes. 20 main NGOs in each country or region with a CAP participate actively in main parts of programme cycle. CAP Training tool-kit updated and disseminated to active CAP trainers. | SWG members SWG members OCHA OCHA OCHA and Agencies OCHA OCHA and Agencies SWG members IASC CAP SWG OCHA | Year-round February March Year-round Year-round, with focus on Aug-Sept April Year-round Year-round Year-round Jan-April | Done. (CAP SWG is considering whether to re-engineer CAP publicity events, to better influence public opinion during legislative budget deliberations.) Done Being implemented in October 2008, with a focus on new EU members. Done – 13 national workshops conducted in 2008. CAP ToT refresher done in July. 23 new persons trained. Five of them already deployed Done. Done – in particular, close follow-up of the development of OCHA’s HFCP. Done (though difficult to measure without detailed reports from clusters on participation) Partly done. |
| IV: Provide a structured forum for discussion, consensus-building, and realization of the above objectives through efficient management and committed participation in the SWG. |
| Meetings are held on a monthly basis, each with a focused agenda and clear outputs. Review which crises warrant a CAP for the following year and submit to IASC WG meeting in June. SWG membership base ensures that members have the relevant experience to advance the CAP as a strategic planning and programming tool. | Agendas are shared in advance with members and meeting notes are prepared within three working days. Follow up actions are monitored and followed-up. Recommendation to WG on which countries, or regions to have a CAP in 2008 IASC members appoint staff with the relevant programme, field or training experience to the SWG; IASC members attend meetings regularly, are prepared to discuss agenda items, and are actively involved in follow-up actions. | OCHA HC, SWG, WG SWG members | Year-round June Year-round | Done. Meeting rescheduling too frequent – linking with other entities could be improved. This year, the WG was not explicitly involved in selection of CAP countries for 2009. Done |