DRAFT ACTION POINTS

Global Cluster Appeal Workshop with Donors, Cluster Leads, IASC Partners

Geneva 12 December 2006

A Global Cluster Appeal Workshop took place with donors, cluster leads and IASC partners to decide on the format and content of the Report on the 2006 Cluster Appeal, to share lessons learned from the previous Appeal, and to agree on next steps for preparing the 2007 Appeal. The following outlines proposed action points from the workshop:

## Report on Implementation of Global Cluster Capacity Building, 2006

- Participants agreed on the proposed timeframe for preparing the report, which will be launched on 28 February (see annex with deadlines). Cluster leads should detail progress made against the indicators outlined in the Revised Global Appeal, which was issued 31 May. Global cluster leads should also report on results and outcomes at the field level as well as major efforts that are completed or underway to improve systems, procedures and the inclusion of partners. In addition, global cluster leads should highlight lessons from their first year of work, including lessons on funding modalities. The report should include details of funds received, spent, and carried-over and impact of late funding. Participants agreed to provide final comments on the template for the report by 14 December to HRSU <hrsu@un.org>. It was agreed that HRSU would facilitate a review of the draft report among a small group of donors to ensure the document meets requirements identified by donors at this workshop. While some agencies are required to make formal financial reports individually, all ten donors agreed that they will accept the report in lieu of agency-by-agency reporting. Agencies based in New York and Rome agreed to coordinate closely with their donor counterparts to re-confirm this point

2007 Global Cluster Appeal

- Participants agreed to extend the proposed deadline for launching the Cluster Appeal by two weeks. It will be launched 15 April (see annex with deadlines). The document should include a summary of Global Cluster work plans, based on rigorous gap analysis. The work plans should summarize the priority activities to be undertaken over one year, with clear targets and indicators to measure progress. The work plans should cover intra-cluster and cross-cluster issues as appropriate. The crosscutting issues network should provide advice on how best to support proposed crosscutting issues costs in the Appeal (e.g. gender). The template for providing inputs to the cluster appeal will be adjusted based on workshop discussion as well as input received to date and circulated by 15 December. Donors emphasized that there needs to be greater prioritization across clusters in the next Appeal and that there should be a balance across clusters in the amounts being requested. To address this, OCHA will make proposals for an inter-cluster review panel (including donor participation) to screen projects and minimize disparities across clusters. (This panel would essentially perform the role of an HC in a traditional country-level CAP.)

Funding

- Cluster Leads should ensure they are up-to-date in reporting to FTS on funds received towards the 2006 Appeal. Donors have agreed to no-cost extensions. Cluster leads agreed to have bilateral discussions on modalities related to the no-cost extensions with donors.  Donors requested that in 2007 OCHA continue to maintain and update the  ‘live’ table initiated in 2006 to track the spread of contributions. Participants requested that the ‘live’ table be modified to include the actual date of funds received from donors by cluster leads, and (where relevant) the date  these were distributed onwards to cluster members. Cluster Leads, supported by OCHA, are to take the lead in mobilizing and advocating for resources and should work to expand the donor base beyond the 10 donors who contributed to the 2006 Appeal. Donors, for their part, agreed on the need for even greater efforts to coordinate their contributions to the 2007 Appeal.  Donors emphasized that as of 2008, all cluster activities should be mainstreamed into core programming and that they would not support a third Global Cluster Appeal in 2008.

Partnerships

- Cluster leads are to proactively widen their partnership base among INGOs and southern NGOs, and seek their inclusion in work planning and the 2007 Appeal. It was emphasized by NGOs present that cluster leads need to ensure capacity constraints are taken into account with greater collaboration emphasized, less meetings and more substantive engagement. Some cluster leads reported that they have been able to ensure very active participation from NGOs in a number of ways: proactively visiting NGO headquarters to promote dialogue on the cluster approach, objectives and added value of participation; addressing capacity constraints through hosting trainings and events outside of Geneva, allowing for more national and regional partner participation; and providing direct funding support during an emergency to enhance local partners response. Cluster leads and donors agreed that good practices of partner engagement in 2006 should be reinforced in 2007 by all cluster leads.

Additional Clusters

- The discussion on inclusion of new clusters in the next Appeal was postponed, pending the outcome of the IASC Principals and receipt of formal proposals by sectors hoping to be included in the Appeal.

Funding Channels

- Donors emphasized that Cluster Leads, together with their partners, must highlight priorities within clusters to assist donors in directing their funding. Donors favored channeling funding through OCHA, and if not, through cluster leads rather than direct to cluster partners. They viewed managing and directing funds, in consultation with partners, as a key role of cluster leads. Some agencies have made progress in managing low-cost pooled cluster funding arrangements in 2006, while others expressed reservations about pooling funds. It was agreed that those clusters that are not using pooled funding channels should go back to their partners to explore pooled funding / ‘pass-through’ mechanisms for 2007. One of the causes for late receipt of funds in 2006 was lack of clarity on disbursement arrangements (cluster leads vs. direct funding to partners) and donors urged that this must be clearly articulated in 2007.  OCHA will work with cluster leads to clarify final agreed funding channels, aiming for consistency if possible, and will communicate outcomes to donors. Strengthened donor coordination on funding was welcomed with clusters leading the prioritization process.

OCHA/HRSU

14 Dec 2006

ANNEX I: AGREED DEADLINES

Report on Implementation of the Global Capacity Building, 2006

- Report covers period: 1 April 2006 to 31 March 2007

- Cut-off for financial reporting: 31 January 2007

Final Report template circulated						15 December

Cluster leads coordinate inputs from all cluster partners			December - January

Cluster leads provide consolidated narrative input 			15 January

OCHA circulates draft 							31 January

Cluster leads provide financial reporting input				31 January

Donor Group to review draft with OCHA as agreed at workshop		31 January

Full document ready for publication					15 February

Report launch								28 February

Cluster Appeal 2007

- Appeal covers period: 15 April 2007 – 15 April 2008

Final Appeal template circulated						15 December

Cluster leads coordinate inputs from all cluster partners			January – February

Cluster leads provide consolidated narrative input & project sheets	28 February

OCHA leads Project Review Panel to minimize inter-cluster disparities	Late Feb – early March

OCHA circulates draft for comment 					15 March

Full document ready for publication 					30 March

Cluster Appeal launch 							15 April

ANNEX II: PARTICIPANT LIST

| Name | Donor Country or Organization | Email | Telephone Number |
| --- | --- | --- | --- |
| Martin Gallagher | Ireland | martin.gallagher@dfa.ie | 022-919-19-57 |
| John Webster | United Kingdom | john.webster@fco.gov.uk | 022-918-23-38 |
| Victor Carvell | Canada | victor.carvell@international.gc.ca | 022 919 92 24 |
| Darcy DeMarsico | Canada | darcy_demarsico@acdi-cida-gc-ca | (+1) 819 994 38 72 |
| Catherine Godin | Canada | catherine.godin@international.ge.ca | (+1) 613 992 86 40 |
| Tanja Gren | Finland | tanja.gren@formin.fi | 022 919 42 49 |
| Christine Ghétin | France | christine.guetin@diplomatie.gouv.fr | 022 758 91 58 |
| Florence Duvieusart | Belgium | florence.duvieusart@diplobel.be | 022 733 57 55 |
| Asser Berling-Rasmussen | Denmark | assber@um.dk | 022 918 00 62 |
| Jette Michelsen | Denmark | jetmic@um.dk | 022 918 00 44 |
| Nancy Kyloh | USA | kylohnm@state.gov | 022 749 44 02 |
| Alesha Black | USA | blackaf@state.gov | 022 749 43 18 |
| André Mollard | European Commission | andre.mollard@ec.europa.eu | 022 918 22 17 |
| Kim Eling | European Commission | kim.eling@ec.europa.eu | 022 918 22 36 |
| Julia Stewart-David | European Commission | julia.stewart-david@ec.europa.eu | (+32) 2 29 86 594 |
| Walter Van Hattum | European Commission | walter.van-hattum@ec.europa.eu | (+32) 2 29 53 522 |
| Masako Sato | Japan | masako.sato-2@mofa.go.jp | 022 717 71 53 |
| Natalie Hicks | New Zealand | natalie.hicks@mfa.govt.nz | 022 929 03 65 |
| Alexander Ernert | Germany | alexander.ernert@diplo.de |  |
| Valeska Pfam | Germany | franke-valeska.pfam@diplo.de |  |
| Asbjorn Braanaas | Norway | Asbjorn.braanaas@mfa.no | 022 918 04 02 |
| Jakob Hallgren | Sweden | jakob.hallgren@foreign.minitry.se | 022 908 08 56 |
| Olivier Pauchard | Switzerland | olivier.pauchard@eda.admin.ch | 022 749 24 24 |
| Philippe Kaeser | Switzerland | philippe.kaeser@eda.admin.ch | 022 749 24 24 |
| Timothy Poletti | Australia | timothy.poletti@dfat.gov.au | 079 240 86 68 |
| Peter Medway | International Medical Corps | pmedway@imcworldwide.org.uk | (+) 44 78 55 77 11 30 |
| Jahal De Meritens | UNDP/BCPR | jahal.de.meritens@un.org | 022 917 87 04 |
| Esteban Leon | UN-HABITAT | leon.unhabitat@unog.ch | 022 917 87 57 |
| Lea Matheson | IOM | lmatheson@iom.int | 022 717 93 26 |
| Yoichiro Tsuchida | UNHCR | tsuchida@unhcr.org | 022 739 83 41 |
| Shoko Shimozawa | UNHCR | shimozaw@unhcr.org | 022 739 87 30 |
| Manoucher Lolachi | UNHCR | lolachi@unhcr.org | 022 378 87 27 |
| Liziana Clerico | UNHCR | clerico@unhcr.org | 022 739 83 72 |
| David Jensen | UNEP | david.jensen@unep.ch | 022 917 81 67 |
| Paul Hulshoff | UNICEF | phulshoff@unicef.org | (+)212 326 71 82 |
| Jean McCluskey | Wash Cluster, UNICEF | jmccluskey@unicef.org | (+) 41 22 909 56 16 |
| Paul Sherlock | Wash Cluster, UNICEF | psherlock@unicef.org | (+) 212 326 75 56 |
| Marina Komarecki | UNICEF | mkomarecki@unicef.org | (+) 212 326 77 83 |
| Luc Chauvin | UNICEF EMUPS Inter-Agency | lchauvin@unicef.org | 022 909 56 63 |
| Erin Kenney | WHO | kenneye@who.int | 022 791 24 48 |
| Samir Ben Yahmed | WHO | benyahmeds@who.int | 022 791 29 23 |
| Cintia Diaz-Herrera | WHO | diazherrera@who.int |  |
| Sarah Padre | Lutheran World Federation | spa@lutheranworld.org | 022 791 6441 |
| Kabi Bernander | UNHCR | bernande@unhcr.org | 022 739 84 10 |
| Flora Sibanda-Mulder | Nutrition Cluster, UNICEF | fsibandamulder@unicef.org | (+) 212 326 75 62 |
| Hanah Entwisle | UNHCR | entwisle@unhcr.org | 022 739 87 12 |
| Jane Janz | UNHCR | janzj@unhcr.org | 022 739 32 41 |
| Clarissa Azkoul | IOM | cazkoul@iom.int | 022 717 95 01 |
| Pär Liljert | IOM | pliljert@iom.int | 022 717 92 32 |
| Amy Christofferson | ICRC | achristofferson@icrc.org | 022 730 28 46 |
| Chen Reis | WHO | reisc@who.int | 022 791 46 96 |
| Nina Sreenivasan | UNFPA | sreenivasan@unfpa.org | 022 917 84 40 |
| Paul Paredes | FAO | pparedes-pontella@unog.ch | 022 917 36 81 |
| Matthew Hollingworth | WFP/Logs Cluster | matthew.hollingworth@wfp.org | (+) 39 347 05 41 511 |
| Giammichele Denao | WFP External Relations | giammichele.denao@wfp.org | (+) 39 06 65 13 35 33 |
| Karine Hoyer | UNMAS | hoyer@un.org | (+1) 917 367 58 22 |
| Katy Webley | Save the children | k.webley@savethechildren.org.uk | (+44) 207 012 67 87 |
| Roberta Cecchetti | Save the children | roberta@savethechildren.ch | 022 919 20 00 |
| Elisabeth Rasmussen | Internal Displacement Monitoring Centre | elisabeth.rasmussen@nrc.ch | 022 799 07 04 |