Workplan for Development of a Cluster Toolkit

## Background

In light of the Real-time Evaluation of the Cluster Approach in Pakistan, the Nutrition Cluster has adopted Key Action 3:

“The Global Cluster Leads to develop Cluster Toolkits for policy guidance, common planning and assessment formats, minimum standards and benchmarks, and other relevant documentation.  Ensure training is provided within Cluster Lead Agencies, as well as stakeholders including NGOs and IOs.”

The Cluster agreed a toolkit was necessary to equip the country cluster lead/facilitator with key tools and guidance on strengthening the cluster approach, but which would also aim to improve assessment, monitoring and response as a whole.

Components of the Cluster Toolkit

  - Principles of the cluster approach (what is it and how is it different from the sector approach)

  - Guidance on linkages/accountabilities between country and global clusters

  - TORs for cluster lead agency/facilitator at country level

  - TORs for cluster coordinator at country level

  - Minimum interventions/scope of cluster accountabilities (these should also feed into country CAP activities)

  - Response triggers for identified interventions

  - Performance benchmarks for the cluster

  - Key technical policies/standards/references

  - Common assessment/survey tools

  - Training package at country level for technical participants (to be implemented as part of preparedness in slow onset/disaster prone countries)

  - Training package for Nutrition coordination

  - Stakeholders mapping at national and global level

Format

- Format of the toolkit was discussed as potentially a hard copy handbook with key references on CD (IASC handbook for HIV/AIDS a good reference)

- Technical guidance should be distinguished from generic guidance applicable to all cluster coordinators (coordination with OCHA on consistency to other toolkits must also take place).

Timeline

- Cluster toolkit should be finalized latest by end 2006 (with updates on a rolling basis)

Workplan

| Chapter | Action Point | Agency (ies) Responsible | Primary Focal Point | Timeline | Status |
| --- | --- | --- | --- | --- | --- |
| Principles of the Cluster Approach (to include linkages/accountabilities between country and global clusters) | Draft chapter to be shared with cluster | UNICEF | Rainer Gross/Sherine Guirguis | June 1, 2006 |  |
| TORs for cluster lead agency/facilitator at country level | Finalize existing draft TORs | UNICEF | Rainer Gross/Sherine Guirguis | April 25, 2006 |  |
| TORs for cluster coordinator at country level | Finalize existing draft TORs | UNICEF | Rainer Gross/Sherine Guirguis | April 25, 2006 |  |
| Minimum Interventions/scope of cluster accountabilities | Agree upon list of minimum interventions | All | All | April 20, 2006 | Done |
|  | Develop/identify response triggers which inform when an intervention should be put in place | Agencies identified in table below | Primary focal points identified in table below | June 1, 2006 |  |
|  | Minimum standards and performance benchmarks for monitoring performance of the intervention | Agencies identified in table below | Primary focal points identified in table below | June 1, 2006 |  |
|  | Key guidelines (which reflect best practices) for each intervention | Agencies identified in table below | Primary focal points identified in table below | June 1, 2006 |  |
| Common assessment/survey tools | Map existing early assessment tools | WFP/IFRC/USAID | Martin Bloem | May 10 | In process with assistance from USAID consultant |
|  | Map existing survey tools | WFP/IFRC/CDC | Mija Ververs | ? |  |
|  | Analysis complete for discussion on recommended assessment tool | WFP/IFRC/CDC | Martin Bloem | June 1, 2006 |  |
|  | Analysis complete for discussion on recommended survey tool | WFP/IFRC/CDC | Mija Ververs | ? |  |
| Technical training package for country level for UN/NGO programme managers | Develop TOR, objectives and outline of training package | UNICEF, FAO, WFP, UNHCR, WHO | Flora Sibanda-Mulder | May 1, 2006 |  |
|  | Draft training materials developed | UNICEF, FAO, WFP, UNHCR, WHO | Flora Sibanda-Mulder | October 1, 2006 |  |
| Stakeholders mapping at national and global level | Draft Capacity mapping at global & national level | ACF | Caroline Tanner | June 1, 2006 |  |

Detailed Workplan for Development of Response Triggers, Standards/Performance Benchmarks, and Key Guidelines

| INTERVENTIONS | AGENCIES RESPONSIBLE FOR DEVELOPING GUIDANCE | Primary Focal Point for Response Triggers | Primary Focal Point for Standards/Performance Benchmarks | Primary Focal Point for Key Guidelines |
| --- | --- | --- | --- | --- |
| Cross-Cutting |  |  |  |  |
| Assessment, Monitoring & Surveillance (also covered in point 5 above) | WFP/IFRC | - | - | - |
| Communication/Advocacy | SCN (Caroline Wilkinson?) | - | - | - |
| Capacity Development (also covered in point 6 above) | UNICEF | - | - | - |
| Treatment of Undernutrition |  |  |  |  |
| SFPs | WFP | Anne Callanan | Anne Callanan | Anne Callanan |
| Facility and non-facility-based therapeutic feeding programmes (treatment of severe malnutrition) | WHO/UNICEF | Zita Weise Prinzo | Flora Sibanda-Mulder | Flora Sibanda-Mulder |
| Treatment of micronutrient deficiencies | WHO/UNICEF/WFP (CDC&GAIN interested to participate in working group) | Zita Weise Prinzo | Flora Sibanda-Mulder | Martin Bloem |
| Prevention of Undernutrition |  |  |  |  |
| Household Food Security ** General food security Primary production Income and employment Access to markets | FAO | Brian Thompson | Brian Thompson | Brian Thompson |
| Food Aid** Food aid planning Ration planning Appropriateness and acceptability Food quality and safety Food aid handling Food handling Supply chain management Distribution | WFP | Anne Callanan | Anne Callanan | Anne Callanan |
| Social Care |  |  |  |  |
| Protecting & promoting infant and young child feeding | ENN/ IFE (Core Group on Infant Feeding in Emergencies) and SCN Working Group on Nutrition in Emergencies (guidance already completed) | Caroline Wilkinson | Fathia Abdallah | Fathia Abdallah |
| Community based child care systems (including for unaccompanied children and other vulnerable groups) | ACF | Caroline Wilkinson | Chris Leather | Chris Leather |
| Psycho-social components | ACF | Caroline Wilkinson | Mija Ververs | Mija Ververs |
| Food preparation (knowledge, beliefs, practices, resources, tools, NFIs, etc.) | WFP | Anne Callanan | Chris Leather | Chris Leather |
| Health & WES |  |  |  |  |
| Vitamin A supplementation (reduction of morbidity and mortality) | UNICEF/WHO | Zita Weise Prinzo | Zita Weise Prinzo | Zita Weise Prinzo |
| Multimicronutrient supplementation (prevention of micronutrient deficiencies) | UNICEF/WHO | Flora Sibanda-Mulder | Flora Sibanda-Mulder | Flora Sibanda-Mulder |
| ORT/Zinc (management of diarrheoa) | WHO | Zita Weise Prinzo | Zita Weise Prinzo | Zita Weise Prinzo |