Inter-Agency Standing Committee

IASC Subsidiary bodies

IASC Task Force on Information Management 
Work Plan for 2011

# Narrative Summary

Introduction

To address deficiencies in managing information in emergencies that were identified by humanitarian partners in early 2006,   OCHA and the IASC membership were requested by the IASC Working Group (WG) at its 65th meeting to implement ten recommendations to address the identified weaknesses.  By December 2007, all ten recommendations were substantively implemented by the members of the IASC through the Inter-Agency Information Management Work Group (IA IM WG).  One of the most important outputs of the IA IM WG was the development of an inter-agency agreement on the responsibilities of cluster/sector leads and OCHA in managing information emergencies: the Operational Guidance on Responsibilities of Cluster/Sector Leads & OCHA in Information Management (hereafter referred to as Operational Guidance on IM). This Operational Guidance was endorsed by the IASC Task Team on the Cluster Approach in 2007 and by the IASC Working Group in 2008.

At the 71st IASC WG meeting in June 2008, OCHA provided an overview of progress made in 2006-2008 by the IA IM WG, presented the Operational Guidance on IM, and recommended that an IASC Task Force on Information Management (IASC TF on IM) be established to strengthen inter-agency information exchange before and during emergencies.  After clarifying the main focus of the group through a concept note, the IASC WG endorsed the establishment of the IASC TF on IM as of 1 January 2009 for an 18 month period.  Throughout 2009, progress against the overall objectives has been made and the Task Force is likely to achieve its main activities as outlined below.

At the 77th IASC WG meeting in July 2010, the IASC TF on IM provided a presentation on IM preparedness, including the Common Operational Datasets, and a general status report outlining substantive progress in delivering the outputs assigned by the IASC WG.  In order to complete the remaining activities supporting each output, as well as addressing the substantive recommendations and sub-recommendations on information management within the cluster approach stemming from the Final Synthesis Report of Cluster Approach Evaluation Phase 2, the IASC TF on IM requested a 12 month extension of its mandate, which was endorsed in November 2010.

Objectives

The overall objective of the Task Force is to strengthen the management of information in humanitarian emergencies by building on and improving existing inter-agency processes and tools for the collection, processing, analysis and dissemination of information to support improved decision making in emergencies.

In order to provide the members of the IASC, including global and field cluster/sector leads, with improved information management guidance and tools, the primary objectives of the IASC TF on IM are:

# Needs assessments efforts are supported from an IM perspective;

# Enhance the effectiveness of information management within the cluster approach;

# Produce agreed guidance and tools to implement the revised Operational Guidance on IM; and

# Develop a framework for monitoring the effectiveness of IM in humanitarian emergencies.

II  	Key Expected Outcomes 2011

The IASC TF on IM will have the following expected outcomes in 2011:

- Address the recommendations of the Review of the Operational Guidance on Responsibilities of Cluster/Sector Leads & OCHA in Information Management as well as the recommendations on information management within the cluster approach stemming from the Final Synthesis Report of Cluster Approach Evaluation Phase 2.

- Review of the humanitarianresponse web platform and implement the recommendations stemming from the report.

- Pilot a Cluster/Sector IM distance learning course for personnel involved in strategic, operational, technical, or managerial side of collecting, analyzing and using data.  This will allow for a common standard, understanding and expertise of how IM supports humanitarian response.

- Collaborate with the IASC Needs Assessment Task Force (NATF) to ensure harmonization among Common Operational Datasets, humanitarian dashboard and needs assessment indicators.

- Establish a framework for monitoring effectiveness of IM in humanitarian emergencies.

| Objectives | Activities | Focal point(s) | Timeframe |
| --- | --- | --- | --- |
| Needs assessments efforts are supported from an IM perspective | Provide IM guidance, recommendations and technical support to the IASC Task Force on Needs Assessments (NATF) Ensure harmonization among common operational datasets (COD), humanitarian dashboard and needs assessment indicators Provide support to the NATF in terms of IM human resources related to assessments | OCHA, UNICEF and WHO with the support of the entire Task Force | In line with NATF work plan for 2011 |
| Enhance the effectiveness of IM within the cluster approach. | Review and address the recommendations of the Cluster Approach Evaluation Phase 2 Review and address the recommendations of the Review of the Operational Guidance Note to reflect best practices Produce a report on implementation of the recommendations | Entire Task Force | By 3rd quarter 2011 By 2nd quarter 2011 By 3rd quarter 2011 |
| Produce agreed guidance and tools to implement the revised Operational Guidance on IM | Develop online “resource kit” for field practitioners on implementation of the Operational Guidance Note on IM Review of the humanitarianresponse web platform and implement the recommendations stemming from the report. Pilot the Cluster/Sector IM distance learning course, evaluate feedback from pilot and make appropriate changes to the course. Update or create new information management solutions to meet unforeseen gaps arising from the review Systematise the COD that will be consistently shared between Cluster/Sectors and OCHA in emergencies and further develop the fundamental operational datasets (FOD) and related governance | To be determined Sub-group on governance Sub-group on training As appropriate Sub-group on datasets | By 3rd quarter 2011 Review conducted before end 1st quarter 2011 Pilot by end 1st quarter 2011 By 3rd quarter 2011 COD by 1st quarter 2011 and FOD by 3rd quarter 2011 |
| Framework developed for monitoring effectiveness of the Operational Guidance Note on IM | a) Taking into account standard indicators and tools, develop a framework to monitor the effectiveness of IM in humanitarian emergencies | Entire Task Force | By 3rd quarter 2011 |

III	Work Plan for 2011

# Footnotes

In June 2006, at the request of the IASC-WG, OCHA hosted an Information Management Workshop in Geneva where 29 representatives from the IASC participated (FAO, ICVA, IFRC, IOM, OCHA, UNDP, UNFPA, UNHCR, UNICEF, UNJLC, WFP, WHO, VVAF,  and World Vision International) and came to this agreement on the role of humanitarian information management

See Background Note, Implementation of Inter-Agency Framework for Information Management in Emergencies, presented at the 71st meeting of the IASC-WG.