Case Study Findings –Nairobi, Eldoret, Manila

Draft Synthesis Paper

Introduction

- Background and purpose of the case studies

Over many decades humanitarian policymakers and practitioners have focused primarily on rural emergencies and disasters. However, with the recognition that urban areas already are and increasingly will be where humanitarian needs are to be met, humanitarian actors and agencies are increasingly directing their attention to cities and towns in the developing world. During the last few years, two trends have emerged, demanding rethinking of modalities and approaches to urban based humanitarian response. Firstly, e conflict and disasters often drive large-scale sudden displacements of rural populations to cities and towns. This trend has increased considerably in recent years; more and more refugees and internally displaced people migrate to cities and towns during and after conflict, seeking protection or to reduce their visibility. Discussions on assistance methods to population displaced in urban areas have started including thinking of modalities of assistance for population outside camps in urban areas. Secondly, more and more natural disasters such as earthquakes, typhoons, storms etc are occurring in cities, highly vulnerable to the impact of natural disasters. The recent disasters in Haiti, the Phillipines, and Indonesia etc have placed significant pressures on humanitarian organizations in relief, recovery and reconstruction in urban areas. Operations in urban contexts can not be viewed in the same way as operations in rural contexts. They take place on a completely different scale and are multidimensional, raising issues of a financial, spatial, societal, economic, political and administrative nature. Urban areas are densely populated with majority of informal settlements and in high risk zones.

II.                       Framework

To enhance IASC understanding of effectiveness of current methods, practices and capacity in responding to humanitarian crises in urban areas, the IASC Task Force on Meeting Humanitarian Challenges in Urban Areas (MHCUA) recommended a Nairobi, Eldoret, Manila as case studies, including a review of the urban challenges recently experienced by the IASC in Haiti.  The urban areas studied represent cities that have experienced recent emergencies impacting densely populated urban areas.

The Nairobi case study included a field visits to Eldoret, a smaller city that suffered post-election violence in 2008 and where humanitarian activity intensified for the duration of the crisis. The purpose of including Eldoret in the study was to draw out the different nature of challenges and responses experienced in a smaller urban area in comparison with Nairobi. The purpose of the case studies is to facilitate a closer understanding of the tools and approaches used by stakeholders in humanitarian action in responding to disasters, whether sudden or slow onset, with the wider aim of formulating a Comprehensive Strategic Framework for Meeting Humanitarian Challenges in Urban Areas. The case studies aimed to provide a ground-level view of plans, activities, methodologies, tools and approaches that were employed in both city contexts and are different to, or adapted from, those used in rural areas. Their purpose is to feed into the wider Strategy formulation for meeting humanitarian challenges in urban areas, designed to provide the IASC TF on MHCUA with sufficient information to make clear recommendations and priorities for what the Strategy should include.

III. Objective and Scope

The overall objective of the case studies was to understand the urban challenges – as distinct from rural ones - encountered by humanitarian actors in the cities of Nairobi, Eldoret and Manila, to study at first hand the tools and methodologies employed by IASC member agencies and to learn from their experiences in delivering humanitarian assistance in these two specific urban areas. The scope of the studies included the different kinds of disaster contexts in both cities and all disaster phases, with a view to understand what humanitarian activities and programmes were successful, why others may not have been so, what made the challenges of operating in an urban area different to rural areas, what stakeholders consider could be done better in future and what the constraints (gaps) exist to achieving this.  The studies provide recommendations, based on best practices and gaps identified to date, on how humanitarian assistance delivery could be improved in urban areas, in tandem with development actors, to have a greater impact.

IV. Timeframe and Methodology

The case studies were conducted between 18 and 28 May 2010 (Nairobi) and 2 and 11 June 2010 (Manila). Preparation for the studies, desk review, field visits and drafting of the present synthesis report took place between the beginning of May and the end of June 2010.  A review of existing reports including evaluations, lessons learnt, and related documentation was conducted for each case study which contributed to the framework. Interviews and meetings during the field phase were semi-structured around a question-set pre-agreed by the TF, with individuals in national and local government departments including disaster coordination councils, emergency response focal points in local government units, IASC organizations, non IASC partners includes the NGOs, private sector actors and focus group discussions with affected communities.

The visits were facilitated by OCHA in Nairobi and UN-HABITAT in Manila as focal points and a national consultant was contracted in each city to provide assistance in background information and in logistical support.

V. The Crisis Context

Nairobi

The proliferation and expansion of informal settlements in Nairobi reflect ongoing economic migration to cities as well as population growth. Sixty per cent of Nairobi’s residents live in slums with no or limited access to even the most basic services.  The country’s reduced food production due to prolonged drought and political violence has resulted in higher food prices, negatively affecting the urban poor and increasing food insecurity in city slums.  Moreover, the percentage of the urban population in the poorest categories of all is on the increase, and the gap between rich and poor is rapidly widening. While some urban dwellers have seen their position improve due to impressive levels of economic growth in recent years, poverty has been deepening for the majority of the urban poor who have become trapped in downward spirals of deprivation and vulnerability: unable to find work, or finding only menial work that pays very low wages, of being forced to live in low-income areas (categorized variously as slums or informal settlements), of living in over-crowded, unsanitary situations where hazards such as periodic fire, flooding and violence produce multiple shocks from which people are increasingly hard-pressed to recover.  Town and city infrastructure is not keeping pace with the number of arrivals resulting in a proliferation of slums and informal settlements.

Humanitarian emergencies in these settings are twofold:

- Chronic emergencies.  These have emerged because the slums in Kenyan cities have become increasingly disaster-prone due to structural processes creating rapid urbanization, population movements and high population densities.  Migrants to the city have settled in areas that may not be unsafe per se, but where the high concentration of people creates the potential for man-made disasters such as environmental degradation, periodic fire outbreaks and health hazards.  People have become increasingly vulnerable by living in an over-crowded and unsanitary environment which creates the conditions for a proliferation of crime and SGBV-related insecurity and exposure to epidemics.  An estimated 46,000 refugees live in Nairobi in the anonymity of local communities, over 6,000 of them arriving within the space of a few days in June 2010.

Humanitarian practitioners working in slum areas believe that humanitarian indicators such as global acute malnutrition (GAM), under-5 mortality and overall mortality rates are as high in these areas as they are in some rural areas.  Without adequate supply of potable water, the MDGs on child mortality, maternal health, and combating HIV/AIDS, malaria and other diseases, could be under threat. A recent study by OXFAM states that urban poverty is set to be Kenya’s defining crisis over the next decade if it is not urgently addressed.

- Sudden-onset emergencies.  In the Kenya context these include fire outbreaks, flooding and episodes of widespread violence of the kind experienced after the 2007 elections resulting in loss of life, property and a general breakdown of law and order. People who have lost their homes in these events become displaced and have to find alternative shelter – often with friends or family members in similar circumstances, whose own precarious conditions become further stressed.

Eldoret

Whereas Nairobi is a city of over 3 million inhabitants, Eldoret has just over 700,000. It is surrounded by a rich agricultural area and is home to many farmers and farm-related industries. Post-election violence (PEV) affected Eldoret in both urban and rural areas, many of whom fled the latter for Eldoret in search of safety. UNHCR indicates that there remains a lack of clarity on actual numbers of PEV-related IDPs.  The Government of Kenya (GoK) conducted a nation-wide IDP profiling exercise covering PEV-related IDPs only (ie. not the pre-existing IDP caseload) and estimated the number at 663,921. As at May 2010 the number of IDPs stood at some 18,570 displaced in 25 transit sites in the Rift Valley (Eldoret area) and 34,000 in self-help groups.  Some of the IDPs in Eldoret have returned to their areas of origin and/or ancestral home areas or are in the process of doing so. Others have not done due to their fear being in the minority, and thus remain in transit or self-help sites near the town for reasons of greater security.  An undetermined number have left these sites to move into urban areas – Eldoret, Nakuru and Nairobi where they have placed further pressures of space and competition for resources on the urban poor. The IDP caseload remains in a state of flux and will not be resolved until the Government signs into law a draft National IDP Policy which aims to provide greater protection to IDPs, prevent future displacement and fulfil the country’s obligations under international law. The Proposed Constitution of Kenya also recognises lawfully held land by individuals or communities. Many Kenyans believe that this will address historical land issues which were the underlying problem of displacement during the elections.

The crux of the differences between Nairobi and Eldoret is that IDPs and the urban poor in Eldoret can rely on a modicum of food security through their proximity and linkages to nearby farms, whereas in Nairobi, all needs must be satisfied by paying cash and there is no ‘rural’ safety-net. The IDPs and the urban poor in Eldoret have a strong social network of sharing and borrowing for survival but those in Nairobi have to struggle individually in a society with little social capital and a cash-based economy.

Manila

Asia and the Pacific is highly vulnerable the disasters, and the IASC organizations have been engaged in humanitarian response and recovery in several countries. Being a fastest urbanizing region, and with recent disasters taking place in urban areas, the Phillipines is one country considered most disaster-prone in the world. Its location makes it vulnerable to a variety of natural disasters. Lying on the western rim of the pacific and along the circum-pacific seismic belt, it is subject to storms, typhoons, earthquakes, floods, volcanic eruptions, droughts and faces other natural hazards. Disasters are a serious threat to people and economic assets, particularly in densely populated urban areas. At least 60 percent of the total land area of the country is exposed to multiple hazards, and as a result 74 percent of its population is vulnerable. In urban areas, those living in calamity-prone areas such as riverbanks and estuaries are highly vulnerable to natural and man-made disasters. Those in flood-prone areas, along the coast and on steep slopes in upland areas are also at risk.

Metro Manila is the most populous metropolitan areas in the Philippines. It consists of 16 cities and one municipality, and is considered a unique example of the mega-city in the Asia-Pacific region, with high hazard, high vulnerability and considerably high earthquake risk. The proximity to the active fault region, rapid urbanization and population expansion makes it a disaster hotspot. Natural disasters in these areas as witnessed in the 2009 Tropical Storms of Ketsana, Pepeng and Mirinae placed pressures on humanitarian responses in urban areas of Metro Manila.

The urban conditions in Manila’s are similar to those in Nairobi’s slums, characterized by over-crowded, unsanitary situations with multiple hazard risks.  Manila slum residents, as Nairobi’s, form a dynamic part of the workforce but city infrastructure has not kept pace with their numbers. The majority work in the informal sector and claim to earn a better living than they could in rural areas, or in the outskirts of the city where city government officials plan to move them. The tropical storms of 2009 affected the urban poor disproportionately given their propensity to live in hazardous areas prone to flooding.  Some have accepted relocation plans from the government and are being assisted to move there, but it is a slow process requiring attention to livelihoods. Others melted back into slum areas and resist relocation, afraid to lose their livelihoods.

VI. Humanitarian Challenges in Urban Areas

    - Operational opportunities and challenges encountered by IASC agencies and organizations in urban areas

The humanitarian community faced particular challenges in managing the humanitarian response in the three case study cities. The following issues were identified as critical areas for redress, in all phases of a disaster and in different disaster contexts and clearly state the need for prioritizing improvements.

    - The recent growth pattern in both Manila and Nairobi shows that the cities have been expanding in unsustainable ways for many years: in Manila, in the direction of the known tectonic fault lines and in Nairobi, by simple haphazard organic expansion absent of coherent planning. This has impacted the humanitarians significantly, in terms of navigation in urban areas and logistics of delivery of humanitarian assistance during the immediate emergency phase, as most urban areas were blocked due to massive blockage by debris, or infrastructure damage or facing violence.

    - Labour and cash for work have proven to be important tools for clearing urban areas and assisting the affected populations.

    - Clusters during urban disasters need to have the right interlocutors and a strategy to work in urban areas with urban administrations and national governments. The capacity of government departments (especially DSWD in Manila) is very weak at the municipal level during relief phase. There is a lack of capacity at local government level with which humanitarian agencies can forge coherent coordination mechanisms. The coordination cluster strategy for urban areas needs to be developed, as in the Philippines it involves several layers of coordination, addressing the often weak capacities at local levels. The previous model of rural setting response for clusters is not relevant when the agents of first response, ie. national government departments, are themselves unable to respond or play a lead coordination role.

    - The role of private sector in emergency relief and scaling up the response needs to be leveraged. Organizations such as BDO in Manila, with numerous branches all over the city, can mobilize funds for recovery; explore land availability options for emergency and early recovery.

    - Humanitarian organizations must have a clear strategy for how to manage shelter response on scarce urban land. Experience from the typhoons in Manila and the violence in Nairobi and emerging issues in Haiti reconstruction shows that the shelter response continues to be a key challenge due to a) need for enforcement of shelter/housing standards and enhancing governments’ technical expertise for urban shelter; b) lack of available land, especially land suitable and acceptable to residents for temporary and long term resettlements/ relocation.

    - Planning for scenarios where urban partners and the Government are themselves impacted by disasters are important for contingency planning exercises. It would be important for HCTs (the KHPT in Nairobi) to identify new or alternative capacities to mobilize in such situations.  Identification of evacuation centres not affected by flooding was a major challenge for some organizations in Manila. Identification of any form of temporary safe haven shelter for fleeing residents is a challenge in Nairobi.

    - Contingency plans need to include scenarios for quick recovery of emergency infrastructure (debris clearance, road recovery, communications, transport, water systems etc.) that would be damaged in a high intensity earthquake or flooding/typhoons, or destructive urban violence.

9. Lack or inadequacy of existing Standard Operating Procedures (SOPs) for urban settings was cited as one major problem by most, as the procedures are different than rural settings. The SOPs were not elaborative, and did not seem to work. In Nairobi, the government needs to find alternative civilian ways to mitigate the risk of violence, and to address it when it occurs, without recourse to military means.

10. Capacities of the local government departments are very limited in general, apart from some resource-rich municipalities in Manila. Crucial issues and gaps cited included: what capabilities each actor brings to the table during the emergencies, where to stockpile for future emergencies in high density cities, how to reach out to urban areas blocked due to flooding and/or debris and insecurity, and how to mobilize capacities when the first responders, i.e. the municipalities and other actors are themselves affected, identifying the vulnerable affected population vs the urban poor in urban settings, and defining procedures for how to identify the urban vulnerable.

11. The LGUs in Manila over emphasized their Search and Rescue (SAR) capacities as their disaster response in urban areas and discussed resource needs for SAR at length, however an appreciation of SOPs and preparedness has to move beyond SAR. Contingency plans in CTs should include SOPs for activating partners, standby contracts, staff deployments, etc. UN agencies, NGOs and Government Counterparts highlighted the following gaps in SOPs for complex and dense urban settings such as Nairobi and Manila: Capacities of the local government departments are very limited in general, apart from some resource-rich municipalities in Manila. Crucial issues and gaps cited included: what capabilities each actor brings to the table during the emergencies, where to stockpile for future emergencies in high density cities, how to reach out to urban areas blocked due to flooding and/or debris and insecurity, and how to mobilize capacities when the first responders, i.e. the municipalities and other actors are themselves affected, identifying the vulnerable affected population vs the urban poor in urban settings, and defining procedures for how to identify the urban vulnerable.

The municipalities interviewed in Manila seem to focus on conventional preparedness measures of emergency drills, setting up operations rooms and stocking equipment (only in some cases, others don’t want to invest for future calamities). In Eldoret, local officials depend entirely on the central government for resources (unlike the municipalities in Manila, which raise their own funds) and admitted their under-capacitation for responding to disasters. They rely to a much greater extent than their Manila counterparts on the rapid support of the international humanitarian community.

12. Where to shelter the population in emergencies in cramped urban settings with little or weak infrastructure such as schools, public buildings etc. Evacuation centres for high-density cities such as Manila need to be planned by the Government, with humanitarian organizations playing a supporting role, as part of preparedness.

  - Vulnerability, Targetting, Partnerships and Coordination Challenges in Urban Settings

These were analysed in the case studies according to a condensed form of the challenges identified in 2009 as part of the IASC’s initial strategy and identified from the document review of key studies and evaluations, to capture key points, namely: vulnerability and targeting, coordination, partnerships, capacities, sector specific challenges (the key problematic sectors being Shelter, combined with Housing, Land and Property (HLP), WASH and Protection from Violence), and preparedness.

- Vulnerability and Targeting

Identifying the challenges

People affected by emergencies, whether slow or sudden onset, face similar immediate vulnerabilities in urban areas. These may be compounded, as in the case of Nairobi, by the chronic poverty of people living in slum areas where additional shocks to already fragile survival strategies mean a depletion of family assets and an increase in vulnerability. The key challenge is food security. People affected by rural emergencies are closer to food producing areas and can usually obtain access to some form of food supply, whereas people in urban areas cannot avail themselves of this possibility. Additional vulnerability and targeting challenges were highlighted by the case studies:

- During a sudden onset disaster and in the immediate post-crisis phase, vulnerability is widely considered to be geographical in nature, that is, all those in the affected areas are considered vulnerable (communities most affected by violence in Nairobi and Eldoret and by the flooding in Manila). Targeting in this phase is mostly blanket assistance (food, domestic and hygiene items) to all those falling within the most affected geographical areas. Governments, humanitarian agencies and communities involved in distributing assistance faced two main challenges: (1) Access: flooded streets, un-navigatable by traditional trucks, or streets blocked by violence and debris inhibited a rapid and effective delivery of humanitarian assistance. Access problems were significant in all three city case study contexts. (2) Lack of data: inadequate, outdated or simply no baseline data on the numbers and characteristics of people living in slum areas, compounded by a highly mobile population: people fleeing the violence or flooding in search of temporary safe haven inhibited effective planning for the numbers of people affected and at risk. The governments and humanitarian organizations had little idea of how many people required assistance. In some parts of Nairobi the number of residents decreased dramatically and in others, they were higher. Despite the intention to provide blanket assistance to those in need, planning figures could only be rough estimates.

- In the chronic emergency context of the Nairobi informal settlements /slum areas, as well as in the post-crisis phase of Manila, identifying specific vulnerable groups or individuals is problematic given their dispersal in urban communities.  IDPs, children (especially street children), pregnant and lactating women, the elderly, the chronically sick and the disabled were the groups most often targeted as being especially vulnerable. In Nairobi refugees are an additional vulnerable group, particularly challenging to identify by virtue of their need to remain ‘invisible’ to avoid deportation. In Nairobi also, prolonged and severe chronic vulnerability requires careful targeting of humanitarian assistance to the totally destitute – requiring also carefully-designed criteria to distinguish the most in need from overall chronically poor population groups.

- A key challenge identified by humanitarian actors in Nairobi is that of determining emergency thresholds, that is, the ‘tipping point’ at which a generalized situation of chronic deprivation becomes an emergency.  This is largely due to the way statistics are collected.  Health and other statistics are collected at District level, but this is too big and diverse a level of analysis by which to capture the very different situations between the better-off, middle class areas and the slum areas that share the same district. Thus the statistics, averaged out between these different areas, do not give an accurate picture of the worsening humanitarian emergency in the slums.

      - Tools and Approaches

The different approaches employed to identify the location and numbers of the most vulnerable and to deliver assistance depended largely on the phase of the crisis and who was doing the targeting. Different actors used different approaches according to their resources and networks. Thus, in the immediate aftermath of the tropical storms in Manila, the government-led approach was to get a general overview of geographical areas most affected in order to have an idea of the numbers of people in need of assistance, while at community level, the approach taken was more geared towards using existing networks as sources of information to identify those needing immediate assistance. Both approaches were useful in the particular context but the separate initiatives produced a ‘silo’ effect of unshared knowledge and uncoordinated response, resulting in some people receiving multiple assistance packages while others went unserved.

- A joint UNHABITAT /OCHA-led process was initiated in Kenya in 2009 to strengthen coordination of humanitarian response in urban areas produced.  Building on this process, the GoK and the Kenya Humanitarian Partnership Forum (KHPT) created an ‘Assessment and Monitoring Working Group on Kenya Urban Vulnerability’ that will, in the next few months, draw up vulnerability indicators and measurements to identify the drivers of vulnerability in Kenya’s cities.  The Task Force will design a ‘basket of indicators’ to mark the point at which these vulnerabilities can be classified as an emergency.  This exercise has great relevance to the MHCUA initiative: it has the potential of providing a common benchmark, or set of benchmarks, that can be replicated in other urban areas confronting similar challenges.  The work of the TF should be sufficiently advanced to provide useful material to the overall MHCUA strategy.

- Meanwhile, in Nairobi, a bottom-up approach has been taken to enable accurate targeting of especially vulnerable families suffering from chronic poverty, using communities as first instance resource to identify the most destitute in a given area of particular deprivation and feeding information up to planning levels. The approach is time and resource intensive but considered by humanitarian agencies to be necessary and effective for accurate targeting.

- In both contexts a cash-transfer delivery system helped those targeted to regain a measure of food security and also used by beneficiaries to restart their livelihoods.

- The most appropriate approach in both countries was stated to be working through traditional partners: In the more stable period following the disasters and in chronic emergencies, international agencies in both cities worked through traditional government and NGO partners at central and local levels, who in turn worked through local community leaders to identify the most vulnerable, followed up by house-to-house verification by agency staff.  Finely-tuned targeting to those with special needs was done through partnerships with community groups, such as Oxfam, Help Age International, WFP and the IFRC, all of whom worked through their traditional and established community or local NGO or local government partners. This worked well according to those interviewed: targeting was not only accurate but accepted by the community.

- Given the special concerns of refugees in Nairobi, UNHCR worked through international NGO partners to assist ‘invisible’ refugees. Mobile phones were used to send text messages to indicate where assistance could be provided; messages were spread through word of mouth and refugee networks.

- A concern raised in evaluations on Manila was the resort to ‘easy targeting’: international agency targeting was, in the early post-crisis phase, directed predominantly to survivors in easily accessible and visible locations, ie. those in ECs.  Later on, working through a combination of community groups and local government departments (barangay leaders in the case of Manila) agencies directed more assistance to those remaining in their flooded houses and those in more remote areas on the margins of the city. In Eldoret, vulnerable groups were easy to target as they self-directed themselves into informal settlements which later became IDP camps. This then became a more traditional rural format, easier for aid targeting purposes.

b . Tools to address targeting in a sudden onset disaster

- Aerial targeting: this was undertaken by WFP and World Vision in Manila to identify those areas most affected by the flooding, and to use subsequent demographic data from the Department of Social Welfare and Development (DSWD) to calculate the amount of assistance likely to be needed in those areas. Such a method presupposes that demographic data exists, or has not been destroyed. It is useful for an immediate rapid appraisal of disaster-struck areas but limited to this phase.

- Blanket targeting: Applicable only in the post-crisis phase when whole disaster-affected populations need some form of assistance and no distinctions between the different groups is yet possible. The decision of when to withdraw blanket assistance needs to be undertaken as a participatory exercise between government officials and assisting agencies, eg. in the case of WFP in all three contexts, in consultations with local government, agencies, community leaders and CBOs.

- Remittances: there is only anecdotal evidence to indicate the degree of support drawn from friends and relatives abroad or in better-off parts of the country. However, none of the community members interviewed in the case studies attested to having received support from this source. Targeting done in this way can be useful in assisting those with the requisite networks but inevitably omits many more who do not have them.

c. Tools to address targeting in a chronic emergency

- Community-based surveys: See model below. The salient features of these surveys are: (i) community participation essential to do first-instance targeting of most vulnerable; (ii) specific vulnerability criteria according to the needs of the community and poverty context; (iii) constant monitoring /house-to-house verification; stable security environment.

- IDP Urban Profiling: similar in approach to community-based surveys, it uses sampling techniques to identify high-density IDP areas and control groups. Questions do not ask about displacement but draw out household information that enable identification of IDPs through analysis of answers. UNHCR assisted the GoK to undertake IDP profiling throughout the country in the PEV context, adapting it to the ‘urban’ model for Nairobi.

- Information Centres:  These are being considered by UNHCR’s implementing partner, IRC (International Rescue Committee) in Nairobi. The centres would act as a drop-in hub where refugees fearful of detection can find information on issues such as their rights and responsibilities, citizen self-help groups, legal and SGBV counseling, HIV/AIDS treatment, and a range of other services available in their community. The aim is to allow refugees to ‘self-target’ by seeking the services they need for their protection and welfare.

- Remittances: see above, particularly relevant in chronic emergencies. A number of studies indicate these are important sources of support to many urban IDPs and refugees.

Examples of models and tools used in vulnerability targeting in urban areas:

Cash transfers are emerging as tool used in urban settings, dependent on that the conditions conducive to their implementation are found in urban areas, for instance, the existence and functioning of markets, security and rule of law, availability of necessary stocks needed by the affected population etc. A joint programme organized by the GoK, WFP, Care, Concern and Oxfam aimed to target especially vulnerable groups in Nairobi by providing them with small cash grants over an eight-month period. The cash transfer programme was implemented in several stages, by first having community committees target the most needy, followed by agency house-to-house verification, registration in the programme and the distribution of a sim card that allowed the beneficiaries to access cash through mobile phone transfer. Details of this scheme can be found at http://www.alnap.org/pools/files/innovationcasestudyno1-concern.pdf. The cash transfers aided families initially to gain food security and subsequently allowed them to use the money to establish micro-enterprises. A few beneficiaries of this scheme were so successfully assisted that, after a few months, they asked Concern to target another family instead of them.

‘Map Kibera’ draws upon community participation to digitally map the Kibera slum with GPS mapping tools. The maps are shared with communities to input essential features in their community, such as water points, streets, schools, health, religious and information centres, even individual houses. The maps (hard as well as soft copies) can be used for a variety of applications and can be added to as community features change.  http://mapkibera.org/

In Manila, the CCCM Cluster developed a tool for IDP tracking, identifying needs and gaps in service delivery to affected population. The Humanitarian Response Monitoring System identifies vulnerabilities through beneficiary profiling: information gathered for the GoP Access Card, a kind of registration card that enables those eligible to claim assistance. Vulnerabilities captured through this tool include GBV, children, IDPs. The tool is used in partnership with the DSWD, all stakeholders in the CCCM Cluster and other clusters.

  - Gaps

There is no one-size-fits-all methodology for targeting individuals and families most affected in urban areas due to a) dispersed families in urban areas, b) variations in population density, c) different forms of organization for affected population after a crisis such as camps, host families, evacuation centres/ collective centres and self settled camps/settlements etc, requiring varied approaches for identification and targeting. and the difficulties of identifying those who may be moving around and/or wishing to remain invisible in search of safety remains of great concern. Targeting approaches during the immediate relief phase have to change later to address evolving situations such as security and access. Access difficulties to aid actors in the immediate aftermath of emergencies mean that many of those who remain in their homes, inaccessible to food trucks or other forms of assistance must rely on community support, remittances or nearby relatives and friends.

  - Recommendations for improvements

- One way to address access challenges would be to set up distribution points in urban areas with messages over the media or by text-messaging to indicate their location, allowing those in need to find their way to the nearest distribution point. However, this needs to be done with due consideration of all contextual factors as it raises inevitable questions of safety: beneficiaries may be targeted by gangs of looters to divest them of their supplies in the proximity of the distribution point.

- In a more stable phase, to distinguish between the chronically urban poor and those affected by crisis, most agencies agree that proper vulnerability targeting, based on a case-by-case needs criteria in each urban area, cannot be ‘short-circuited’. This requires a household survey method, such as the urban IDP profiling methodology, which can only be done in a safe environment with sufficient time and financial resources.

- For those fearful of detection, information ‘drop-in’ centres should be considered more widely in urban areas, allowing for ‘self-targeting’ of visitors to find information on services in their community and to seek protection.

- Technology advances are opening the way to pilot ‘biometric identification’ to help agencies track beneficiaries of assistance and reduce the incidence of ‘double dippers’. Nairobi and other urban areas hosting a high number of chronically poor would be ideal testing ground for such techniques, given the mobility of the urban poor and those affected by crises.

2. Coordination

Urban areas usually contain higher numbers and diversity of aid responders than rural areas, having implications for coordination of response in a crisis situation. Capitals can draw upon national and municipal authorities, international, national and community organizations, private sector, municipal service delivery bodies, and a generally higher level of educated population groups. On one hand, a greater number of actors can facilitate access to communities and coordination, but if not well-planned, the greater numbers pose a challenge to coordinate. Accountability of humanitarian aid reaching those who need it is greater because of direct knowledge of the communities, residents and needs by these actors. Opportunities to harness the various different actors as part of the aid monitoring process should not be missed.

- Identifying the challenges

Coordination was cited as being considerably more difficult in the Nairobi and Manila urban contexts than in rural ones because of:

  - More actors to coordinate;

  - Cluster decision-making risked being slowed by too many voices;

  - High numbers of unknown local actors: NGOs, CBOs, private companies, who remained outside the cluster mechanism but who needed to be coordinated at the local level;

  - Distances to travel to meeting fora, further complicated by traffic jams;

  - Concentration and concerns of national level actors tended to obscure the coordination needs of local actors (central GoK departments in Nairobi viz-a-viz local departments in Eldoret, and the pre-eminence of the NDCC over LDCCs and LGUs in Manila).

A common challenge to both countries was the ‘silo effect’ produced by cluster coordination with inadequate cross-cluster coordination. While not specifically an urban problem, it was felt more keenly at the urban level due to the unwieldiness of the greater number of actors.

Another common challenge was ensuring horizontal coordination (between different actors in the city) and vertical coordination (between central government and organizations with their counterparts in the field). Eldoret officials in Kenya were frustrated that they often learnt of central government decisions and policies through international partners at local coordination fora, not from their own departments at central level.  As the emergency progresses and systems are set up, the need for local-level coordination becomes more pressing but in Eldoret there was no indication from central government as to which local authority should be in charge of local coordination. In the Philippines case of Metro Manila, the National Disaster Coordinating Council is replicated at regional (province) level and local (municipality) level but each has different roles and responsibilities. LGUs should, according to NDCC and other government authorities, coordinate activities within their administrative boundaries but this was not done in the aftermath of the disaster – even where municipal structures were less affected. The local level coordination gap left international actors unsure about whom they should coordinate with, resulting in ad hoc arrangements and a missed opportunity for programmatic synergies.

- Tools and Approaches

- Cluster coordination was strong in Nairobi during and after the crisis, due to the long-term presence of OCHA and long-established coordination mechanisms, which worked well. Specific to the urban challenge was the issue of blocked road access and lack of information on the affected areas and population during the height of the disaster, but informal networks of coordinating agencies were able to disseminate information, when available, by electronic means and the physical coordination centres just outside the city could continue without disruption. Agencies had established offices, programmes and networks in the country and heightened security of office assets and staff was a major issue.

- The CERF tool to secure rapid funding for the emergency was attested by all interviewees in Nairobi to have been effective and timely in accessing emergency funds.

- In Manila coordination between international organizations was weak to non-existent prior to the disaster because the pre-disaster context was mainly a development one where clusters are not required. The sudden onset disaster was reported to have overwhelmed the capacities of the national and local government and the UN organizations. Urban areas in metro Manila which were affected by the typhoons were unprepared for the emergency of such a scale. Coordination was haphazard and did not follow established SOPs because the planned rescuers became themselves victims. Some municipalities such as Marikina had preparedness plans in place but their operationalization proved inadequate because of the high degree of flooding impeding access. The disaster caught everyone by surprise and it took some weeks before coordination under the auspices of the UN became systematized and effective. Government officials were consternated by the perceived ‘paternalistic’ attitude of the international agencies in the clusters, feeling marginalized and by-passed.

- International NGOs coordinated through PINGON (Philippines International NGO Network) which was activated the day after the disaster and served initially as an information-sharing forum for partners. Gradually coordination with the GoP strengthened, the clusters liaising with the GoP through the NDCC, and with Oxfam, an early member of the UN cluster system, relaying information back to PINGON.

- In Nairobi, programmatic coordination was effectively enhanced with respect to addressing the needs of the most destitute of the chronically urban poor by the grouping together of the GoK, WFP, Oxfam, Concern and Care to jointly design and implement the cash transfer programme to various affected families throughout the city (see above).

- In Manila, the GoP adopted the cluster mechanism to the early recovery context where it now takes the lead in the Health, WASH and Early Recovery clusters (but not Shelter). This has to some extent smoothed the transition from UN-led to GoP-led coordination and ensured continuity from the relief phase, furthermore representing good practice in having the government take the lead.

- Gap Areas

The greater number of actors in urban areas calls for coordination mechanisms adjusted to the challenges of traffic jams and time spent in attending coordination meetings. This has not been realized in either of the case study cities and it is difficult to see how it can be: post-crisis coordination needs a centralized approach, but this means long hours of precious time being spent in traffic for attending agencies. On the other hand, interviewees all recognized the need for de-centralized coordination to take place at the local level concurrently with centralized coordination. Not only would local coordination address the priorities specific to each area but would enhance relationships and partnerships between actors operating in them. Future preparedness plans should address this need, jointly between governments and international agencies.

- Recommendations for improvements

In both countries it is necessary to put in place a local coordination mechanism that can be activated through a designated national and international agency in times of emergency. The mechanism should be tested for scaling up and down, after the heat of the emergency has abated.

Opportunities exist to leverage resources and inputs from communities, NGOs and private sector companies. These need to be explored and mechanisms put in place to activate them in times of emergency through newly-established SOPs, as well as to harness their knowledge for effective monitoring aid delivery.

Community-based organizations in urban areas know the community. Improved coordination planning should include knowledge of and access to CBOs to draw on them to coordinate and assist identification of where assistance is most needed.

3.   Partnerships and National Capacity Development in Urban Areas

a)   Identifying the challenges

Humanitarian agencies have been conducting activities for many years in Kenya and are mostly familiar with the government structure and national institutions. Prior to 2008 they engaged predominantly in food security and development programmes in rural areas with a variety of partners, including the GoK.  Following the post-election violence in 2008 that brought devastation and chaos to urban areas, a new set of partnerships were necessary to work in these areas. The problem was not so much the absence of possible partners, because there are many government departments, civil society groups and local NGOs in urban areas. The challenge was more in assessing which ones would be the most appropriate, in terms of capacity, technical skills and community outreach, and resources with whom to implement specific tasks and activities. This challenge was further exacerbated by the disabled status of most of the possible partners by the violence and its aftermath. A challenge for humanitarian organizations is how to address the vacuum of partners in conflict or natural disaster settings.

The fabric of local urban communities, already fragile from facing competition of resources - was further damaged through the violence, which was divided along ethnic and political fault lines. Caught up in, and themselves affected by the violence, it was difficult for the Government of Kenya (GoK) and CBOs to respond to humanitarian needs or to be able to form partnerships with international actors due to the disruption of their usual community activities.

While disasters are frequent annual occurrences in the Philippines, the GoP had thus far retained the capacity and means to address them unilaterally or with limited external assistance. Previous disasters – mainly flooding, landslides and volcanic eruptions – affected predominantly rural areas. The tropical storms of 2009 that hit Metro-Manila caught all parties unawares: the government, civil society, the population and the humanitarian community, necessitating a rapid scale up of emergency response activities and requiring partnerships previously unexplored. As in Nairobi, the problem was in distinguishing which of the many community-based partners would be the most appropriate with whom to work, in terms of capacity, technical ability and community outreach. Added to this problem was, especially for the many emergency teams newly arrived in the country, understanding the complex and sophisticated government structure for disaster coordination and management at both national and local levels in the midst of a full-blown emergency.

Both countries have well-established government structures keen to take the lead in addressing emergencies but the sheer scale of the crisis overwhelmed their capacity to respond effectively and comprehensively. In Kenya the post-election violence was political in nature and government actors did not enjoy the trust of all citizens. Additionally, the government’s response to violence is usually through the army and/or police and these actors can exacerbate an already inflammable situation, such that the post-election violence risked amplification. In the Philippines the government, both at national and local levels, is traditionally the ‘first responder’ in emergencies and is geared to reacting swiftly to bring relief to affected populations.  The 2009 storms affected government personnel such that they became the victims, along with the rest of the affected population, and were unable to respond rapidly or effectively at either central or local levels.

The logic of LGUs taking the lead in disaster response at the barangay level is understood well in the Phillipines context, as they are closer to the disaster affected areas and sites, and have contact with the affected population. However, the LGUs have very weak capacities at the local level, with very few financial resources, latests tools and equipment, modern early warning systems, the disaster coordinating councils do not exist at the Barangay level, but do exist at national, provincial, and municipal level, where the national disaster coordinating council takes the lead in coordinating disaster prevention and response, but is not an implementing body on disaster preparedness and response, and is left to the LGUs and other organizations to respond to.

a)  Tools and Approaches

In both countries a range of similar measures were taken to identify and select partners and to collaborate with national and local authorities. Although the activation of partnerships took some time, the following were noted as examples of good practice in urban areas.

Community-based organizations (CBOs): In both countries, the difference between rural and urban partnerships was that, in the latter, community-based organizations became the ‘partners of choice’ in most (but not all) cases by virtue of their knowledge of the affected communities and the work that needed to be performed in those communities. In rural areas, by contrast, traditional partnerships tend to be between a combination of government departments and international or local NGOs.

Established partnerships: In both countries, partnerships that had been well-established prior to the emergencies were most effective in responding rapidly and efficiently, using pre-arranged SOPs with clear roles and responsibilities. A good example is that between the IFRC with Red Cross Societies in both countries. Although this partnership is not specific to urban areas, the RCs have extensive outreach networks in urban areas which enable them to respond rapidly, even in the worst hit areas and communities. Similarly, international NGOs such as Oxfam, Save the Children and World Vision in the Philippines were able to rapidly re-direct their attention from activities in Mindanao and to work with their traditional local partners to undertake a joint rapid needs assessment in Manila.  Help Age International supported COSE (Coalition of Services of the Elderly), itself in partnership with COPAP (Confederation of Older Persons Association of the Philippines), to bring immediate life-saving and material relief to those trapped in their flooded homes and later worked closely with the DSWD to target specific assistance programmes to the elderly and their families.  In Kenya, Oxfam, Concern and Care all worked through their traditional partners to respond to the PEV in urban areas while WHO, UNICEF, MSF and the DoH in Kenya drew on their close working relationship to ensure a rapid response in difficult-to-access urban hotspots in Nairobi and other parts of the country. WFP’s “Forward Purchasing Tool” allowed WFP to access it from its stocks in Mombasa and sell it to partners who needed it for distribution to affected populations. These examples demonstrate the need for investing in high risk countries for building capacities of national NGOs and the private sector in humanitarian response. In emergency situations, these resources can be leveraged in urban areas.

Government partnerships: In both countries international agencies had built up strong partnerships with government departments prior to the emergency, such as WHO and the respective Government Health Departments, UNICEF, UNDP, UNHCR and WFP with Departments of Social Welfare, Education, and others. In Manila, despite partnerships having been built up in rural areas, none of the agencies had relations with local (municipal) government units (LGUs) prior to the disaster, so these had to be forged from scratch in the midst of the emergency. In Kenya, IASC agencies were able to re-direct their existing government partnerships to jointly address the challenges in urban areas. WFP worked with its GOK and other partners in the Kenya Food Security Steering Group (KFSG) to undertake an “Urban food Security and Nutritional Baseline” survey in Nairobi slum areas with the aim of providing evidence for specific intervention triggers. UNHCR partnered with the Department of Mitigation and Resettlement to assist the latter in conducting a study to profile IDPs throughout the country.

Inter- and Intra-Community partnerships: See under ‘Vulnerabilities and Targeting’ above for a description of community self-help.

Private-sector partnerships were also built in both countries: WFP in Kenya had previously forged partnerships with local food suppliers and negotiated pro forma agreements which were activated in times of emergency.  World Vision, IFRC and other NGOs did the same in Manila, but only after the emergency. Several agencies are considering preparing such pro forma arrangements as part of their preparedness activities. UN-HABITAT has had long-standing partnerships with Habitat for Humanity and with individual companies of architects and other technical actors.

New partnerships: these usually take time to develop and are not advisable in the context of a full-blown emergency.  A good example of a new partnership was found in Eldoret where Save the Children partnered with the Ex-Street Children Community Organization (ECCO), building their capacity and resources to expand protection activities for this extremely vulnerable group, requiring a highly specialized approach.

The Cluster mechanism in both countries served as a useful tool to collect and disseminate examples of community-based partners with specific competencies or areas of expertise and it was reported that some agencies had used the information provided to select local partners.

While all the above approaches constitute good practice, what came out most emphatically from both case studies was the importance of building up urban partnerships and invest in capacities before a disaster, jointly establishing and rehearsing SOPs that can be rapidly and effectively activated in an emergency. Private-public partnerships are particularly interesting examples of how flexible arrangements can be made for instance with local suppliers: since it is generally considered good practice to buy, where possible, local products through local agents rather than stockpile cumbersome tonnages of goods in urban areas where storage space is at a premium, a lighter arrangement can be made to activate previously negotiated pro forma contracts to ensure priority procurement of goods for early response. Similarly for shelter,  private sector, BDO, one of the largest private sector organizations in the Phillipines was able to mobilize resources from individual national and international funding for the relief goods and shelter for the recovery phase.

- Gap Areas

There is much more that agencies can do to build strategic partnerships in preparation for emergencies, particularly in high risk countries on a long-term basis. The above examples show different models for entering into partnerships and building capacities, working models and trust. For international agencies arriving for the first time in a country after a disaster, it is likely to be more difficult to identify viable partners. For such cases it may be best, where possible, to partner with government departments in the first instance (assuming these are operational) and to learn from cluster coordination which other local partners may be considered worthy. For such arrangements, however, it is best to take time over the selection and capacity-building process, and scale activities up gradually - as Merlin found in Manila. In the cases point out to an enormous potential for developing partnerships with the private sector in the city, given that this is the central hub for most companies. For instance, Coca Cola has very big water filtration systems which could be tapped for clean water provision – but the question is how to design the approaches. Clusters could join together and advocate with private sector companies for joint preparedness activities. The media could also be a powerful partner in an emergency, capturing difficult-to-reach audiences with key messages, warnings, advice etc. for a variety of different purposes – another possibility which could be explored in preparation for the next emergency.

Capacities can be understood as knowledge and experience, manpower, partnerships and resources in urban areas.  The following gaps exist in urban areas, which the IASC organizations must focus upon:

b) Capacity of the National Governments and municipalities in general is very weak. There exist differences in municipalities in terms of size and resources, and resource and capacities of communities and local organizations.

d) Capacities of emergency responders (Govt, NGOs) when they themselves are affected, as witnessed in the Phillipines were affected, and hence capacities in terms of human resources had to be employed from neighbouring cities. World Vision is now developing a plan in the Phillipines to enhance capacities for provincial offices in nearby cities for disaster response.

d)  Recommendations for improvements:

Preparation is the key to strengthen existing, or create new SOPs for partners in urban-based emergencies and to set in place mechanisms for rapid partner scale up. In anticipation of partners themselves being affected by the disaster it would be wise to create standby partners in neighbouring provinces or even regional partners who can step in an emergency, assuming there is little or no capacity remaining operational in the disaster hit areas (as in Haiti). Agency preparedness plans should include the identification of partners in provinces or nearby cities who may not be affected by an urban emergency and could step in to work jointly with others. This would require agencies to undertake mapping of capacities to identify suitable partners in similar fields.

Sectoral Challenges in Urban Areas

This section examines key sectoral challenges in urban areas, identified by interviewees as: Shelter, WASH, Health and Protection /Violence. Key common challenges specific to urban areas as opposed to rural include:

1. Shelter challenges

In both Nairobi and Manila, the disasters had the greatest effect on informal settlements – especially those located along the banks of rivers, canals, ‘esteros’ and the Laguna de Bay in the Metro Manila area.  Many of the crowded and fragile structures closest to the water were completely destroyed by the fast-flowing floodwaters, leaving many with nowhere to return to. Three weeks after the 2009 tropical storms Ketsana and Parma (Mirinae is rarely mentioned), the Emergency Shelter Cluster drafted an initial shelter strategy, identifying the different target population groups per the following:

Most vulnerable families and populations* affected by the typhoons:

- who remain in or live nearby their damaged homes and need shelter support

- who live with host families and need shelter support; this may also include the host families

- who need help to rebuild their partially or totally damaged houses

- who live in evacuation centres and need shelter support

- who live in evacuation centres and can return to their homes and need shelter support

*especially people with disabilities, elderly, children, female headed households and other disadvantaged groups.

At the time of the case study, some 5,402 people remained in 54 evacuation centres in the most affected municipalities, and another ……… in transitional shelter on land provided by the municipalities for temporary purposes. According to some reports, many people prefer to remain in the transitional shelter sites since their homes were either completely destroyed or so badly damaged they are uninhabitable. The most vulnerable group, however, remains those in evacuation centres: covered sports courts with plastic sheeting with continued dependency on food and non-food aid.

In Nairobi, the pre-existing vulnerability of fragile homes and shelter in informal settlement and their sheer numbers and density made them easily destructible.  A post-election IDP Profiling Study conducted by the GoK produced a national statistic of 663,921, but it is unclear how many of these are estimated to be in Nairobi, and how many there remain today, or where they are.

- Identification of the challenges

“Many cities are no longer safe havens to which to escape. Indeed, now they often expose their civilian population in ways that make everyone a potential victim of violence”.

Nairobi

- Slums are so densely compacted, houses are literally built on sewage dumps. Any spare land in the slum is rapidly claimed and built upon.

- Lack of land title in slum areas, or titles exist but are not transparent or transferable.

- No space to build emergency shelter for evacuees in an emergency in Nairobi slum areas or even further afield.

- According to the MoSSP and supported by humanitarian agencies, crisis-affected people tend to flee to areas where they can stay with host families of the same ethnic group. This is also true of urban refugees. Others rent space where their means allow. Families also move around to maximize their coping strategies, so it is difficult to enumerate them accurately.

Eldoret

- PEV-related IDPs were housed in IDP camps during the height of the emergency, in a more traditional rural model of humanitarian shelter.  They were easier to enumerate there.

- Others stayed with host-families. Same challenges as those encountered in Nairobi to identify and enumerate.

- While return and reintegration was one option for PEV IDPs and many have returned to their home areas, others are still fearful of insecurity there and remain in self-settled camps or have melted into the urban poor areas in Eldoret’s slums. IDPs encountered in the community said they tried many coping strategies, including moving to Nairobi, but returned to Eldoret having described social conditions in Kibera as ‘merciless’.  This is one challenge of capital cities, where sometimes more humanitarian assistance may be available, but the pressure on services is immense.

- The GoK has now closed the shelter programme and is offering no more assistance. However, many people remain displaced without recourse to any assistance.

Manila

- The scale of the disaster revealed the inadequacy of government preparedness measures: while evacuation centres are designated as public infrastructure: schools, sports courts, stadiums, churches, community centres, etc. these proved inadequate in terms of space and equipment for the number of people displaced by the flooding;

- Inadequate facilities – toilets, washrooms, waste disposal – at the ECs for the number of users: well below Sphere standards and indicators in all sectors except food. The slow rate of declining water levels meant that families could not return to their homes for months after the disaster, prolonging an acutely uncomfortable situation for all.

- ECs put school activities on hold in the affected areas. This presented conflicting priorities between those with nowhere else to go and parents becoming increasingly vocal about the need to re-open the schools. Finally the government was obliged to remove all the school occupiers by mid-November 2009 to allow the schools to re-open. Some went to Transitional-Shelter sites and others either melted back into the informal settlements, received assistance for relocation, or went to stay with relatives in rural areas.

- Difficulty in finding appropriate land for temporary living space and long-term resettlement/relocation.  A majority of the displaced are unable to return to their former homes (renters, squatters and the landless). Many of the informal settlers are planned to be relocated to sites outside the city, where they have no social networks and are far removed from their previous livelihoods. Many people, having heard about plans to build post disaster shelters in the city centre, prefer to put up with sub-standard living conditions hoping they might sooner or later benefit from this option.

The common challenge in all three case studies is how to provide sufficient shelter to all those who need it while longer-term housing solutions are being slowly implemented.

- Tools and approaches adopted in the post-crisis aftermath

Some shelter assistance in the form of shelter materials to urban IDPs in Eldoret. However, since many had been used to living in concrete structures and hence were not willing to accept the assistance of what they considered inferior materials.

The GoK gave cash compensation to those who lost their homes, and an additional amount to those availing themselves of the return option. However, anecdotal reports indicate that those targeted did not receive the full amount of their grants, percentage amounts having presumed to have been skimmed by local officials.

Presidential Executive Order 803 of 21 May 2009 created a Metro-Manila Inter-Agency Committee on Informal Settlers (MMIAC) and mandated it to draft a ‘Comprehensive Shelter Program’ (CSP) for the relocation of informal settlers, which is being currently implemented. However, implementation takes time due to lack of resources, available land and negotiations with the affected population on the needs and processes of those being resettled.

Several international agencies are assisting the GoP to relocate those willing to avail themselves of this option;

GoP/shelter cluster discussion over the use and appropriateness of ECs resulted in these being confirmed as the only option as emergency shelter sites. Consideration of other options led to recognition that providing dedicated facilities for evacuation would result in the likelihood of these being taken over as informal settlements.

Where possible, house owners have been assisted to rebuild their homes with building materials and technical assistance to ensure sound construction.

The private media company, ABS-CBN is assisting relocation through the development of low-cost, medium-rise apartments for those who can pay modest rents. This is an interesting disaster reconstruction model of an integrated approach, including infrastructure planning, livelihoods and training on composting techniques as a home enterprise (among other activities).

WFP is offering Food for Assets and Food for Training to those opting for relocation in support of the GoP relocation programme. Food is provided for families building their new houses and community infrastructure, as well as during livelihoods training.

c)	Outstanding Gap Areas

The predominant gap is what to do with the high number of homeless people, the majority of whom used to live in informal settlements but have no independent means to rebuild their destroyed homes (little more than fragile shacks prior to the disaster). International agencies will not go against government regulations (or their own principles) by providing reconstruction assistance to those living in informal settlements or on land where ownership or right-of-use does not exist or is contested. The transitional shelter sites cannot be used indefinitely:

The urban municipal infrastructure is under immense pressure in the already high dense urban areas and services such as water, sanitation, electricity and waste removal are stretching municipality services and budgets.

While relocation represents one option for a long-term solution and conforms with urban planning regulations, an urgent solution is needed for the homeless waiting for the new housing to be built.  In Manila, recognizing the need for an urgent interim housing solution, UN-Habitat, the GoP and the shelter cluster are examining the feasibility of facilitating transitional shelter solutions in informal settlements while waiting for the new housing to come on line. There are opportunities, currently being identified, to undertake temporary repairs and retrofitting to houses in areas that are marginally less at-risk of natural hazards.  It would be possible, for example, to assist some families build on top of their existing homes – even though there is no legal title because zoning laws prohibit such land being used for residential purposes. The families would benefit two-fold: from strengthening their own house with appropriate materials and technical advice, and from one or two storeys being added to their homes, also from donated materials and advice, which they can rent out to homeless former members of the community. Since most people were paying some kind of rent prior to the emergency, there is a culture of rent-paying which should open the way to providing transitional shelter to the homeless. Benefits from the system would include:

A short-term priority in both cities is to develop a Master Plan of those needing resettlement from slum areas. This would be a relatively straight-forward and cost-effective exercise entailing enumeration by local community leaders, verified by independent sources,  and registering people on a waiting list for different options of housing. Bio-metric ID schemes could be tested at the same time to avoid ‘double dippers’.

Implementing such a scheme in Nairobi and Eldoret could include data collection on IDPs in a variation on the IDP urban profiling tool to capture a better understanding of how many people remain displaced, in what kind of situation (host family, rental, squatting, etc.) and other essential socio-economic data. This would provide an entry point to designing humanitarian, recovery and development programmes in addition to urban planning for residential areas.

Opportunities exist to step up support to host families in emergencies. If these are well-supported they can alleviate pressures on ECs, which IDPs go to only in a last resort, given their well-known unhealthy and crowded conditions.  Only been timid attempts have been undertaken to address host family options (Goma and Bukavu) but past experience (Swiss CDC, Aceh) show that host families can provide long-term shelter and safe haven if provided with targeted support. It is time to develop a strategy for host family options in the context of IDPs, emergency shelter and transitional shelter.

2. WASH challenges

a)  Identification of the challenges

These are different to those encountered in rural areas for the following reasons:

In rural areas it is easy to sink a borehole and create a well. In tightly-packed urban slum areas it is difficult not only to find the space to do this but harder and more expensive to drill beneath concrete and to maintain proper care of a well. The sheer numbers of people using it could contaminate it, rendering unfit any drinking water. Maintenance is an issue.

In evacuation centres the existing water, sanitation and waste facilities are quickly overwhelmed by the number of people using them. There is no space for temporary construction of additional facilities. Humanitarian actors in the WASH sector are among those most concerned about the challenges of providing adequate facilities, even way below SPHERE standards, since these have enormous health implications.

Faced with challenges such as ‘flying toilets’ and large swathes of raw sewage in both Nairobi and Manila slums, humanitarians and development actors need to work together in re-thinking the whole concept of WASH provision in dense urban areas.

Sanitary conditions are particularly problematic in Nairobi’s slums where a majority of residents resort to pit latrines that are over-used and inadequately maintained. Nairobi is overwhelmed by refuse generation as the council’s collection service is inefficient and restricted to a few areas only. At times Nairobi experiences acute water supply shortages, in addition to problems of distribution, waste, illegal connections, overloading and mismanagement, all of which contribute to supply shortages.

- Tools and approaches adopted in the post-crisis aftermath

        - In Nairobi, OXFAM and other agencies are looking at innovative ways to provide safer and more sanitary toilet systems to households in the slum areas. This entails a ‘commode’ type toilet which can be used at household level, the contents of the commode can be emptied at designated waste points.

        - A variation on this theme (from internet research) is the ‘peepoo’ bag, biodegradable and usable as compost on garden plots (though these are rarely available in slum areas). The Peepoo eliminates fixed and hard infrastructure for a soft approach to sanitation and excreta management.

        - In the team’s visit to Mathere slum (Nairobi) the team witnessed safe and well-run water and waste systems, installed and run by the community. There is a small fee for water collection and the proceeds feed back to paying for maintenance. Residents interviewed said they were able to afford the small amounts, which are not as high as commercial rates. Waste is gathered in a specific site and collected twice a week by the council.

        - In Manila, Save the Children and Oxfam constructed raised toilets in transitional sites to take into account high water levels. Desludging is organized by the municipality, but this is a temporary solution and not intended for the long-term. A remaining gap is in ECs, where there are insufficient sanitary conditions for the number of people using them.

- Gaps

WASH solutions need to be designed according to the urban context and there is no ‘one-size-fits-all’ solution because of the different land and water table configurations in individual cities, and in different areas within cities. It is not possible to have a generic solution, but the examples above provide temporary measures.

- Recommendations

- In Manila humanitarian actors should advocate with LGUs to upgrade school toilet facilities to comply with minimum national standards for schools. This would go part-way to improving their situation. However, in times of emergency it is necessary for LGUs to have on hand, or organize standby procurement arrangements for additional ‘portoilets’ that can be deployed rapidly to ECs.

- In other urban areas ‘contextual’ responses need to be worked out for different sanitation arrangements according to the geo-physical nature of the land. Advocacy with municipal government officials should be stepped up to improve waste removal conditions in slum areas. The above UN-HABITAT and community-based solutions mentioned above can be developed for longer-term combinations of waste disposal and livelihoods.

- For large-scale disasters impacting heavily-populated areas (eg. Haiti), OXFAM advocates for better preparedness by aid agencies to cope with heavy demands for WASH facilities. These need to take into account adequate numbers of water bladders and desludging mechanisms, vital to prevent outbreaks of water-related diseases, and engineers with experience of working in urban areas. The WASH agencies are struggling to meet the population’s needs in Haiti mainly due to lack of desludging facilities.

    - Health challenges

- Identifying the challenges

In both case studies the main challenge recognized by all health actors is the lack of disaggregated data.  This is largely due to the way statistics are collected. In Nairobi, health and other statistics are collected at District level, but this is too big and diverse a level of analysis by which to capture the very different situations between the better-off, middle class areas and the slum areas that share the same district. Thus the statistics, averaged out between these different areas, do not give an accurate picture of the worsening humanitarian emergency in the slums.  While a ‘chronic emergency’ is suspected by aid actors, it is hard to base it on documented demographic evidence. MSF-B says it is impossible to track deaths in slums since statistics are unreliable: people often return to their home areas when they are sick and dying; others are buried in unknown ways.

In Manila, disaggregated health statistics are collected by the DoH, but they are not disaggregated by geographical area, which creates inefficiencies in preparing for disasters (how to stockpile adequate supplies when the potential number of victims is not known). These however are not urban specific challenges. Disaster-related deaths resulted from the inability of medical staff to diagnose leptospirosis, so it did not get treated. Over 100 deaths could have been prevented.

      - Tools and approaches

WHO and MSF-B attested to having worked well with the DoH during the PEV in Nairobi and throughout the country. WHO was able to tap into CERF funds which it used to help NGOs and DoH purchase essential medicines and equipment for rapid deployment to affected areas.  No deaths were recorded as resulting from inadequate health or medical-related response.

To address the lack of surveillance data in future emergencies, DoH with technical support from WHO and the Health Cluster in Manila are developing a new tool : Surveillance in Post-Extreme Emergencies and Disasters (SPEED) as an early warning surveillance system for post disaster situations. Rolled out in May 2010, planned activities entail training to health centres around the country on how to install and use the system to track disease incidence through sms reporting to computer based hubs in health centres.

      - Gaps

Improved health surveillance systems in urban are a priority but have not yet been addressed. A lack of resources to employ more health workers in urban slums is a problem in Nairobi, whereas the issue in Manila is a mismatch between existing capacities and their full deployment.

      - Recommendations

WHO and humanitarian agencies should advocate with the GoK for statistical collection and analysis according to discrete slum areas in Kenya. The current methods do not allow for a full picture of health or other concerns in these areas, negating the possibility to respond effectively.

In Manila, the SPEED rollout and testing should improve health surveillance in urban areas and could serve as a model for other urban contexts.

4.5.4.   Protection and Violence

The World Health Organization (WHO) defines violence as ‘the intentional use of physical force or power, threatened or actual, against oneself, another person, or against a group or a community that either results in or has a high likelihood of resulting in injury, death, psychological harm, maldevelopment or deprivation’ (WHO, 2002, p. 5 ). As this definition implies, violence is not only a physical act but also a phenomenon that can be embedded in wider social structures. Exploitation, exclusion, inequality and injustice can all constitute violence.

- Identifying the challenges

- In Kenya priority protection challenges include: access to land and housing for IDPs, both in self-help groups and transit sites. UNHCR is concerned about the issue of land titles for land purchased by IDPs with their compensation funds, or against anticipated compensation, on the grounds that this is legally precarious. There are instances of IDPs having been given fake/ contested titles or squatting on land they are yet to own legally and hence face a constant threat of eviction. In transit sites the issue is not land titles since many own the land, but a lack of housing which continues to be of concern despite many ongoing housing construction projects.  Instances of SGBV –prostitution/ survival sex and child abuse is reported to be on the rise in Eldoret, according to the Protection Working Group. Child protection concerns in areas of return and in urban areas include prostitution and a noticeable rise of street children.  Other protection concerns for IDPs and refugees, especially those affected by the PEV: women and girls in slum areas affected by community violence and SGBV. A significant challenge is how to protect IDPs and refugees who wish to remain anonymous and others who are hard to identify in dispersed communities. Many refugee children from these families are not attending school. Many refugees simply do not know their rights and even with correct documentation, can fall prey to police harassment. Protection issues are different in urban areas to rural – in camps refugees have access to basic goods and services but it is more difficult for them in urban areas to access these. Agencies must be careful not to publish sensitive information about beneficiary statistics in urban areas in case it puts them at risk with the authorities.

- In Manila there are higher protection and violence incidents of a particular urban nature with a greater incidence of stress from poverty and living in cramped conditions or temporary shelter, leading to drink, family conflict and breakup, family violence. As violence is often more prevalent inside the home than out, it is more difficult to detect.  Conflicts can be mediated by barangay officials who can usually solve the problems or advocate cases to other authorities.

- Tools and approaches

- In Kenya, a newly finalized National IDP Policy should soon become an integral part of Kenya’s legal framework, serving as a garantor of IDP protection through all phases of displacement and during the return phase. This should help to gradually de-congest self-styled IDP settlements and stem the flow of IDPs trickling back to urban areas from the camps.

- IRC, a UNHCR implementing partner in Nairobi, works with local organizations running safe houses, though it is not clear if these will ever be sustainable. Through its psycho-social counseling IRC can learn about protection problems and refer refugees to legal support services. The agency is considering setting up ‘information centres’ for people living in Eastleigh neighbourhood (the community of choice of many urban refugees). This would help newly arriving refugees to learn about community goods and services availability, better understand their rights and responsibilities, learn where to get treatment for ‘stigma’ issues such as SGBV and HIV/AIDS, where to get Swahili lessons, etc. Such a centre would be one way to capture the numbers and characteristics of ‘invisible’ IDPs and refugees and act as a profiling tool.

- Save the Children undertook child protection and developed child friendly spaces in the emergency phase that allowed it to detect and refer child trauma, though the programme has ended now. It negotiated with the barangay captains to find suitable space in cramped EC conditions.

- UNHCR in Manila has conducted Training of Trainers of ‘government protection responders’ for LGU officials in Luzon as a pilot project and aims to expand this. The training encompasses international standards in child protection among other protection issues and will be mainstreamed into disaster response SOPs.

- UNHCR has just developed a ‘Participatory Protection Appraisal’ tool which it aims to train LGU staff in, for detecting and appraising protection problems in communities and in disasters. The tool has specific applications for urban settings and would be useful in other contexts.

- Community self-help is instrumental in dealing with family disputes and providing solidarity to victims of domestic violence. The culture is geared towards that kind of support, according to community members interviewed.

- Gaps

Protection issues remain difficult to address in urban areas because of the many people who wish to remain anonymous and the sheer degree of urban violence, especially in Nairobi slums. In addition, protection activities such as information centres are resource-intensive and may not find sufficient donor support.

- Recommendations

- The UNHCR PPA tool shows great promise and, if implemented successfully in the pilot project, could be used in other urban contexts.

- Information centres are useful ‘self-targeting’ support mechanisms for urban communities and could be replicated in more communities, with sufficient funding. They could be tapped as sources for information on urban vulnerability and IDP profiling.

- Agencies can advocate with government departments to have more community health workers who would be trained in dealing with victims of violence and would detect serious problems for referral.

- Agencies, through community groups, could make greater use of information technologies such as text-messaging periodic information about community services, events, new legislation and human rights issues to refugees and IDPs in urban areas.

5.   Preparedness

a)   Identifying the challenges

- In Manila, GoP preparedness plans were out-of-date and overwhelmed by the magnitude of the disaster. The Rapid Assessment tool was found to be too lengthy and cumbersome LDCC preparedness addresses mostly SAR responses but does not deal with follow-up issues such as EC or community preparedness.

- UN and NGO country contingency plans were out of date. None of the preparedness plans took sufficient account of what and how to prepare for disasters in urban areas.   However, apart from the inadequacy of preparedness at all levels, an ‘enabling environment’ has been created by the disasters, with renewed impetus to improve all aspects of preparedness and DRR.  Humanitarian agencies in Nairobi are drawing up contingency plans for future possible violence scenarios in Kenya’s cities in anticipation of the forthcoming Constitution referendum. However, due to government sensitivities the KHCT feels it is unable to conduct joint contingency planning, which would be more efficient and effective if put to the test.

- Tools and Approaches

  - The Humanitarian Country Team has embarked on a holistic contingency planning exercise with plans on how to respond to different kinds of disasters, both rural and urban, at different scales of severity.

  - The GoP (DILG) is preparing training courses on good governance for ‘newly minted’ local government officials, including training on disaster contingency planning, preparedness and response SOPs. Its main concern is how to encourage mayors to update their skills and knowledge of managing disasters.

- Gaps and Recommendations

- Preparedness measures could capitalize on the institutional and individual expertise of a rich variety of actors and competencies that exist in Manila. Furthermore, many actions can be taken that do not require high levels of investment. The emphasis should be on knowledge-based preparedness that becomes gradually hard-wired into individual mindsets and mainstreamed into government and agency activities.

- IASC and non IASC organizations need to anchor their preparedness activities at the municipal level and advocate with mayors and disaster response departments for joint disaster preparedness: defining roles and responsibilities of different actors, priority needs to be addressed etc. Some of the measures can be, mapping of municipal disaster risks and vulnerable areas and population, enhancing capacities of the local government in disaster response and preparedness,, mapping of capacities and resources such as those o private sector enterprises, faith based organizations and NGOs, which could join in simulation exercises and raise their own awareness of preparedness gaps and allow for information-sharing on particularly useful techniques and procedures.

# Recommendations

The following is a summary of recommendations made in the body of this report. These are prioritized according to what can be achieved in the short, medium and longer-term timeframes to help with planning processes. It is best to plan these actions within clusters or sectoral groups in the country and ensure participation of National and Local Government departments in the planning, where possible. Quite a number will require cross-cluster cooperation and coordination (eg. combination of Shelter, CCCM and WASH clusters, Food Security and Health clusters, Protection and Shelter clusters, etc.)

- Short-term priority recommendations: 1-2 years

  - Vulnerability Mapping: Prepare inventories of urban areas where more/improved socio-economic data is a priority consideration, and select appropriate data-collection tools :

- household surveys

- IDP urban profiling, including refugee profiling in urban areas where these may be ‘hidden’;

- community mapping

- establishing or expanding ‘information drop-in’ centres

- desk review of existing information etc.

- Map Kibera digital mapping to do physical vulnerability mapping of urban areas.

- NB. The forthcoming ‘Urban Food Security and Nutritional Baseline’ conducted by the Kenya Food Security Steering Group (KFSSG) in Nairobi should yield useful vulnerability data which can be used as an entry point for a number of urban vulnerability-related programmes.

Who ? National/local government officials should lead the exercise with collaboration and technical support from HCT. Clusters involved could be: Protection (lead with government) shelter, food security, others interested in participating.

Issues to consider : organizing a community-based approach to design criteria that distinguishes between the chronically urban poor and other vulnerable groups in need of targeted assistance; ‘survey fatigue’ of already heavily-analysed populations; possibility of setting up distribution points with media or text-messaging to indicate their location (for situations were distribution of assistance is planned to take place); use of bio-metric identification measures for distributions.

  - Relocation/resettlement Master Plan: to identify those needing long-term resettlement from slum areas. This can be a relatively straight-forward and cost-effective exercise entailing enumeration by local community leaders, verified by independent sources,  and registering people on a waiting list for different options of housing. Bio-metric ID schemes could be tested at the same time to avoid ‘double dippers’.  NB. A master plan may already exist in Manila given (a) that official statistics state a housing backlog of 3.5 million prior to the storms, added to which 220,000 houses were damaged and destroyed in the disaster, and (b) Presidential creation of the Special National Public Reconstruction Commission to oversee implementation of the reconstruction programme.

  - Who? Relevant government department should lead the exercise with collaboration and technical support from different clusters, e. g. Shelter, CCCM, others interested in participating. Should be carried out with community participation - community leaders and CBOs – who may already have information prepared. Implementing such a scheme in Nairobi and Eldoret could include data collection on IDPs in a variation on the IDP urban profiling tool to capture a better understanding of how many people remain displaced, in what kind of situation (host family, rental, squatting, etc.) and other essential socio-economic data. This would provide an entry point to designing humanitarian, recovery and development programmes in addition to urban planning for residential areas.

  - Transitional Shelter Plan: concurrently, with previous point, to identify those needing short-term shelter solutions. While relocation represents one option for a long-term solution and conforms with urban planning regulations, an urgent solution is needed for the homeless waiting for the new housing to be built. In Nairobi and Eldoret many people who lost their homes in the PEV remain unable to return and no one knows exactly what happened to all of them.  It would therefore be necessary to precede this plan with (a) community consultations on where people are now, and (b) an updated IDP profiling exercise to ascertain the whereabouts of the newly displaced. The Philippines PDNA recommends that ‘people who have lost their homes must be urgently provided with short-term or transitional housing options near their sources of livelihood. Resettlement of urban dwellers in peri-urban (or rural) areas that does not take proximity to livelihoods into account has been less than successful worldwide’.  This mitigates in favour of a creative solution for transitional shelter within the same informal settlements where the homeless used to reside, as a temporary measure while waiting for a place in new housing schemes.

Who? Shelter Cluster with relevant government officials at national and local levels, discuss options for medium-term transitional shelter: host families, and support thereto, and/ or transitional shelter assistance to families to return to slum areas while waiting for longer term solutions.

Issues to consider: any plan to temporarily upgrade informal settlement homes to allow for the transitional shelter of former residents must be accompanied by a municipality-IDP written agreement that the latter will vacate the site once permanent housing becomes available. Transitional shelter solutions should not be an indirect means to shelve permanent housing plans and continue to allow people to live in hazardous areas, such that many informal settlements are. Shelter clusters implementing such a plan must carefully weigh the ethical pros and cons. On the other hand, all other options are worse.

  - Actor mapping:

Prepare summary of actors in a given location who may be useful contacts in times of emergency, with contact details and brief explanation of their main roles, for purposes of coordination in emergencies, eg:

- Key national, regional and local government officials

- Local NGOs, including Red Cross Societies

- CBOs

- Community leaders

- Private Sector companies

- Religious Groups

- Media groups

- Technical specialists (architects, engineers, planners, commercial suppliers etc.)

Who?  OCHA as lead agency, other IASC organizations or NGOs as designation in coordination discussions. Information should be stored, inter alia, on One Response site as well as relevant cluster sites.

Issues to consider : select disaster-prone locations as priority; note any previous activities these actors may have been particularly effective in; prepare to offer own-agency technical assistance and other collaborative schemes, based on gaps in previous experience.

  - Actor engagement: As follow up to actor mapping and for the purpose of coordination in emergencies, prepare action plan for engaging with the above local actors to establish contacts, share information on each others’ roles and activities, identify possible synergies to be explored for preparatory and /or DRR activities; sound out for possible partnerships or commercial agreements in emergencies; identify what disaster preparedness activities may be undertaken as a joint exercise; identify capacity needs and upgrading possibilities; explore possible partnerships for beneficiary monitoring and feedback; agree on regular update sessions.

Who? OCHA as lead agency, other organizations according to individual activities and priorities.

Issues to consider: Prior to engagement, define what own-agency might be able to offer in terms of technical assistance, capacity-building, preparedness projects etc. in order not to arrive ‘empty-handed’.

  - Land mapping :  With national or local government officials, advocate for joint exercise to plan and carry out identification of land that could be used as an evacuation or emergency shelter site. Having identified suitable sites, agree preparedness measures with relevant actors, eg. where emergency goods and stocks may be pre-positioned for rapid deployment in an emergency, design SOPs for activation of partnerships.

Who? Relevant government department should take the lead, assisted with technical expertise by interested clusters: Shelter, WASH, Health, Education.

Issues to consider: Requires planning experts and land developers, capacities likely to be available locally. External experts should only be brought in as a last resort. Donors such as JICA may have experts in the country for advice on earthquake resistance etc. having identified the land, agencies must have some capacity to contribute to minimum preparedness needs.

1.8. Standby capacities: Humanitarian agencies should revise their strategies to maintain a workable system of standby staff with experience in urban areas, ready for immediate deployment to urban emergencies. Regional multi-sectoral standby teams could be trained for urban emergencies, learning the specific urban complexities. These is especially necessary for the emergency shelter and WASH sectors. Ideally, staff should have prior experience in disaster-prone and conflict affected countries so they deploy with the requisite background and cultural knowledge, as well as technical.

Who? The IASC could draw up specific guidelines for rapid deployment for urban emergencies, including requisite technical as well as country-specific needs.  Humanitarian agencies can work with government partners to scale up their emergency capacity.

1.9. Preparedness measures for an urban disaster:  It is acknowledged that some of these tasks are already being prepared by HCTs in Nairobi and Manila, but they are elaborated here as a ‘checklist’ of action that needs to be taken on a more generic level.

- Contingency planning for conflict and disasters of different urban scales, with correspondingly scaled preparedness plans.

- Pre-positioning of some stocks (food, domestic items) but concomitant plans can be made with commercial companies, eg. Stand-by contracts with pre-negotiated clauses and operational procedures, to be activated if possible in an emergency.

- Standby rosters of government and agency staff need to be kept up-to-date and ensure their rapid deployment. This is a key area and also a key challenge, since it is difficult to retain qualified staff on a standby basis. It may be necessary to train additional staff in disaster response management with particular focus on responding in urban areas. The IASC may need to prepare a disaster-preparedness training strategy specifically for urban areas, drawing on the experience and tried and tested good practices of individual organizations. Specific training plans for sectors such as WASH and Shelter in urban areas are urgently needed – there are currently insufficient staff either within organizations or effectively rapidly deployable external sources with specialized knowledge. In anticipation, and given the hazard-prone nature of the Philippines, the HCT could usefully conduct its own research and discussion on this and share its experiences with the IASC.

1.10   Wash preparedness:

- In Manila humanitarian actors should advocate with LGUs to upgrade school toilet facilities to comply with minimum national standards for schools. This would go part-way to improving their situation. However, in times of emergency it is necessary for LGUs to have on hand, or organize standby procurement arrangements for additional ‘portoilets’ that can be deployed rapidly to ECs.

- In other urban areas ‘contextual’ responses need to be worked out for different sanitation arrangements according to the geo-physical nature of the land. Advocacy with municipal government officials should be stepped up to improve waste removal conditions in slum areas. The above UN-HABITAT and community-based solutions mentioned above can be developed for longer-term combinations of waste disposal and livelihoods.

- For large-scale disasters impacting heavily-populated areas (eg. Haiti), OXFAM advocates for better preparedness by aid agencies to cope with heavy demands for WASH facilities. These need to take into account adequate numbers of water bladders and desludging mechanisms, vital to prevent outbreaks of water-related diseases, and engineers with experience of working in urban areas. The WASH agencies are struggling to meet the population’s needs in Haiti mainly due to lack of desludging facilities and challenges in identifying the number of waste disposal landfills required.

- Medium-term priority recommendations – 1 to 3 years (some of the following activities can overlap with the short-term priority recommendations)

- Host family strategy for urban areas:   Opportunities exist to step up support to host families in emergencies. If these are well-supported they can alleviate pressures on ECs, which IDPs go to only in a last resort, given their well-known unhealthy and crowded conditions.  Only been timid attempts have been undertaken to address host family options (Goma and Bukavu) but past experience (Swiss CDC, Aceh) show that host families can provide long-term shelter and safe haven if provided with targeted support.

Who? Global Shelter Cluster: to elaborate a strategy. This could be done through consultations with government departments in selected countries where host families are already a fact on the ground. Implementation: relevant national and local government departments should take the lead in identifying host families with CBOs. Local Shelter Clusters and other clusters interested to assist with inputs in case government lacks resources and capacities.

Issues to consider: there are various models of support to host families, mainly cash-based. Would need to determine cash transfer modalities and ensure follow-up monitoring to ensure hosted families remain in situ and are not facing undue exploitation (eg. free labour, SGBV etc.). Host family support could take the pressure off over-crowded IDP camps such as ECs in urban areas. Given a modicum of support for taking in friends and relatives, this would provide a more humane solution for all concerned.

- Demographic statistics – health

Advocate with the GoK for statistical collection and analysis according to discrete slum areas in Kenya. The current methods do not allow for a full picture of health or other concerns in these areas, negating the possibility to respond effectively.

Who?  Health Cluster, WHO and other humanitarian agencies

Issues to consider: The GOK claims it is interested in getting a more representative breakdown of demographic statistics in the slums but implementation might prove problematic given the administrative complexities involved. Agencies can provide technical support and possibly financial support to relevant ministries for dedicated staff to work on this.

In Manila, the SPEED rollout and testing should improve health surveillance in urban areas and could serve as a model for other urban contexts.  Testing results should be shared with the Global Health Cluster for future use.

Midwives in the Philippines should be empowered to administer life-saving injections in emergencies and provisions in current health SOPs should be revised to encompass this. The excellent but under-utilized medical capacity in the Philippines should be more effectively utilized. Standby capacities should be maintained on DoH rosters for immediate activation in urban emergencies of an overwhelming character.

- Livelihoods strategies: Humanitarian agencies can do much to advocate with donors and governments for scaled-up livelihoods schemes as an integral part of the post-disaster recovery effort. IDPs in Eldoret said they would rehabilitate their destroyed shelters in the town themselves if they could get assistance with livelihoods recovery. This would be relatively simple, since they are already businessmen and would not need undue business training with matching micro-finance assistance. There is evidence in all the slum areas visited in Kenya that people take care of their own home upgrading if they improve their livelihoods security but there appear to be insufficient funds to engage in this in the Kenya recovery context.  In Manila, DSWD is engaged in livelihoods activities with support from WFP and other agencies in the early recovery cluster.

The Swiss NGO HEKS/EPER model of MSME rehabilitation in Aceh and Nias was successful in restoring businesses, opening up new ones and multiplying employment possibilities and could be replicated in all the case study cities. While it is a medium-term endeavour it should be started as soon as possible to allow people to recover and to build sustainable livelihoods.

Who?  Early Recovery cluster working with relevant government departments.

- Protection Strategies

- The UNHCR PPA tool in Manila, if implemented successfully in the pilot project, could be scaled up for use in other municipalities and other urban contexts.

- Information centres are useful ‘self-targeting’ support mechanisms for urban communities and could be replicated in more communities, with sufficient funding. They could be tapped as sources for information on urban vulnerability and IDP profiling.

- Agencies can advocate with government departments to have more community health workers, trained in dealing with victims of violence and detecting serious multi-sectoral problems for referral.

- Agencies, through community groups, could make greater use of information technologies such as text-messaging periodic information about community services, events, new legislation and human rights issues to refugees and IDPs in urban areas.

# Footnotes

A desk review of the urban challenges in Haiti is not included as of today, and will be incorporated in July 2010. Some elements however have been highlighted, where appropriate.

Threats to food security in urban areas are largely poverty, competition for resources and HIV/AIDS, according to WFP.

idem

Kenya Humanitarian Snapshot, May 2010, OCHA Kenya, 14.6.10, source: MoSSP

Urban Poverty and Vulnerability in Kenya, 2009, OXFAM GB Briefing Note

Fact Sheet – IDPs in Kenya, May 2010, UNHCR

Interview with Mr. Michael Musembei, Mitigation and Resettlement Department of the Ministry of State for Special Programmes MoSSP)

Kenya Humanitarian Snapshot, May 2010, OCHA Kenya, 14.6.10, source: MoSSP

IRIN, 19 March 2010. The article also states that: “The draft policy, unveiled in Nairobi on 17 March, broadens the definition to cover displacement due to political and resource-based conflict and natural disasters, as well as development projects that force people from their homes without proper relocation.”

The fifteen challenges identified in 2009  TF report and which further need prioritization are: (1) Identifying and collaborating with urban institutions, authorities and partners; (2) Inter-agency coordination in an urban context; (3) Identification and targeting beneficiaries; (4) Adjusting organizational tools, procedures and capacities to urban requirements; (5) Linkages between humanitarian response and risk reduction in urban areas; (6) Linking humanitarian assistance to recovery and sustainability; (7) Urban shelter challenges; (8) Housing, land and property (HLP) rights and issues in urban areas; (9) Protection challenges; (10) Gender Based Violence; (11) Violence and security; (12) Health risks in urban areas; (13) Food assistance, security and livelihoods; (14) Water, sanitation and hygiene; (15) Vulnerability to climate change impacts.

### Protracted displacement and remittances: the view from Eastleigh, Nairobi, Anna Lindley, 
Research Paper No. 143, PDES Working Papers, UNHCR, 1 August 2007, http://www.unhcr.org/46ea519d2.html

### Migrants' Remittances in Insecure Settings: The Somali case, doctoral research, Oxford University, 2003-2006

### http://www.compas.ox.ac.uk/research/dynamics/migrants-remittances-in-insecure-settings-the-somali-case/

Emergency Shelter Cluster (ESC) Typhoons Ketsana and Parma, Philippines 2009 - Initial Shelter Strategy, Timeframe:  October 15 – 31, 2009

http://sheltercluster-ph.googlegroups.com/web/Initial%20Shelter%20Strategy%20-%20Phil%20Typhoons%202009%201510.doc

Interview with Mr. Michael Musembei, Mitigation and Resettlement Department of the Ministry of State for Special Programmes MoSSP)

Between war and peace: humanitarian assistance in violent urban settings, Elena Lucchi Operational Advisor Urban Settings, Médecins Sans Frontières, Spain, published in Disasters, June 2010.

Interviews with IDP and urban community in Langas slum, Eldoret

UN-HABITAT, Nairobi Urban Sector Profile, 2006.

OXFAM evaluation paper, March 2010.

Interview with OXFAM, Geneva, June 2010

Galtung, Johan, 1969. 'Violence, Peace and Peace Research', Journal of Peace Research 6(3): 167–191.

UNHCR Fact Sheet: IDPs in Kenya, May 2010

For the case study sites

Typhoons Ondoy and Pepeng: Post-Disaster Needs Assessment (PDNA), October 2009

PDNA, p. xiii

Interview with OXFAM, Geneva, June 2010

# Text boxes

Case Study Cities

Manila:  Taguig, Pasig, and Pila (Laguna) municipalities, including a combination of local city officials, private sector actors, local NGOs and communities in informal settlements and relocation sites. A list of organizations and individuals interviewed in these cities is attached as an annex.

Nairobi: IASC organizations and other international NGOs, Mathere slum, meeting local NGOs and CBOs and community members, as well as government officials

Eldoret: Langas slum, meeting with community members, a local NGO (ECC), implementing partner of Save the Children, as well as city officials and international agencies/ NGOs at their offices.

Key Challenges for Humanitarian Cluster Responses

- Cluster Approach to Urban Areas: With humanitarian actors increasingly working in urban settings, the cluster strategies and responses on WASH, Shelter and protection etc need to be articulated for urban settings which will include models, strategy, partners, scenerios etc. Discussions with staff in the relevant organizations in Kenya and Nairobi and some initial discussions with operational staff deployed in Haiti show that many are struggling with adapting the technical rural models to urban areas especially in WASH sector. Developing such response models will help in translating elements for clusters into operational plans for urban areas, as learnt from Haiti. An important element linked to address this gap is to embracing non IASC partners within the clusters in urban areas to leverage capacities, experiences and resources.

- Urban density and space challenges: SPHERE standards cannot be met in urban areas because of the density of the population’s living conditions. Kibera slum in Nairobi is among the most densely populated places in the world, rating higher than even the world’s most densely-populated capital city - Malé, of the Maldives. People rarely enjoy SPHERE standards in terms of living space, availability of clean water, sanitation facilities, waste management or access to health care. Although access to these are basic human rights, country development aims, such as MDGs, have failed to keep up with their commitments. In the case of urban evacuation centres, such as Manila, SPHERE standards are also unable to be met in times of disaster due to severe over-crowding.

- Protection and violence issues in urban context need a strategy for actors to improve protection for urban areas.