Inter-Agency Standing Committee

Working Group Meeting

IASC Subsidiary Bodies

Core Group on Humanitarian Space
Work Plan for 2011

# Summary

Led by OCHA and NRC, the IASC Core Group on Humanitarian Space provides a forum for discussion of current challenges impacting the ability of humanitarian actors to operate in a safe and principled manner.

The Core Group's strategic goals are to ensure that IASC partners are provided with (i.) timely and in-depth analysis on priority challenges to humanitarian space; (ii.) advice and recommendations for measures to be taken by the IASC to address humanitarian space concerns; (iii) effective tools to support principled humanitarian action and decision making with regard to humanitarian space dilemmas.

During 2011, the Core Group is focusing on the following issues:

- UN integration and humanitarian space,

- counter-terrorism measures and the impact on humanitarian action,

- operating in complex security environments

The Core Group is also engaging in:

- review of a field manual on humanitarian access

- development of guidance and good practice on the reaffirmation of humanitarian principles

The  Humanitarian  Space  Core  Group  will incorporate in its analysis  relevant  aspects  of  the  work  of the IASC Integration Focal Point Group, the civil-military Relations Forum, and the Steering Group on Security, with an in-depth thematic discussion with IASC Working Group in 2011 leading to the endorsement of recommended options/approaches to address humanitarian space challenges.

# Work Plan for 2011

| Objectives | Activities | Focal point(s) | Timeframe | Status / Update |
| --- | --- | --- | --- | --- |
| UN Integration and Humanitarian Space | Collaborate in the ISG study on humanitarian space and integration Present findings and recommendations to IASC WG for endorsement and follow up Support roll out of the study and implementation of relevant recommendations | OCHA, in collaboration with UN Integration Steering Group and IASC Integration Focal Points | July 2011 July 2011 3rd and 4th quarter |  |
| Counter-terrorism measures and the impact on humanitarian action | Mapping of existing legal and policy frameworks and documenting of the implications for humanitarian actors Endorses proposed messages on counter-terrorism and humanitarian action and requests the Core Group to develop a sequenced IASC advocacy strategy, including: Interim note for the field on the current situation concerning counter terrorism legislation and policies and its implications for humanitarian operations. | OCHA and NRC | May-Nov 2011 |  |
| Operating in complex security environments and humanitarian space | Present findings and recommendations of “To Stay and Deliver” to IASC WG for endorsement and follow up Support roll out of the study and implementation of relevant recommendations | Core Group |  |  |
| Reaffirmation of humanitarian principles | Review of Field Manual on Humanitarian Access Guidance and good practice on Codes of Conduct, Minimum Standards, Groundrules, etc. analyse and disseminate good practices | Core Group OCHA with Core Group | 4th quarter 3rd quarter | Draft disseminated to Core Group, currently under revision Preliminary compilation presented to Core Group, currently compilation under finalisation |
| Support ad hoc initiatives in support of humanitarian space issues | Support to HPG/ODI project on Dilemmas and Principles of Humanitarian Action | UNICEF | TBC |  |

III  Key Expected Outcomes 2011

- IASC follow up to findings and recommendations of study on Integration and Humanitarian Space, including agreed common messages.

- IASC follow-up to findings and recommendations of study “To Stay and Deliver” on operating in complex security environments.

- Study on counter-terrorism measures and implications for humanitarian actors.

- IASC agreed common messages on counter-terrorism measures and humanitarian action.

- IASC endorsement of Field Manual on Humanitarian Access.

- Analysis and dissemination of good practices on codes of conduct, minimum standards, groundrules, etc.

# Work Plan for 2010

| Objectives | Activities | Focal point(s) | Timeframe | Status / Update |
| --- | --- | --- | --- | --- |
| Reaffirmation of humanitarian principles | Support the organization of learning events on Humanitarian Principles Elaborate minimum standards/good practices on Codes of Conduct Develop guidance, including for UN Mission personnel, to ensure a clear understanding of humanitarian principles and mandates Support the development of guidelines on the exchange of information (conflict and situation analyses, needs assessments, and protection of civilians’ issues, etc.) between missions and humanitarian actors |  |  |  |
| Promote learning on humanitarian actors engagement with criminal tribunals | Organise an initial informal consultation among Core Group members on practices of interaction with Criminal Tribunals. The consultation would also aim to determine what the ultimate objective of Core Group work on this issue should be. |  |  |  |
| Promote efforts to address humanitarian space challenges posed by UN integration | Collaborate on scoping exercise aimed at assessing positive/negative impacts of integration on humanitarian space issues Collaborate in development of an analysis framework to guide decision making on structural integration arrangements |  |  |  |
| Support ad hoc initiatives in support of humanitarian space issues | Support to HPG/ODI project on Dilemmas and Principles of Humanitarian Action Support country specific initiatives (e.g. Chad roundtable) |  |  |  |
| Develop IASC endorsed options/approaches to address humanitarian space challenges | Organise IASC-WG Discussion in December 2010 Develop proposal options/approaches to address humanitarian space challenges to submit to the March 2011 IASC Organise an exchange of lessons learned on operating methods in insecure/complex environments |  |  |  |