Inter-Agency Standing Committee

Working Group Meeting

IASC Subsidiary Bodies

Task Force on HIV in Humanitarian Situations
2009 Work Plan

Finalised: 30 March 2009

# Narrative Summary

Following the endorsement of the 67th meeting of the IASC Working Group (WG), the IASC Task Force on HIV was reconvened in March 2007 for a period of two and half years with the following objectives:

- Assess the state of implementation of 2005 IASC Guidelines for HIV/AIDS Interventions in Emergency Settings and integration of HIV into emergency settings – field level outputs

- Revise the IASC Guidelines on HIV/AIDS Interventions in Emergency Settings including the elaboration of new modules

- Update the IASC training materials and develop new ones as needed (and designate institutional home for these materials)

- Strengthen and harmonize of monitoring and evaluation of IASC tools, including indicators, on HIV interventions in emergency contexts.

In 2008, most of the work focussed on assessing the implementation of the current Guidelines and on their revision. An advanced draft of the revised Guidelines is now ready. In late 2008 and in 2009, the Guidelines will be finalized and made available in key languages, and a roll out strategy for their systematic dissemination will be developed with emphasis on integrating HIV into cluster/sector work. An advocacy brief for senior managers will be developed as will be a standard training package. Various other tools to facilitate the integration of HIV into humanitarian responses drafted in 2008 will be finalized and harmonized with the Guidelines, and specific efforts made to strengthen the integration of HIV into emergency preparedness.

# Work Plan for 2009

| Objectives | Activities | Focal point(s) | Timeframe | Status / Update |
| --- | --- | --- | --- | --- |
| Finalize, disseminate and roll-out the revised Guidelines for Addressing HIV in Humanitarian Situations | Finalize and print the Guidelines and make them available in print in key languages and in electronic format. Develop a standard resource/training package including the Guidelines, an advocacy brief for senior managers, and an induction package for humanitarian workers. Develop and implement a roll out plan for the systematic training on the Guidelines at regional and country levels including by: Training clusters/sectors Making use/combining HIV training with other IASC trainings Conducting training within individual UN agencies Training NGO staff Maintain inventory of the trainings | Task Force members, UNAIDS Secretariat UNHCR, WHO, UNICEF, UNAIDS Secretariat, Task Force members UNHCR, WHO, UNAIDS Secretariat, Tearfund UNAIDS Secretariat, | First/second quarters First/second quarters First/second quarters ongoing |  |
| Finalize/update various other tools to facilitate the integration of HIV into humanitarian responses | Circulate and finalize the CAP diagnostic tools in harmonization with the Guidelines Finalize compilation of needs assessment tools Finalize guidance on CERF funding | WHO, UNHCR, UNICEF, UNAIDS Secretariat UNAIDS Secretariat, Task Force members OCHA, UNAIDS Secretariat, Task Force members | First/second quarters |  |
| 3. Support regions and countries to integrate integration of HIV into humanitarian action | Decide on and use successor arrangement for IASC Task Force (such as informal network or reference group) if any Maintain AIDS in emergencies website | IASC Working Group, Task Force members, NGOs UNAIDS Secretariat, TF members | mid-2009 Ongoing |  |
| 4. Strengthen HIV integration into emergency preparedness | Finalize guidance for HIV integration into emergency preparedness in harmonization with the IASC Guidelines on Addressing HIV in Humanitarian Settings Integrate HIV into regional and country emergency preparedness trainings and planning processes | WFP, UNAIDS Secretariat , TF members Task Force members | First/second/third quarters Second/third quarters |  |