IASC Task Force on Meeting Humanitarian Challenges in Urban Areas

Tentative Work Plan Nairobi & Manila

|  | General Workplan | Duration Days | March | April | May | June |
| --- | --- | --- | --- | --- | --- | --- |
|  | ISO Week Number |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 21 | 22 | 23 | 24 |
| Preparation Phase | Identification of national consultants; collection of and familiarisation with agency tools in both countries; national consultants arrange meetings with stakeholders; | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Identify data collection and analysis methods, prepare programme and logistics for travel | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Field Phase | Travel to Nairobi | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Introductory meeting with IASC members | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Visiting stakeholders and sites | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Workshop | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Clarifications/follow-up with stakeholders | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Travel to Manila | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Introductory meeting with IASC members | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Visiting stakeholders and sites | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Workshop | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Clarifications/follow-up with stakeholders | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Travel back to Europe | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analysis | Write up of draft report | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Finalisation | Incorporation of TF inputs, finalisation of synthesis report | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Incorporation of findings into MHCUA Strategic Framework. | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Total Working Days | 61 |