Inter-Agency Standing Committee

Working Group Meeting

IASC Subsidiary Bodies

IASC Task Force on Information Management 
Work Plan for 2010

# Narrative Summary

Introduction

To address deficiencies in managing information in emergencies that were identified by humanitarian partners in early 2006, OCHA and the IASC membership were requested by the IASC-WG at its 65th meeting to implement ten recommendations to address the identified weaknesses.  By December 2007 all ten recommendations were substantively implemented by the members of the IASC through the IA IM WG.  One of the most important outputs of the IA IM WG was the development of an inter-agency agreement on the responsibilities of Cluster/Sector leads and OCHA in managing information emergencies: the Operational Guidance on Responsibilities of Cluster/Sector Leads & OCHA in Information Management (hereafter referred to as Operational Guidance on IM). This Operational Guidance was endorsed by the IASC Task Team on the Cluster Approach in 2007 and by the IASC Working Group in 2008.

At the 71st IASC WG meeting in June 2008, OCHA provided an overview of progress made in 2006-2008 by the IA IM WG, presented the Operational Guidance on IM, and recommended that an IASC Task Force on Information Management (IASC TF on IM) be established to strengthen inter-agency information exchange before and during emergencies.  After clarifying the main focus of the group through a concept note, the IASC WG endorsed the establishment of the IASC TF on IM as of 1 January 2009 for an 18 month period.  Throughout 2009, progress against the overall objectives has been made and the Task Force is likely to achieve its main activities as outlined below.

Objectives

The objective of the Task Force is to strengthen the management of information in humanitarian emergencies by building on and improving existing inter-agency processes and tools for the collection, processing and dissemination of information to support improved decision making in emergencies.

Main Activities

In order to provide the members of the IASC, including global and field Cluster/Sector leads, with improved information management guidance and tools, the primary activities of the IASC TF on IM are to:

# Review of current Inter-Agency IM and implementation of the Operational Guidance Note on IM to identify best practices;

# Update the Operational Guidance Note on IM (based on the Inter-Agency review);

# Produce agreed guidance and tools to implement the revised Operational Guidance on IM; and

# Develop a framework for monitoring the effectiveness of the Operational Guidance Note on IM.

# Work Plan for 2010

[See attached]

III  Key Expected Outcomes 2010

The IASC Task Force on Information Management (IASC TF on IM) will have the following expected outcomes in 2010:

- Update of the Operational Guidance on Responsibilities of Cluster/Sector Leads & OCHA in Information Management.

- Roll-out of the inter-agency web platform – provisionally called OneResponse - to support and manage the exchange of operational information in emergencies.

- Cluster/Sector IM distance learning course developed for national, international and external personnel involved in strategic, operational, technical, or managerial side of collecting, analyzing and using data.  This will allow for a common standard, understanding and expertise of how IM supports humanitarian response.

- Guidance on “Common Operational Datasets (COD)” for use in humanitarian emergencies.

- Framework for monitoring effectiveness of the Operational Guidance Note on IM.

Deadline of the Report for 2009 and draft Work Plan 2010 to be received by the IASC Secretariat: 11 December 2009 (addressed to silva12@un.org  )

# Work Plan for 2010

| Objectives | Activities | Focal point(s) | Timeframe | Status / Update |
| --- | --- | --- | --- | --- |
| Needs assessments efforts are supported from an IM perspective | Clarify linkage between IM and Needs Assessments (NA) Provide IM guidance and recommendations to the IASC Task Force on Needs Assessments | WASH (UNICEF) and HEALTH (WHO) | In line with IASC Task Force on Needs Assessments work plan for 2010 | On-going support to the IASC Task Force on Needs Assessments |
| Review of current Inter-Agency IM and implementation of the Operational Guidance Note | Undertake review Produce a review report with recommendations | OCHA, PROTECTION (UNHCR), WASH (UNICEF) | Before end of 1st quarter 2010 Before 2nd quarter 2010 | Consultant identified and Review underway |
| Update the Operational Guidance Note on IM | Post review, update the Guidance Note to reflect best practices | Entire Task Force | Before end of 2nd quarter 2010 | Awaiting results from the review |
| Produce agreed guidance and tools to implement the revised Operational Guidance on IM | Develop online “toolkit” for field practitioners on implementation of the Operational Guidance Note on IM Develop inter-agency web-platform to support and manage the exchange of operational information in emergencies Design and deliver inter-cluster information management training to Cluster/Sector members to allow for a common standard of understanding and expertise Update or create new information management solutions to meet unforeseen gaps arising from the review Define the minimum set of data and information that will be consistently shared between Cluster/Sectors and OCHA in emergencies Provide guidance on IM linkages to early recovery and transition. | To be determined OCHA OCHA, PROTECTION (UNHCR), HEALTH (WHO), ES (IFRC) CCCM (IOM) and WASH (UNICEF) As appropriate PROTECTION (UNHCR), HEALTH (WHO), ER (UNDP), LOGISTICS (WFP), as well as participation from USAID, UNOSAT and UNOSA OCHA, ER (UNDP) | By end of 18 months Evaluation based upon pilots before end 1st quarter 2010 By end 2nd quarter 2010 As appropriate By end of 18 months By end of 18 months | An inventory of available toolkits will be conducted 1st quarter 2009 Pilots are being undertaken Chapters of the distance learning identified and being formed. Delivery to UNITAR by end 1st quarter 2010 Policy paper being formed with a completion date before end 2nd quarter 2010 To form a part of the Review of current Inter-Agency IM and implementation of the Operational Guidance Note |
| Framework developed for monitoring effectiveness of the Operational Guidance Note on IM | a) Develop a monitoring framework, including standard indicators, to supporting monitoring of the effectiveness of the Operational Guidance Note on IM | To be determined | By end of 18 months | The sustainability of Inter-Agency policy for Information Management will be elaborated and presented to the IASC WG as part of the final report of the IASC TF on IM |

# Footnotes

In June 2006, at the request of the IASC-WG, OCHA hosted an Information Management Workshop in Geneva where 29 representatives from the IASC participated (FAO, ICVA, IFRC, IOM, OCHA, UNDP, UNFPA, UNHCR, UNICEF, UNJLC, WFP, WHO, VVAF,  and World Vision International) and came to this agreement on the role of humanitarian information management

See Background Note, Implementation of Inter-Agency Framework for Information Management in Emergencies, presented at the 71st meeting of the IASC-WG.