## Sheet1
TARGET DATES OF MID-YEAR REVIEWS OF CONSOLIDATED APPEALS 2008
Who Does What and by When?
(NB References to "OCHA" means the main OCHA Office in country)
Before Friday | [Hidden: number of days from last step] | 2008-05-23 |  | [Hidden: number of days of duration of this step] |  | CAP consultations have taken place:
(a) Sector working groups have reviewed sectoral objectives and updated as needed; have reviewed each project in the CAP and added, modified, or deleted as appropriate, and have reviewed official FTS funding tables1 and communicated any corrections to fts@reliefweb.int, including use of loosely earmarked funds; compiled reports on outputs, and impact assessment if available, and summarised for MYR;
(b) Country Team (including UN agencies, Red Cross and Red Crescent Movement, and NGOs), in consultation with the relevant authorities and donors, has reviewed and updated needs analysis, strategic priorities, objectives, and changes in key monitoring indicators; has agreed on general boundaries of humanitarian action for remainder of 2008 and for 2009; has agreed with donors a plan for needs assessment and analysis for the 2009 CAP, including who will do it, how much it will cost, and who will pay for it.
Fri-Tues |  | 2008-05-23 | till | 4 | 2008-05-27 | Sector working groups draft sector inputs, while OCHA field office drafts rest of document.
COB, Tue |  | 2008-05-27 |  |  |  | Deadline for sector working groups to submit sector inputs to OCHA field office.
Wed-Thu |  | 2008-05-28 | till | 1 | 2008-05-29 | OCHA field office compiles draft of Mid-Year Review (MYR).
OOB, Fri |  | 2008-05-30 |  |  |  | Humanitarian Coordinator distributes draft to agencies, Red Cross Movement, and NGOs in country. These have three full working days to read the draft and consult their headquarters to discuss the draft.
COB, Mon |  | 2008-06-02 |  |  |  | Deadline for agency etc. field offices to send comments on draft to OCHA field office.
Tue-Wed |  | 2008-06-03 | till | 1 | 2008-06-04 | OCHA field office incorporates comments in consultation with agencies and sends new draft to the Humanitarian Coordinator.
COB, Thu |  | 2008-06-05 |  |  |  | HC clears final field draft and sends it to OCHA’s CAP Section. (NOTE: If the HC must be absent on this date, s/he must empower the deputy or OIC to approve and send the document, on time.)
Fri |  | 2008-06-06 |  |  |  | CAP Section (Geneva) pre-formats all Mid-Year Reviews (MYRs).
OOB, Mon |  | 2008-06-09 |  |  |  | CAP Section circulates final field drafts to agency HQs, which have three working days to return comments on the documents.
COB Wed |  | 2008-06-11 |  |  |  | Final comments from headquarters due. CAP Section starts drafting chapeau doc.
Thurs |  | 2008-06-12 | till | 1 | 2008-06-13 | OCHA-HQ Desk Officer responsible for MYR incorporates and reconciles HQs comments.
Mon-Wed |  | 2008-06-14 | till | 11 | 2008-06-25 | CAP Section style-checks, uploads changes onto FTS, and formats MYRs.
Mon |  | 2008-06-23 |  |  |  | CAP Section finishes draft of chapeau doc and circulates to CAP SWG for review (due in 3 days).
Thurs |  | 2008-06-26 |  |  |  | MYR documents finished and sent to print (on rolling basis, with last going on this date).
Thurs |  | 2008-06-26 |  |  |  | Donors receive e-mail notification that MYRs are available electronically.
Thurs |  | 2008-06-26 |  |  |  | Humanitarian Appeal Web site post MYRs with note "Embargoed to the Media until launch". Deadline for SWG review of chapeau doc.
Mon |  | 2008-06-30 |  |  |  | CAP Section finishes chapeau.
Tues |  | 2008-07-01 |  |  |  | CAP Section and UNOG Print Shop format chapeau.
Fri |  | 2008-07-04 |  |  |  | Printshop finishes printing chapeau; chapeau put on line, and donors notified.
Mon |  | 2008-07-07 |  |  |  | Distribution of MYR; ship MYRs & chapeau to NY
Tues-Thurs |  | 2008-07-15 | till |  | 2008-07-17 | Launch of the MYR in New York en marge of the Humanitarian Segment of the ECOSOC.
1 |  | The most detailed table, and hence best for spotting corrections, is Table E, “List of Appeal Projects (grouped by sector), with funding status of each.” This is accessible on your FTS CAP page, for example: http://ocha.unog.ch/fts2/pageloader.aspx?page=emerg-emergencyDetails&emergID=15190.