IASC-UNDG Task Force Meeting

South Asia EQ

Draft Summary

28 September 2006

Co-chaired by Merete Johansson, Chief Asia and Pacific Section, OCHA Geneva

and Mr. Bradley Forster, UNDGO

Participants:

Participants in NY represented OCHA, UNDGO, UNDP, IOM, UNICEF and UNDSS. The GVA participants represented UNDP/BCPR, UNICEF, UNHCR, OPS, IOM, WHO, UNEP. Participants in Islamabad are from UNRC/HC Office and UNDP.  FAO Rome also attended.

- Update on the implementation of the ‘ERRA/UN Early Recovery Plan’ (ERP)

- ERRA demonstrates greater stakeholder awareness by requesting donors to provide additional resources

- Sector working group at local and regional levels are functioning well

- Development of IASC working group helps to flag critical issues and highlight gaps

- Creation of a disaster risk reduction unit is discussed in parallel to the national disaster management authority

- ERRA Annual report will be presented next Friday, including a part on early recovery

- WATSAN, Housing and Protection need more funds

- There are needs for wheat seeds. Procurements are ongoing. FAO will provide an update.

2) Contingency planning and preparation for next winter

- The CP is fully developed and is waiting for formal endorsement of the Government

- Emergency shelter working group is conducting an assessment that will be completed by 5 October with focus on rural areas

- A comprehensive health assessment will be ready for discussion next week by the IASC and the working group

- Relief and camp management show needs in WATSAN. The MoU between NRC and UNHCR is pending approval for the deployment of staff

- CP focal points are going to be set up, including NGOs

- Locally available funding resources are to be mapped and best use identified

- As part of the UN reform, the RC proposed the creation of a risk reduction group chaired by UNDP in relation with the national disaster commission

- A joint programme for risk reduction would involve collaboration between the national risk reduction advisor (UNDP) and the national disaster reponse advisor (OCHA)

- Support is expected by the IASC TF to mobilize resources once the CP has been endorsed by the Government

- The Quartely report will be ready next week and shared with HQs

3) Activities planned for the first year commemoration

- Briefing by the RC Office. A matrix of events happening in Pakistan will be shared

- Joint OCHA-UNDP press brief will take place on Friday 6 October in Gva. Strong and clear key messages for international media are needed.

- An event will be organised in NY under the lead of UNDP (Hafiz Pasha) on the 6th October. TPs will be provided for JE, Special Envoy and UNDP Administrator

- Donor event in NY is pending confirmation of presence of a high-level Pakistan official

4) Floods

- A field assessment has been undertaken, report ready tomorrow

- Request for short-term assistance will be issued to cover needs that have not been met by the Government

- Main issues are: WATSAN and decontamination of wells

5) Joint UNDP-UNDGO mission

- Positive feedback about joint mission by Kathleen Cravero of BCPR and Sally Fegan-Wyles of UNDGO

- The mission briefed the UNCT on UN reforms and advocated for more attention and resources for the health sector and the ERP on the press conference

6) AOB

In principle, the next IASC-UNDG TF MEETING will take place on Wednesday, 18 October at 09:00 NYT, 15:00 GVA time, 18:00 ISL time.