Inter-Agency Standing Committee

IASC Subsidiary Bodies

Sub-Working Group on Preparedness and Contingency Planning

2008 Progress Report

Endorsed: 30 March 2009

# Status Update on Activities Undertaken in 2008 with Reference to Objectives Set in the 2008 Work Plan

| Objectives | Activities | Focal Point(s) | Timeframe | Status of Completion by the end of 2008 |
| --- | --- | --- | --- | --- |
| Inter-Agency Collaboration | Maintain and enhance the SWG as an active inter-agency forum on matters related to early warning, preparedness and contingency planning; increase inter-agency dialogue, information sharing, collaborative efforts. | SWG | - SWG mtgs - Monthly conf calls; 1st Thurs - On-going dialogue: actions as useful | Completed : Organisation of 3 SWG meetings (February, May, October), with sustained dialogue, information sharing and collaboration on projects (c.f. 2., 3., 4. 5. below) |
|  | Enhance collaboration with other working groups (e.g. clusters, Framework Team, other SWGs, ISDR) | Co-chairs | On-going | Completed by sharing of information and views with partners during serious crises in 2008, monthly conference calls, inviting partners and other working groups to SWG meetings to present and discuss initiatives (CADRI, ISDR, others). |
| Normative Guidance | Develop tools to support the revised Inter-agency Contingency Planning Guidelines, including inter-agency simulation. | SWG | On-going | Completed IACP Training/ simulation modules developed and finalised. |
|  | Work with clusters to assess and support development of cross-cutting early warning, preparedness and contingency planning tools/processes | SWG | On-going | Not completed |
|  | Consider and operationalize recommendations from the inter-agency contingency planners consultation(e.g. inter-agency roster/surge capacity for contingency planners; inter-agency simulation package) | SWG | On-going | Partially completed, with the development of the training and simulation package. |
| Early Warning/ Early Action | Continue global reviews and assembly of the IASC Early Warning – Early Action report | SWG | March, June, September | Completed, with the development and submission to the IASC of 3 IASC EWEA reports (March, June, November). |
|  | Support and enhance HEWSweb | SWG | On-going | Completed, with the finalisation of a methodology review, discussions and partnership with JRC, and development of a mock-up system for testing at inter-agency level. |
|  | Support linkages and enhancement of early warning systems of IASC member agencies | SWG | On-going | Partially completed, with enhanced web linkages between agencies systems, and information sharing / discussions on EW methodologies. |
|  | Organize a 3rd inter-agency consultation on early warning to enhance agency and inter-agency systems developments. | Co-chairs | 2nd quarter | Not completed Will be undertaken in 2009 |
| Agency Capacities | Share/compare S.O.P.s, and other materials to enhance agency capacities re preparedness and early warning | Co-chairs | On-going | Not completed |
| Regional preparedness/ Contingency Planning | Work with regional emergency officers/teams to harmonize practice, standards, profile, capacities, structures | SWG members | On-going | Work in progress To be completed in 2009 |
|  | Pilot 2-3 inter-agency contingency planning processes in regional or sub-regional hubs (e.g., Central Asia, Central America, South Asia, Pacific, etc.) | Co-chairs | On-going | Completed Two inter-agency contingency planning missions where undertaken in 2008, in Nepal and in DRC. |