Inter-Agency Standing Committee

Working Group Meeting

IASC Subsidiary Bodies

IASC SWG on Preparedness and Contingency Planning 2009 Work Plan (revised 25 Feb 2009)

Endorsed: 30 March 2009

# Work Plan for 2009

[Please use the template below. This matrix should be used for reporting at the end of 2009.]

Deadline of the Report for 2008 and draft Work Plan 2009 to be received by the IASC Secretariat: 13 October 2008 (addressed to silva12@un.org  and  yoshiday@un.org   )

# Work Plan for 2009

| Objectives | Activities | Focal point(s) | Timeframe | Status / Update |
| --- | --- | --- | --- | --- |
| Inter-Agency Collaboration | Maintain and enhance the SWG as an active inter-agency forum on matters related to early warning, preparedness and contingency planning; increase inter-agency dialogue, information sharing, collaborative efforts. | SWG | - SWG quarterly meetings - On-going dialogue, regular conf calls: actions as useful | Retreat planned for June 2009 to review progress and enhance collaboration. |
|  | Enhance collaboration with other working groups (e.g. Clusters, Framework Team, other SWGs, ISDR) | SWG | On-going | Feed EWEA Report into Framework Team; Retreat to consider external collaboration. OCHA as Focal Point to push for inclusion of SWG work on RC/HC and HCT training agendas. IASC to organise discussions with their subsidiary bodies to avoid overlap and ensure synergies. |
| Normative Guidance | Roll out the inter-agency CP Guidelines and training tools and pilot IACP training/simulation in at least 2 countries pilot countries. | SWG | Q1 2009 | To be followed up: UNICEF as Focal Point (suggest 2 from SWG, 2 from Regional Hubs). Tool box is on-line, actively being used. |
| Early Warning | Sustain the production of the tri-annual IASC EWEA report | SWG | February, June, October | First Report of 2009 in production. |
|  | Test and pilot the HEWS web phase II | SWG | On-going | In progress. |
|  | Support linkages and enhancement of early warning systems of IASC member agencies | SWG | On-going | Agreed to share alerts, information on a regular basis. |
| Support to HFA priority 5 (Preparedness) | Contribute/support at the agency level by providing inputs to the 2008-2009 HFA Report and Global Platform meeting. | SWG | Q2- Q3 2009 | Actively contributing to the Global Platform, June 2009. |
|  | Support agency level promotion of guidance package on implementing HFA Priority 5 | SWG | Agreed. | To be discussed at SWG Retreat, June 2009. |
| Regional preparedness/ Contingency Planning | Produce and circulate a concept/guidance paper on strategies to strengthen inter-agency CP and Preparedness capacities at regional level. | SWG | On-going | Work in progress on identification of best practices at regional level. Focal Point: OCHA. |
|  | Work with regional emergency officers/teams to harmonize practice, standards, profile, capacities, and structures. | SWG | On-going | Capacity building on-going at an agency level. |
|  | As required, respond to genuine requests for 2-3 inter-agency contingency planning processes in regional or sub-regional hubs (e.g., Central Asia, Central America, South Asia, Pacific, etc.) | SWG | Q 2009 | Agencies in readiness to respond; SWG member is supporting the Inter-Agency Contingency Planning exercise in Montenegro, scheduled for March 2009. |