Inter-Agency Standing Committee

Working Group Meeting

IASC Subsidiary Bodies

Report on the Mental Health and Psychosocial Support Reference Group Activities in 2009

# Activities Undertaken in 2009

## Achievements in line with the 2009 Work Plans endorsed by the IASC.

Throughout 2009 roll-out of the guidelines has focused on 1/ interface with the relevant clusters 2/ consolidation and development of tools 3/ development of training materials and 4/ supporting country initiatives. In addition to those outlined in the matrix, activities undertaken in 2009 have included:

- Integration of MHPSS into Sphere and INEE revisions

- Development of key documents with the Health and Protection Cluster

- Development of a document on how to work on institutionalisation

- Organization of sustainable dissemination of the IASC Guidelines on MHPSS

- Printing of a field version of the IASC Guidelines on MHPSS

- War Trauma Foundation has joined the RG

- Country implementation in Opt, Jordan, Philippines, Peru, Jordan, Iran and Nepal

## Opportunities and constraints faced by the TFs / SWGs

Following the launch of the Guidelines in 2007 the subsequent year was filled with much field activity. This year has been more focused on consolidating these activities and developing tools to assist field implementation. In addition, the opportunity of having a part-time person based in Geneva has allowed the mainstreaming of Mental Health and Psychosocial Support into other domains such as Health, and Protection, and engagement with the Education and Nutrition Clusters, as this is an important principle of the Guidelines.

An expected output of this year was the development of four Regional Trainings. Due to constraints in resources and time, as RG members will do this work in addition to their normal work, these training have not yet taken place. Unicef, World Vision and MdM have committed to taking the lead in 2010 on two regional trainings (Middle East and Latin America) and we hope that at least one other organization will take the lead in a third region. Unicef and World Vision International will be funding the development of the training materials.

# Status Update with Reference to Objectives Set in the 2009 Work Plan

| Objectives | Activities | Focal point(s) | Timeframe | Status / Update |
| --- | --- | --- | --- | --- |
| To disseminate the Guidelines to key stakeholders and institutionalise them | 1.a. Continued printing and dissemination of the Guidelines 1.b. Provide feedback and support to key documents (e.g. SPHERE) 1.c. Develop a checklist for institutionalisation 1.d. Continued institutionalisation of the guidelines within RG organisations, sharing of tools and collaboration on joint initiatives (where relevant) 1.e. Reach out to professional organizations not represented in the RG 1.f. Raise awareness with media stakeholders (e.g. dissemination, workshops etc) 1.g. Raise awareness with key donors (e.g. ECHO) | Co-Chairs Co-Chairs and RG Co-Chairs RG Co-Chairs and RG Action-Aid, GPSI Co-Chairs and RG | Ongoing Ongoing Feb-April Ongoing Jan - March April – June Oct - Dec | Completed Completed Completed Completed Completed Planned for 2010 Completed |
| To interface systematically with the Cluster system. | 2.a. Finalize Guidance Note, Health and Protection Coordinators tool 2.b. Finalize Coordination Toolkit and disseminate in existing and new emergencies 2.c. Mainstream MHPSS into Health Cluster 2.d. Mainstream MHPSS into Protection Cluster / Child Protection Working Group 2.e. Mainstream MHPSS into Education Cluster 2.f. Mainstream MHPSS into Nutrition Cluster 2.g. Support the inclusion of MHPSS in Flash and CAP appeals including funding for use of the IASC MHPSS Guidelines and coordination in large scale emergencies | Co-Chairs, WHO Co-Chairs WHO UNICEF, CCF INEE IMC/ACF Co-Chairs | Jan-Feb Feb – May Ongoing Ongoing Ongoing Ongoing Ongoing Ongoing | Completed In progress In progress In progress In progress Agreement to begin in 2010 Agreement to begin in 2010 Completed |
| To support Regional, Country and Community level activities in different countries. | 3.a. Develop 2 page document “guidance on conducting case studies” 3.b Support new and ongoing country implementation through identifying regional and national champions, provision of financial and technical assistance and facilitating exchange among countries through online platform (psychosocialnetwork.net) 3.c. Find, translate and collate “regional materials” 3.d. Organize 4 regional meetings (see point 4.d.) 3e. Document implementation of the guidelines at country level | Co-Chairs, MdM RG RG Co-Chairs, MdM, GPSI, Co-Chairs | July Ongoing July-Sept March – Sept May-Sept | Completed Completed Completed 2 Planned for 2010 Completed |
| To build capacity on the Guidelines | 4.a. Compile existing resources and post on www.psychosocialnetwork.net 4.b. Develop a peer group to review materials that are IASC certified 4.c. Develop 8 orientation workshops for different audiences 4.d. Develop training kit and use at 4 regional meetings 4.e. Implement and coordinate trainings and orientations at country and global level | GPSI WHO/IMC/SAVE GPSI GPSI/RG Co-Chairs and RG | Jan Aug-Sept Jan-Feb Feb-March Ongoing | Completed Planned for 2010 Completed Completed Completed |