## Slide 1
IASC Task Team on Accountability to Affected Populations and Protection from sexual Exploitation and Abuse (AAP/PSEA)
TASK Team Meeting
13th of April 2015
Update on the workplan:
What have we achieved ?
What remains to be done?
What are the challenges/ opportunities ?

## Slide 2
Objective 1.1
Language Merger
Establishing a common language for AAP and PSEA among organizations
A paper summarizing what is AAP and what is PSEA has been written and disseminated to Task Team member.
Done to date?
Still to be done?
Work Stream 1
AAP/PSEA Advocacy
Lead
Contact: Rebecca Skovbye
Feedback needed on how it has been used to date
Prepare additional key messages to highlight the linkages between AAP and PSEA during the Senior Focal Point meeting on PSEA 16 April 2015
Include the paper in the Helpdesk resources. Members to disseminate the paper when they are doing AAP and/or PSEA related field missions.
Ensure the paper is used as a resource in training related to AAP and/or PSEA

## Slide 3
Objective 1.2
World Humanitarian Summit
1.Ensure inclusion of AAP and PSEA in WHS processes and consultations.
2.Support WHS Secretariat on accountability and PSEA issues and its community engagement efforts during regional consultations in 2015.
3.Activate TT members at regional level for greater engagement in WHS.
AAP and PSEA in the World Humanitarian Summit
Done to date?
AAP emerging as a priority in the WHS consultations
Contact with WHS secretariat to discuss how to prioritise AAP/PSEA has been established.
AAP has been incorporated in the work to date : paper on CAAP has been sent to the WHS secretariat
WFP is a member of the effectiveness team of the summit secretariat , and pushing for AAP
Still to be done?
Work Stream 1
AAP/PSEA Advocacy
Lead
Contact: Rebecca Skovbye
While accountability is coming out strongly from the regional consultation, we need to ensure it is correctly reflected.
Comment on Alice paper
ALNAP Global Forum for Improving Humanitarian Action on 4/5th NY : who is attending ?
AAP needs to be featured in both the WHS June synthesis report and the October 2015 Geneva final report

## Slide 4
Objective 2.1
Support to AAP and PSEA field operations
Field missions and in-country support+ feedback and lessons learning
Somalia : Rapid Accountability Assessment with Building Resilient communities consortium ( BRICS) and identification of areas of improvement + development of work plan
East Africa : Launch of the Core Humanitarian standard in collaboration with the Inter Agency Working Group and plan for dissemination to move from theory to practical implementation
Planned
Work Stream 2
Operationalizing AAP/PSEA in country-level activities and provision of technical support
Lead
Contact: Massimo Nicoletti Altimari
Somalia : Collaboration with BRICS agreed till 2016.
Lebanon 28th of April : workshop with the Lebanon Crisis Response Plan implementing organizations co-led by UNHCR, UNDP, OCHA facilitated by HAP to develop strategies and related workplan for the implementation of the accountability component of the LCRP, coming out of several missions led by HAP in 2014- 2015
Ukraine : request from NGO consortium represented by Helpage to set up accountability mechanism
Lots of advocacy needed to build sufficient trust with operational teams so that they commit to change operational modes and include AAP/ PSEA
Discussions needed to embed AAP/ PSEA with clusters and coordination bodies in operations
Notes: Challenge :

## Slide 5
Objective 2.2
Capitalizing on Protection and AAP/PSEA synergies
Identify common areas and work closely in: training/capacity building actions, field missions and other actions to improve both areas
Capitalizing on Protection and AAP/PSEA synergies
Done to date?
Accountability, as one of the pillar of Protection Mainstreaming, is explored in the Protection Mainstreaming training package being largely disseminated.
Still to be done?
Work Stream 2
Operationalizing AAP/PSEA in country-level activities and provision of technical support
Leads
Contact: Scott Pohl and Protection Mainstreaming TT
Opportunities : shared concern between both Protection and AAP/ PSEA + Upcoming person from the Protection Mainstreaming Task Team to join the AAP/ PSEA TT
Ensure participation of field-based AAP focal points to the upcoming 6 Regional ToT on Protection Mainstreaming
Ensure the integration of AAP/ PSEA considerations into the checklists to be developed with global clusters.
Ensure protection mainstreaming/ AAP/ PSEA issues coming up from fields mission are shared.
Document field examples demonstrating the essential linkages between Protection mainstreaming and AAP
Ensure AAP/ PSEA is included into HCT country level protection strategies. (with GPC support cell)
Notes: Domitille pour DRC
Kenya : Rita Mwai
Afrique de L Ouest
Middle East : ( Massimo Lebanon)

## Slide 6
Objective 2.3
Help desk
Technical support/ helpdesk function on AAP/ PSEA : helpdesk-aap-psea@unhcr.org
Presentation of helpdesk during the AAP webinar on April 16th
Flexible structure for the first phase, with IASC Task Team Coordinator receiving requests and dispatching to experts
Adaptation of the helpdesk structure to the demand
Further dissemination of flyer after an initial period to test our ensure quality of responses and systems
Done to date?
Concept paper
Flyer for dissemination
Preparation of the related pages on HAP website and link with PSEA FAQ
Informal contacts with AAP and PSEA experts
Still to be done?
Work Stream 2
Operationalizing AAP/PSEA in country-level activities and provision of technical support
Lead
Contact: David Loquercio
Need to expand the list of potential contributors to the helpdesk. Mix of UN/ INGO/ Academics and Global/ Field perspective

## Slide 7
Notes: Other PSEA questions On the flyer :
What are the basic mechanisms/structures that need to be in place (Minimum Operating Standards) - Where can I find practical guidance, tools and resources (pseataskfroce.org)

## Slide 8
Objective 2.4
Joint Preparedness
Community awareness of AAP/ PSEA
Include AAP in Disaster Risk Reduction planning , joint preparedness and awareness raising of rights with communities
Done to date?
Kenya /Pakistan : Action aid / local partners/ government and communities have developed Preparedness plans localised to fit specific communities needs through participatory consultative processes involving all stakeholders.
Awareness raising on rights is done by participatory appraisal techniques at community level ( community/ local civil society/government stakeholders). The tool used is PVA (Participatory Vulnerability Analysis.)
Still to be done?
Work Stream 2
Operationalizing AAP/PSEA in country-level activities and provision of technical support
Lead
Contact: John Abuya
Challenges : AAP is sensitive issue within Governments and therefore a challenge. Advocacy in this regard is a long process.
Action Aid, CAFOD, Christian Aid, Concern, Oxfam and Tearfund have launched the “Shifting the Power” project : Bangladesh, DRC, Kenya, Pakistan and Ethiopia over 3 years
The vision is to support local actors to take their place alongside international actors in order to create a balanced humanitarian system that is more responsive and accountable to disaster affected communities.

## Slide 9
Objective 2.5
Civil society, National NGOs and Implementing Partners’
involvement in AAP/ PSEA
Raising awareness and Including civil society, National NGOs, Implementing partners in the AAP/ PSEA discussion
Advocacy work with government and civil society in Pakistan / Haiti (Action aid and other members from forum on PSEA/ and Protection and AAP)
AA Kenya to showcase work on AAP in Core Humanitarian Standards meeting to be held in Nairobi in June.
Suggested paper to be developed with other stakeholders exploring “why can the resilience approach be an opportunity to promote AAP/ PSEA ? ( to be discussed )
Done to date?
Training on AAP conducted by Action Aid in Palestine, Myanmar, Pakistan, Kenya for INGO communities and local partners.
Development of People centred accountability framework and roll out in Pakistan
AA Kenya sharing their work on Accountability at the Inter Agency working group .
Resource book Guideline and tools on accountability for emergency response work
Still to be done?
Work Stream 2
Operationalizing AAP/PSEA in country-level activities and provision of technical support
Lead
Challenges: Lack of knowledge on the ground about Humanitarian standards/ Lack of resources for training.
Opportunities :The resilience building discussion is an opportunity to promote AAP.
Contact: John Abuya

## Slide 10
Objective 2.6
Clusters participation/ support to clusters
Increase engagement of clusters in the Task team+ provision of operational support to clusters for implementation of AAP/ PSEA in their work
Finalise draft checklist for clusters and pilot them.
Provide support to clusters to operationalise AAP in specific emergencies, relying on already deployed staff
Run a workshop with Global Cluster Coordinator focussing on AAP/PSEA
Done to date?
Global Cluster Coordinators draft workplan includes an objective on collective AAP
TT participation to the Early Recovery Technical Working Group on AAP
Set of Draft checklists to include AAP in clusters work
Still to be done?
Work Stream 2
Operationalizing AAP/PSEA in country-level activities and provision of technical support
Lead
Contact: Francesca Fraccaroli
Working group to develop the checklists, ensuring coherence with IASC CAAP tools+ CHS

## Slide 11
Objective 2.7
AAP/PSEA for RC/ HCs
AAP/ PSEA incorporated into RC/ HCs roles and responsibilities in HCT operation, in HC compacts and into training material
Check proportion of HC/RC having AAP/PSEA as an objective in 2015 individual compacts
Support operationalization of AAP PSEA by providing technical support at country level for at least 2 countries.
Done to date?
AAP included as an objective in some Humanitarian Coordinators Compacts
Session on AAP in HC’s annual workshop
AAP included in the HC/RC manual (still under review)
Webinar on AAP organised by STAIT team in English and French, with HC/RC facilitation and/ or participation
AAP included in HCT self assessment indicators designed by STAIT team
Still to be done?
Work Stream 2
Operationalizing AAP/PSEA in country-level activities and provision of technical support
Leads
Contact: Francesca Fraccaroli / Lydia Van De Fliert
Long process to finalise and approve documents such as the HC/ RC manual.
The Compact is a personal “contract” between the ERC and the HC, to:help HCs identify and focus on priorities and provide a documented basis for mutual accountability
HCT : Humanitarian Country Team
RC/HC: Resident Coordinator, Humanitarian Coordinator
STAIT: Senior Transformative Agenda Implementation Team

## Slide 12
Objective 3.1
Advocacy Awareness raising/ recruitement policy
Advocacy/ Awareness raising and recruitment policy
Oxfam to send the one-pager on PSEA good practices for donors
Confirmation is needed to on who will participate in the print or toolkit aspects of the campaign and commitment of funds to print/produce the toolkit.
/4. review in light with the new SG report on PSEA
Done to date?
An update is forthcoming from Oxfam
Leo Burnett has presented concepts and there is agreement on the print aspects/toolkit PSEA campaign
Still to be done?
Leads
Contact: Yasna Uberoi
Challenges/ opportunities ?
Work Stream 3
PSEA activities
1.Develop a one-pager on PSEA good practice for donors.
2.PSEA campaign.
3.Monitor the implementation of recruitment policy recommendations.
4.Follow-up on existing PSEA Task-Force work on recruitment.

## Slide 13
Objective 3.2
Community Based Complaints Mechanisms Pilots
PSEA pilots implementation, lessons learning and recommendations for replications
Done to date?
IASC initiative, with IOM coordinating at global level. interagency complaints mechanism in emergency setting.
Still to be done?
Work Stream 3
PSEA activities
Leads
Contact: Tristan Burnett
Opportunities:
Project builds upon SGBV program in Dollo Ado
Possibility to engage local AAP working group to support the management of non-SEA complaints.
Ethiopia : Pilot through UNHCR and IMC in Melkadida refugee camp in Dollo Ado. (Somali refugees)
Monitoring platform tracking complaints
Multiple entry points for reporting complaints: 73 to date. (6 related to PSEA under investigation)
Two-fold prevention, targeting :
  beneficiaries : “tea talks”+ large scale events
  humanitarian staff: code of conduct + training
DRC: Save the Children is the lead agency implementing in North Kivu. Implementation delays: insecurity and funding
SOPs are still not endorsed at field level and may need to be addressed at the global level, to facilitate replication and avoid duplication of efforts
Learning is being collected, highlighting for instance the need to work with government counter-parts from the start, or with traditional justice actors. A workshop will collect lessons learned end of 2015

## Slide 14
Objective 3.3
PSEA included in organisation recruitment processes, policies and performance appraisals
Key language developed and disseminated for inclusion of AAP/PSEA responsibilities in staff performance appraisal+ partner training package
UNICEF DHR focal point for was just recently assigned, so the work will resume for this stream, including coordination with IOM UNHCR Oxfam and DFS, in support.
Any update on including AAP PSEA into partners training package ?
Any update on “Monitoring of recruitment Policy?“
Done to date?
UNICEF has integrated AAP and PSEA in partnership agreements at field level.
UNDP has shared PSEA specific language, and agencies will see how to adapt it to their own recruitment process
Still to be done?
Work Stream 3
PSEA activities
Lead
Contact: Sipi ?
Challenges : work will now resume since UNICEF DHR is in place.