## Workplan 2016
Strategic Pillar | Activity | Outputs/Deliverables | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec
Build human resource capacity | Develop and conduct training for SAFE WG Energy Expert Roster. | 10 energy experts trained and prepared to deploy in emergencies | June: Kenya (tentative)
| Host annual, global training workshop on energy access in humanitarian settings for field staff, private sector partners, government representatives, and NGO partners. | 50 humanitarian field staff, private sector partners, and/or NGO staff trained in humanitarian energy topics | June: Kenya (tentative)
| Create database of online courses and trainings on energy access in humanitarian settings. | 1 online course available on energy access in humanitarian settings | bar: Sept to Oct
Commission research and build evidence | Conduct and publish study on the impact of fuel and energy technologies on incidence of gender-based violence. | 1 GBV study report published | bar: April to June
| Hold event in DC to convene GBV experts and raise awareness on relationship between GBV and fuel/energy access. | 1 GBV event held with at least 25 participants | bar: Aug
Provide technical support, tools, and guidance for implementation | Each SAFE WG member provides ongoing technical support and advice in their area of expertise for implementing agencies. | N/A
Coordinate the sector and share information | Formalize and lead SAFE Humanitarian Working Group to coordinate energy activities globally and nationally. | N/A | Sept: NYC
| Update and maintain SAFE WG resource library, program database, & social media. | 50 new resources and/or projects added to SAFE WG website | bar: Jan to March
| Coordinate global energy emergency response for any new crises (timeline entirely dependent on emergency). | 1 new coordination website page created per major emergency
Advocate for the sector and build partnerships | Create 2016 workplan and update 2020 advocacy strategy for SAFE Humanitarian Working Group. | 1 workplan for 2016 | bar: Jan to Feb
| Support development of National SAFE Humanitarian Working Groups to ensure local coordination and effectiveness. | 1 functioning national SAFE Working Group | bar: Jan to Feb
| Influence and participate in WHS; host side event on how to effectively integrate energy into response. | 1 side event on energy at WHS | May: Turkey
| Work with academic, peer-reviewed journal to develop an issue that focuses on research and policy on energy access in humanitarian settings. | 1 peer-reviewed journal issue on energy in humanitarian settings | bar: Jan to March
| Strengthen relationship w/ at least 2 major humanitarian partners and target an additional 1-2 for membership in SAFE Working Group to broaden knowledge and awareness on energy programming options. | 1-2 new large humanitarian implementing agencies join SAFE WG
| Formalize the SAFE Working Group in IASC so energy is a component of the formal humanitarian system. | N/A | Feb: NYC; March: NYC
| Showcase energy success stories and innovations. | 1 booklet of case studies on successful humanitarian energy projects and innovations
| Advocate with clusters to more formally recognize and work on fuel/energy. | 2 clusters add materials on fuel and/or energy technologies to their website
| Research how to better integrate energy into the MIRA and other post-disaster needs assessments, as well as funding mechanisms such as the CERF. | 1 concept note on activities needed to get energy incorporated | bar: April to May
Mobilize resources | Fundraise for energy access in humanitarian settings to ensure innovations are piloted and successes are scaled up. | $1 million raised for projects to scale up energy access in humanitarian settings