DRAFT WORKLAN: INTER-AGENCY STANDING COMMITTEE TASK TEAM

ON STRENGHTENING THE HUMANITARIAN DEVELOPMENT NEXUS IN PROTRACTED SETTINGS

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Priority | Objective | Activities | Time Frame | Expected Output | Output Indicators | Resources Needed | Agencies Commitment |
| Develop, Support, and champion humanitarian action in complex protracted emergencies requiring strong, effective & predictable collaboration between Humanitarian, Development, Peace and Security Actors | 1. Establish Common Normative Understanding/ Narrative of HDN in Protracted Situations | * 1. Develop Draft Criteria of HDN in protracted emergencies. | Q3 2016 | IASC Position Paper on Humanitarian Develop Nexus (by end Q4 2016)  Mapping of Existing operational and guidance documents. (by end Q4 2016)  IASC-UNDG Principles of Resilience(by end Q1 2017) | -Background Document on Typologies/ IASC Reading of HDAG Paper  -minutes from TT meeting dedicated to discussing elements of HDN | - small group of TT members to draft Position Paper | UNDP/WHO  UNDP/WHO  FAO/WHO |
| **1.2.** Develop Typologies of Response Scenarios in Protracted Settings (including Area Based Prog.) | Q3 2016 |
| **1.3.** Develop revision Humanitarian Principles of Resilience | Q1 2017 |
| **1.4.** Develop Joint Framework for collective Engagement in Protracted Crises | Q1 2017 | -minutes from joint retreat reflections  - Draft joint IASC-UNDG workplan | - small group of TT members to draft Principles | WHO/UNDP  WHO/UNDP/PBSO |
| **1.5**. Joint Retreat with UNDG WG on Transitions | Q4 2016 |
| 2. Establish and Maintain Compendium of Best Practices related to HDN | **2.1**. Conduct Lessons Learned Exercise from the field | Q2 2017 | Compendium of Best Practices Report (by end Q3 2017) | # of case studies documented  -report on the Survey and recommendations | -Members time to connect with their focal points in various countries  - small group of TT members to draft the report | ICVA/ InterAction |
| **2.2**. Global Survey of field practitioners | Q1 2017 |
| 3. Produce Guidance for Operationalizing the Approach | **3.1**. Produce Draft Adapted Operational Guidance | Q2 2017 | IASC-UNDG Field Guidance for HDN implementation (by end Q4 2017) | -minutes from joint retreat reflections  -IASC/UNDG Guidance for Operationalizing HDN Approach | - Members time to lead small draft team for Reference Document Sections  -small group of TT members to draft the Operational Guidance | URBAN  EDG  CLUSTER/ER  RG ON DISPLACEMENT  TT ON AAP/PSEA  TT ON FINANCING |
| **3.2**. Retreat with UNDG WGT on draft Operational Guidance | Q1 2017 |
| 4. Adapted IASC Response Protocols for protracted emergencies | **4.1** .1Conduct Initial Analysis of Transformative Agenda Protocols and related Guidance documents, and  4.1.2. Conduct Initial Analysis of UNDAF and related Guidance | Q3 2016 | IASC Reference Document: ‘Response Protocols in Protracted Crises’ (by beginning Q2 2017) | -report on the mapping exercise and recommendations  -minutes from the Retreat  -Reference Document | - Members time to lead small draft team for Reference Document Sections (TA pillars + Exploded HPC components)  - small group of TT members to draft Sections of Reference Document | UNDP/WHO  LEADERSHIP (OCHA)  COORDINATION  ACCOUNTABILITY   * HPC * PREP * AAP * Needs Assess: |
| **4.2** HDN Task Team retreat on 4.1 | Q1 2017 |
| **4.3** Produce Draft Protocols | Q1 2017 |
| **4.4** Revise Draft Adapted Protocols following field survey, review process, lessons learned (Activities 3.1, 3.2) | Q3 2017 |