|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Result 1: Promote Policy Coherence and Guidance** | | | | | |
| **Work Stream, Results and Activities** | **lead** | **partners** | **timeline** | **origin** | **observations** |
| 1.1 Develop key messages for Principals on the new way of working/HDP nexus   1. Dissemination of key messages 2. Inclusion of HDP nexus in strategic frameworks under development | Co-chairs IASC TT  Support team of the UNWGT co-chairs |  | First half 2017 | AP 7.4 | 2 pager think piece, building on existing UNWGT products |
| 1.2 Develop common outcome indicators to assess progress and implementation on the HDP nexus | UNDP/  OCHA | MPTFO | 2017 | AP 3.2 | Should ideally be linked to financial flows using a) SDG goal, output, target-IATI b) TOSSD (OECD/DAC)  This is a long term agenda/vision: should have indicators at a system level |
| 1.3 Promote policy coherence and guidance with the IASC TT, including through a second joint retreat |  |  | 2017/2018 | AP 3.3  2016 WP | Should be focused on country self-selection. |
| 1.4 Hold regional and country level workshops on the HDP nexus  *­* | UNDP /  OCHA | ILO | 2017 | AP3.5 |  |
| 1.5 Provide input to intergovernmental and interagency processes, including policies, processes and discussions such as: i) SDGs and 2030 agenda (incl. MAPS, Universality) ii) Integration (incl. ISG, IAP); iii) Peacebuilding (incl. SPG, PBF); iv) Delivering as One and UNDAF Guidance roll out; v) RPBA/PDNA; vi) UN-WB Partnership; vii) ECOSOC Transition Event viii) Land and Conflict  ix) IAP review  x) The SG’s report on Sustaining Peace | UNWGT |  | 2017 | 2016 WP  AP 5.3 |  |
| **Result 2: Collaboration on financing to reduce financial fragmentation** | | | | | |
| **Work stream, Results and Activities** | **lead** | **partners** | **timeline** | **origin** | **observations** |
| 2.1 Map financial flows and pooled fund mechanisms that support the HDP nexus | MPTFO/ WB | HFTT/ OECD-DAC/EU |  | AP 4.1; 2.3  2016 WP | Spectrum of financial instruments was already mapped jointly by WB/OECD-DAC/MPTFO pre-WHS |
| 2.2 Work with financing “champions” on financing options that bridge the HDP nexus and reduce financial fragmentation. | OCHA/UNDP | HFTT/MPTFO |  | AP 5.1  AP 4.3 | Identify donors and other champions e.g. Denmark, WB, OECD |
| 2.3 Develop standardized (legal) tools for fund flows in context of UN mission – UNCT transition planning | UNOPS | DPA/DPKO/ DFS, OLA, UNDPs | 2017-18 | New | Related to UNCT planning (non-core funding) and mission planning (assessed budgets). |
| 2.4 Advocate with UN agencies to provide country level financial data to facilitate HDP financial mapping and planning, | Co-chairs | MPTFO |  | New | Need for overall sense of UN financing flows in order to be able to make the best financing decisions to attain collective outcomes. |
| 2.5 Inputs to the country-level support package on funding to financing including  a. UNDAF companion piece on “From Funding to Financing”  b. Development Finance Approaches & tool for country-level finance mapping.  c. Training package on Funding to Financing | DOCO/MPTFO | HFTT/JFTT |  | 2016 WP | A companion piece to the UNDAF guidelines is already in production, which outlines a number of development finance approaches  This work will entail putting together a training package on funding to financing. |
| **Result 3: Partnerships** | | | | | |
| **Work stream, Results and activities** | **lead** | **partners** | **timeline** | **origin** | **observations** |
| 3.1: Explore entry points for the implementation of the New Way of Working in multi-partner processes, such as the New Deal, MAPS, Grand Bargain and RPBAs |  | MPTFO |  | AP 6.2 |  |
| 3.2 Identify and engage with member state champions to engage in intergovernmental discussion to move forward the HDP nexus |  |  |  | AP 5.1 | Such as Denmark, Mexico |
| 3.3 Contribute tothe draft UN-WB study on development and conflict prevention |  |  |  | AP 6.1 AP 6: 3 | Other IFIs? |
| **Result 4: Communication and Advocacy** | | | | | |
| **Work stream, Results and activities** | **lead** | **partners** | **timeline** | **origin** | **observations** |
| 4.1 Draft messages for member states and donors | Co-chairs  IASC TT  Support team of the UNWGT co-chairs |  | First half of 2017  ECOSOC OAS | AP 7.2 | Linked to 1.1  Linked with QCPR and GHD  Common message and harmonized meeting (One Voice) on HDP in UNDG- Partner meeting on joint funding |
| 4.2. Draft Messages to RC/HC | DOCO |  | First half 2017 | AP 7.2  AP 2.2 | Include draft message in UNDAF roll out workshops (This year 20-24 Feb in Nairobi) |
| **Result 5: Field Support** | | | | | |
| **Work stream, Results and activities** | **lead** | **partners** | **timeline** | **origin** | **observations** |
| 5.1 Support the roll out of field based initiatives, including the WB-UN HDPN initiative |  |  |  | 2016 wp  AP 2 |  |
| 5.2 Mapping of existing capacities and gaps to implement the HDP nexus at the country level in select pilot countries | UNHCR | DPA  WFP  FAO  DOCO  PBSO  UNDP  OCHA  DPKO  OHCHR  IASC TT | 2017 | AP 1.1  AP 2.3 | To determine who to support  Self-selection and invitation: separate activity on selection?  Timing of field support? |
| 5.3 Mapping of status of implementation at the country level |  | DPA  WFP  FAO  DOCO  PBSO  UNDP  OCHA  DPKO  OHCHR  IASC TT |  |  |  |
| 5.4 Review of the Capacity of Agencies, Funds and programmes to sustain peace completed, and follow up to the study provided | UNDP, WFP, PBSO |  | First half 2017 | 2016 WP | ODI study  Link to think piece  Gap analysis |
| 5.5 Provide input into system wide functional capacity mapping (mandated by QCPR) |  |  | First half 2017 | QCPR |  |
| 5.6 Inter-agency technical support provided to self-selected countries to support joint analysis and joined up planning, and advise on financing modalities. |  | MPTFO | 2017  2018 | AP 2.4  AP 2.5 |  |
| 5.7 Compilation of lessons learned and good practices on the new way of working | UNDP  OCHA |  |  | AP1.3 |  |
| 5.8 Identification of concrete programmatic entry points where the new way of working could be piloted at country level. |  |  |  | AP 2.6 | Linked to 5.7 |
| 5.9 Support joint implementation of existing guidance and policies on conflict analysis and conflict-sensitive programming through coordinating inter-agency technical and/or programmatic support to selected countries based on demand for support and on findings of horizon scanning or conflict analyses | Task Team on Conflict Prevention (co-chaired by UNDP and UNICEF) | Inter-agency country specific mechanisms (e.g. ITFs if present) |  | 2016 WP | Flagged in 2016 WP key 2017 deliverable |
| 5.10 Develop and implement One UN Strategic Framework in interested transition countries |  |  |  | UNDG | UNDG strategic priority 2017-2020 |