## Sheet1
GRG AWP 2018
Objective 1: Guidance on and Accountability to Gender Equality - Develop, test and roll out tools for use by the humanitarian community to integrate gender into policies and programming and create accountability mechanisms for monintoring compliance.
Outcome 1.1 - Dissemination and socialization of the 2017 IASC GiHA Policy and AF |  |  | Timeframe |  |  |  | Notes
Activities | Lead | Focal Points (lead and supporting organizations) | 1Q | 2Q | 3Q | 4Q | Care, OCHA, UN Women, HIAS and Women Deliver will form a working group to undertake the activities under this outcome.
1. Launch of GiHA Policy and AF (SG?) | Co-chairs | Co-chairs++ | x
2. Introduction from principals to country reps - letter - Joint statement | Co-Chairs | GRG Sec. | x
3. Guidance notes on roles and responsibilties and other advocacy materials | UNW | UN Women | x
4. Presentation to RC/HC annual retreat | Co-Chairs | Co-chairs | x
Outcome 1.2 - Implementation of GiHA Policy and AF |  |  | Timeframe
Activities |  | Focal Points (lead and supporting organizations) | 1Q | 2Q | 3Q | 4Q
1. CN on Gender Desk Function & GRG Role |  | UN Women, OCHA & UNFPA | x
2. Support implementation model in 2 countries |  | UN Women, OCHA & UNFPA | x | x
Outcome 1.3 - Finalization and Roll Out of Handbook |  |  | Timeframe
Activities | Lead | Focal Points (lead and supporting organizations) | 1Q | 2Q | 3Q | 4Q
1. Finalize handbook and launch | UNW | UNW & Oxfam | x | x
2. Print and disseminate | UNW | UNW, OCHA & Oxfam | x | x
3. Launch | UNW | UNW, OCHA, IASC Sec | x
4. Roll out training | UNW | UNW, UNFPA & Oxfam | x | x | x | x
5. Elearning | UNW | UNW & Oxfam | x | x |  |  | Elearning draft will be circulated to GRG for comments; the tool will be finalized in May
Objective 2: Engagement and Knowledge Management - Provide the humanitarian community with timely and practical information to help meet its commitments to gender equality.
Outcome 2.1 Engage in information sharing with Global Stakeholders |  |  | Timeframe
Activities | Lead | Focal Points | 1Q | 2Q | 3Q | 4Q
1. Side events (x2) at global humanitarian themed event (e.g. CSW, ECOSOC, Women Deliver etc) | WRC (Women Deliver), UNW (CSW), UNW (ECOSOC) | UNW, WRC, Oxfam |  | x | x | x | One side event at CSW was already done.
2. Engage with Hum Data Centre | Co-chairs | Co-chairs |  | x
Outcome 2.2 Update and roll out SOPs for L3 and other large scale emergencies |  |  | Timeframe
Activities | Lead | Focal Points | 1Q | 2Q | 3Q | 4Q
1. Reach out to L3 review team (John Ging, Rudy Miller) for recommendations and capture any other inputs from relevant stakeholders | Co-Chairs | Co-chairs | x | x
2. Review and update GRG L3 SoPs, based on inputs | OCHA | IMC, UNW, UNFPA |  | x | x |  | To make the updated L3 SoPs compatible with the New Way of Working
Outcome 2.3 Contribute gender indicators, reporting and accountability to GB and WHS commitments |  |  | Timeframe
Activities | Lead | Focal Points | 1Q | 2Q | 3Q | 4Q
1. Contribute to gender reporting for Grand Bargain | UNW | CARE, UNHCR | x | x
2. Identify field examples to determine impact of gender lens to particular crisis for advocacy | UNFPA | UNW, Oxfam, OCHA |  |  | x
3. Propose gender Qs that all WHS stakeholders must respond to PACT | OCHA | OCHA | x
Objective 3: Coordination and Leadership - Actively engage and coordinate with all bodies and structures of the IASC to ensure that they encorporate gender equality into relevant aspects of their work in a manner complementing efforts by counterparts.
Outcome 3.1 Act as gender expertise resource on gender equality programming to the IASC and its subisdiary bodies |  |  | Timeframe
Activities | Lead | Focal Points | 1Q | 2Q | 3Q | 4Q
2. Map GRG organizational presence with IASC subsidiary bodies | GRG Sec | GRG | x
3. One day meeting with other subsidiary bodies | Co-chairs | GRG |  | x
3. GRG particpate in 50% of IASC Subsidiary Bodies | GRG Sec | GRG | x | x | x | x
4. GRG to provide input to PwD TT Guidelines | WRC | UNICEF | x | x |  |  | Ongoing
5. GRG to provide input to HFTT Financing Gap study | UNW | UNW and UNFPA | x | x |  |  | To examine financing gaps from a gender angel.
6. GRG to provide input to ….
7. GRG to provide input to ….
8. GRG to provide input to ….
Outcome 3.2 Strategize and design greater collaboration between GenCap and GRG to strengthen support mechanisms |  |  | Timeframe
Activities | Lead | Focal Points | 1Q | 2Q | 3Q | 4Q
1. Finalize and articulate relationship between GRG & GenCap and communicate progress so far to DERC | Co-Chairs | Co-Chairs, UNFPA, OCHA | x | x
2. Plan GenCap briefing of GAM in NY with GRG | Co-chairs | Co-chairs |  | x
3. Support roll out of GAM | Co-Chairs | OCHA | x | x | x | x
4. To promote several new tools together, including GAM, the new Gender Handbook, etc | Co-Chairs