## Sheet1
GRG Workplan 2017
Task | Focal Point/s | Timeline
Handbook
Hand over to Oxfam for field testing and input edits | Oxfaxm
Share field testing results with Steering Committee then roll out in 3-4 countries | Oxfam
IASC Gender in Humanitarian Action Policy Update & Accoutability Framework | UN Women
Hiring consultants for Policy Update and Accountability Framework | UN Women
Recruit for Advisory Group for Policy Update (IASC Members) | UN Women
Launch Event for Policy Update and Accountability at GA with a Head of State | Advisory Committee Members
Assess connection to GBV AOR - perhaps think through when there should be x-briefings (roll out?) | UNFPA
ECOSOC Side Event and potentially other Interagency Meetings (e.g., WPS Review, HLPF SDG, GA, G7/8) | TBD | As needed
Share information about events at which GRG Members are organizing panels/side events | All GRG Members
Finalise SOPs for L3 and other large-scale emergency engagement (based on 2015 version) | CARE, IMC, UN Women
Before doing so, review Health Cluster's L3 SOPs | CARE, IMC, UN Women
Include GenCap in review of updated version of L3 SOPs and potientially Gender Advisors for DPA or DPKO | CARE, IMC, UN Women
Contact Ursula Mueller (welcome, feed into 4/5-6 WG) | Co-Chairs | Prior to 3/1/17
Write IASC re IASC / GenCap relationship and accountability | Co-Chairs
Map GRG organizational presence with subsidiary bodies & WGs/EDGs | GRG Secretariat | ASAP
Periodic reporting on IASC Tasketeam on PwD | WRC | Ongoing
Engage with WG agendas and provide input as necessary (how?) | IASC, Co-Chairs | Ongoing
Strategize and design greater collaboration between GenCap and GRG to strengthen support mechanims | Co-Chairs
GenCap briefing of GAM in New York with GRG in April, Policy & Accontability Framework, Handbook | UN Women, UNDP, Oxfam
Plan GenCap-GRG discussion around more regular communication, collaboration and coordinated roll-out | GRG/GenCap SC
Contribute to Gender Reporting Template for Grand Bargain | GRG Advisory Group: UNW, CARE, Oxfam?
Identify GB workstream gender focal points and offer support to GB Secretariat | GRG Advisory Group: UNW, CARE, Oxfam?
Identify definitions for key GB & WHS terminology to determine if further work required | Oxfam, Concern Worldwide
Join Informal Friends Group of Gender in the GB | GRG Membership
Identify field examples to determine impact of gender lens to particular crisis for advocacy, roll out | UN Women
Share and group GRG member group commitments under WHS, GB | GRG / Secretariat
Propose gender questions that all WHS stakeholders must repond to in PACT reporting - tap into GB (line 25)? | OCHA