## Notes
NOTES
The TOR of the GB sub-group on Linking Humanitarian cash and Social Protection envisages actions in 5 engagement areas (1. Mapping; 2. Coordination; 3. Knowledge Management and Learning (KML); 4. Advocacy; and 5. Guidance). In early 2019, the GB subgroup held a workshop, during which a tentative workplan for the subgroup was drawn up. This proposed a range of activities under the 5 engagement areas. For some of these activities, member agencies (DFID; UNICEF; IFRC) committed to lead them. For the rest, no lead or contributing agencies were assigned.
In 2020, the subgroup co-leads funded a consultancy to update and refine this workplan, based on inputs from subgroup members. A consultation process with all subgroup members was led by Gaby Smith, financed by the subgroup co-lead DFID. All subgroup members were contacted and requested to engage in a call (or to share inputs by email). In the consultations, members shared i) the status of any workplan activities that they had previously committed to lead; ii) whether they had worked (either collectively or independently) on any of the other activities proposed in the workplan; and iii) whether going forward they would be interested to lead or contribute to other proposed activities listed in the workplan. Members also shared recommendations on how the work of the subgroup could be managed going forward.
21 members IFRC, ICRC, BRC, FAO, OCHA, UNHCR, UNICEF, DFID, USAID, Switzerland, World Bank, ECHO, DEVCO, Oxfam (CCD), WVI, CARE, NRC, CashCAP, CALP, SP.org (Cecile); 6 members responded by emailed survey (Christian Aid, IRC, Relief Intl, DFAT, Ireland, GIZ). 7 members responded that they are not currently working in this space - but are interested in the topic and keen to remain part of the subgroup (Canada, Japan, Finland, Belgium, Czech Republic, Norway, Spain).
The workplan consultations yielded common agreement from subgroup members that i) the scope of work of the subgroup proposed in 2019 was too ambitious and unrealistic; and ii) some of the actions proposed in the workplan 2019 were too vague, not being well defined as activities or in terms of any expected end result. For example, "Work with national field staff to promote a collaborative approach". Indeed if we compare workplans of other GB sub-groups, these have a smaller number of clear, well defined activities. There was also common agreement that any activity listed under the workplan of the subgroup should demonstrate added value of the subgroup (ie its members working collectively as a subgroup to achieve results). Some of the activities listed in the 2019 workplan were being taken forward by a subgroup member - BUT through other pre-existing projects and wider networks. They were not conceived of as a sub-group activity and it was difficut to see how the subgroup as a subgroup could add value to these. For example, "Link SP and Humanitarian actors in 6 Sahel Adaptive Social Protection Program (ASPP) countries" - which is an ongoing programme of WB, WFP. Or "Add module in Inter-Agency Social Protection Assessments (ISPA) on fragile settings" - which was an ongoing action of the SPIAC B group.
This workplan draft for 2020-2021 is the output from these consultations. It responds to the feedback from members to be more focused and strategic. It has removed any proposed actions from the 2019 workplan that were not yet already started and that were not well defined as 'sub-group' activities. It has also included some new proposed activities (in RED). These were proposed by subgroup members, as part of Gaby's consultations, or during separate consultations under the KML engagement area that were held in 2019 (led by Isabelle Pelly and Zehra Rizvi - new KML focal point is Lois Austin). The objective is to focus attention of the group on a smaller number of specific deliverables where the group can have greater collective value.
For all activities that have started, the workplan provides an update on their status and timelines as well as which organisation is taking the 'lead' role and which members are or can contribute. For new activities, a lead organisation and potential contributors is proposed (NOTE: a 'lead' agency commits to i) spending time to manage the activity and ii) coordinate the inputs from other members that are contributing to the activity, as needed. For those activities where funding is needed the agency commits to iii) proactively seeking funding.)
The period of the draft workplan is from present date (Jul 2020) until end of 2021. Grey timeline = confirmed, for ongoing and funded activities. Green timeline = TBC, for as-yet-unstarted activities or potential continuation of current activities into 2021.
In the workshop this proposed workplan will be discussed and finalised. Members are invited to share any questions they have, and any feedback. The proposed inclusion of the new activities will be discussed. Members can highlight activities that they would be interested to contribute to (or to help to lead). Members will also be invited to share any activities that they think are missing and that the sub-group can add value to, and their inclusion can be discussed (keeping in mind that the draft workplan is already the result of detailed consultations and the scope of the workplan must remain manageable).

## Draft workplan 2020
Grand Bargain Cash Workstream Sub Group on Linking Humanitarian cash and Social Protection: Draft Work Plan 2020-21
Activity |  | Existing or new activity? | Funding required | Funding secured? | Status | Lead | Contributors | 2020 | [5 empty] | 2021 | [11 empty] | Notes
[8 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Notes following co-leads call
0 | Coordination of Sub-Group | New, proposed | Yes | Yes until Oct 2020 (DFID BASIC); thereafter to be part of the responsibilities of UNICEF staff member | On-going | DFID till Oct 2020; UNICEF from Oct 2020 | All subgroup members leading on the below workplan activities; plus any other interested Sub-group members | [18 empty] | Participants in the workplan consultations suggested that the subgroup needs to be more actively convened, which requires resourcing. This is how other GB subgroups are managed. The DFID BASIC-funded consultancy to develop this workplan (led by Gaby) includes time for a quarterly update to the plan Oct 2020. Thereafter the role will be integrated into the workplan of staff member of co-lead agency. Co-lead definition of the role: Maintain subgroup members' list, attend GB meetings, track progress and follow up on workplan activities. Organise sub-group meetings and events, coordinate with other GB workstreams and groups as needed. Report on sub-group progress and activities to the GB.
ENGAGEMENT AREA 1: Mapping and Analysis of Existing Linkages between CVA and SP
1.1 | Conduct a mapping of linkages between humanitarian CVA and social protection in different contexts, and analyse to understand gaps, barriers and opportunities. | Existing | Yes, human resource for managing the mapping and any analysis | No - but SP.org/ODI possibly interested to support development of a funding proposal | Mapping started (CaLP) Jan 2020; COVID-related mapping activities; analysis will start after initial mapping | CaLP | Potentially all subgroup members can contribute to this (during consultations, contributions were committed to by CashCap, IFRC, CARE, ICRC, ECHO, DFAT, OCHA, Ireland, Oxfam/CCD, WVI, NRC, Oxfam, ODI, UNICEF. | [18 empty] | CaLP started to lead a workstream on this in early 2020. CaLP's early discussions with subgroup members on this, plus consultations with subgroup members to develop this workplan, have highlighted a need to flesh out further the final expected outputs from this exercise - i.e. what the mapping exercise aims to achieve. Collective feedbackis that it must go beyond a list of initiatives to develop some form of living document that provides added value through some form of analysis of entry points and/or as a repository for resources. CaLP (and others) can seek to mobilise the resources that this would require and CALP is in discussion with SP. org on further expansion of this work. Other mapping activities that can feed into this include: UNICEF's mapping of COVID responses (KMLfocal point); IPC; BRC. | bar: 2020 Jul to 2020 Dec
ENGAGEMENT AREA 2: Coordination between humanitarian assistance and social protection actors in countries
2.1 | Adapt Cash Working Group ToRs to incorporate linking with national SPWGs where they exist. | Existing | No | n/a | Some ad hoc activities of individual members to date - needs to formally start as a Subgroup activity | CALP? | CashCAP, potentially WVI, IFRC | [18 empty] | To date, some ad hoc activities have been happening, unilaterally implemented by different agencies and not coordinated as a Subgroup activity under this workplan. CaLP has been a lead agency to date and CaLP (Julie) said that going it could lead this activity on behalf of the subgroup. CaLP has already been promoting the inclusion of clauses on linking with social protection into the ToRs of national CWGs where relevant (e.g. Role in assessments; linking CWG with SPWGs). Other subgroup members are also committed to support this. CashCAP can share details of which countries it will support a ‘CWG lead’ deployment, and can also include these clauses in its deployment TORs. Other subgroup members whose country offices play an active role in chairing CWGs around the world (eg Red Cross; WVI) can also promote these.
2.2 | Develop strategic-level recommendations to the IASC to foster coordination between Humanitarian and social protection actors in countries | New, proposed | No | n/a | Not yet started (new activity) | OCHA | ?? | [18 empty] | This is a new proposed activity from OCHA, which could build on 2.1 above. OCHA highlighted the key role that the subgroup, working collectively, could play in supporting changes to global response coordination processes, to systematically foster linkages with SP. There is now reference to social protection in the HRP strategic planning process but there is still a lack of guidance in terms of how this is done in practice, or on actions as part of assessment and response analysis. The interagency steering group in Geneva is working on the RA side, and OCHA is happy to promote further focus on linkages with SP within this group on behalf of the Subgroup. The Subgroup could collectively decide on a few concrete asks for inclusion in the HPC guidance.
ENGAGEMENT AREA 3: Knowledge, Management and Learning
3.1 | Deliver webinars to share and discuss learning | Existing | Yes | Yes until end Nov 2020 (DFID). | On-going. | UNICEF (KLM focal point Lois Austin) | All subgroup members | [18 empty] | Currently the KML focal point under UNICEF is facilitating 1 webinar per month, with confirmed content and budget to Nov 2020. This activity can continue in 2021 if there is Subgroup interest, and if members are interested to be invovled in content development. In the workplan consultations, several members (including Irish Aid, CCD, Cash Cap, CARE) expressed willingness to be involved. This activity offers opportunity for a strategic approach that links content of these webinars with other activities of the workplan. | bar: 2020 Dec to 2021 Dec
3.2 | Deliver discussion threads to share and discuss learning | Existing | Yes | Yes until end Nov 2020 (DFID). | On-going. | UNICEF (KLM focal point) | All subgroup members | [18 empty] | These discussion threads have been delivered in 2020 in conjunction with the above webinars. This activity can continue in 2021. Co-leads in discussion with SP.org about developing a specific D group under SP.org in future. | bar: 2020 Dec to 2021 Dec
3.3 | Create and manage a community page for the GB sub-group | Existing | Yes | Yes until end Nov 2020 (DFID). | On-going. | UNICEF (KLM focal point) | ?? | [18 empty] | This has advanced the original activity listed in the 2019 draft workplan ("to explore common communities of practice to bring SP and humanitarian CVA stakeholders together"). Co-leads in discussion with SP.org as the host of other GB workstreams.
3.4 | Generate and disseminate a newsletter | Existing | Yes | Yes until end Nov 2020 (DFID). | On-going. | UNICEF (KLM focal point) | ?? | [18 empty] | Currently the KML focal point under UNICEF develops and circulates a regular newsletter on linking humanitarian cash and SP, confirmed until Nov 2020. This activity can continue in 2021 if there is Subgroup interest. | bar: 2020 Dec to 2021 Dec
3.5 | Consolidate case studies and lessons learned | New | Yes | Yes (DFID funding for 5 case studies until end Nov 2020) | Methodology under development | UNICEF (KLM focal point) - NOTE as a convenor of processes for all 5, however these are to be sub-group owned products | All interested subgroup members. | [18 empty] | Under the DFID-funded and UNICEF-managed KML contract, there is funding to develop 5 case studies that will share experiences and learning from linking SP-CVA in the responses to COVID-19. There will be a common methodological appproach and format for the 5 studies, currently being developed by the KML focal point. It is proposed that each case study will focus on a different thematic issue (the themes proposed will be shared with the subgroup), and that subgroup members will be able to contribute to content development by sharing relevant examples and learning.
3.6 | Update the glossary of terms | Existing | Yes | Yes (DFID) | On-going (DFID workplan consultant, Gaby Smith). | DFID | All subgroup members | [18 empty] | In Gaby's ToRs.
3.7 | Maintain a roster of experts to advice planning and delivery of linkages (has cashcap been asked?) | New, proposed | Yes | ?? | New recommended Activity, for discussion | CashCap? | ?? | [18 empty] | This was a new proposed new activity coming out of the KML consultations. If this is a standalone roster itwould need budgeting for. An option could be to integrate these skill sets into an existing roster - the most obvious being CashCAP deployments. This would need to be discussed with CashCAP.
3.8 | Organise sub-group events to share and discuss learning | New, proposed | Yes | Yes to November 2020 (DFID) | 3 planned in 2020 | IFRC/DFID/ UNICEF (DFID workplan consultant, Emma Jowett) | All subgroup members | [18 empty] | This was a new proposed activity coming out of the KML consultations. In 2020 this will include 3 remote events, as webinars facilitated by DFID's workplan consultant Emma Jowett. The first of these (Jul 2020) will focus on discussing and inputting into the subgroup workplan. The focus of the other two is still TBD. This activity can continue in 2021, either as a series of quarterly remote events or a single face to face event. | bar: 2021 Jan to 2021 Dec
ENGAGEMENT AREA 4: Common positions and advocacy
4.1 | Develop a strategy for global policy influencing in upcoming policy fora | Existing | Yes | Yes to November 2020 (DFID) | Engagement plan of possible events) completed by DFID workplan consultant Gaby Smith. Advocacy priorities are now under identification (KML focal point) | DFID/UNICEF | All subgroup members | [18 empty] | Under the workplan consultations, Gaby Smith gathered inputs from subgroup members on potential events and fora to influence. When consulted on priority influencing messages, members made some suggestions (primarily focused on the thematic area of climate change/disaster response; and addressing needs of the displaced) but highlighted the need to first agree as a group, on the audience(s) and thematic focus for any such position statements. In second half of 2020 the KML focal point will seek subgroup inputs to further develop these. Co-leads are happy to continue funding this activity into 2021 as part of the sub-group KML (area 3) and sub-group facilitation (area 0).
4.2 | Advocacy for influencing global practices | New, proposed | Yes | Yes to Novmeber 2020 (DFID) | Not started. | UNICEF (KML focal point) | ?? BRC; DRC; DFID; CARE; SDC | [18 empty] | This modifies the original activity proposed in the subgroup workplan 2019, to 'link the subgroup with the donor group'. Under this activity the subgroup will actively engage with other Grand Bargain actors and workstreams (or other global practices) and seek to influence them. This is inlcuded in the workplan of the KML focal point, who would be tasked with attending the relevant meetings and leading the engagement on behalf of the subgroup. This activity links from 4.1 above, as it first requires sub-group agreement on which stakeholders to influence and what the priority messages should be. Examples of GB workstreams that could be influneced include the GB Assessment workstream (to advocate on the need to include SP in assessments); the localisation workstream, the cash and gender subgroup, the donor sub-group. | bar: 2020 Dec to 2021 Dec
4.3 | Generate short briefing or advocacy papers, making the case for linkages | Existing | Yes | DFID (3 briefing papers) | 2 delivered, 1 to deliver by Oct 2020 | DFID | All subgroup members | [18 empty] | This was an activity of DFID's workplan consultant, Gaby Smith. Two papers were developed with sub-group inputs in 2020 (related to COVID19). Another 1-pager on the importance of linking will be developed as part of the introduction to the guidance document (see Activity 5.1 below).
ENGAGEMENT AREA 5: Guidance and training
5.1 | Development of guidance matrix - How to link Humanitarian Cash and Social Protection | Existing | Yes | yes (DFID) | Ongoing | DFID | CARE, WVI - other Subgroup members? | [18 empty] | This is include in Gaby's contract (DFID).
5.2 | Develop or refresh training | Existing | Yes | ?? Need CALP to confirm | Not started. | CALP | ?? | [18 empty] | In the original 2019 workplan, there was an activity to "Build the capacity of humanitarian staff on the ground to engage in social protection policy and programming". Nothing has yet been started as a subgroup activity. CaLP is currently considering its strategy for how to move forward with capacity building activities in this space. Potentially this is something that can be developed as a subgroup activity, if there is interest amongst members.
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What being assigned a 'lead' means (what is a 'lead' agency committing to?): the agency commits to i) spending time to manage the activity and ii) coordinate the inputs from other members that are contributing to the activity, as needed. For those activities where funding is needed the agency commits to iii) proactively seeking funding.